Strategy Note on Promotion of Navadhanya in APDMP, 2019-20: Draft

Navadhanya is a poly crop system where seed of crops with multiple duration and canopy are sown at once and harvested multiple times across the year. The crop cover will be there up to Feb/ March. The main advantages of the system are:

- Crop diversification

- Farmers get multiple pulses, millets for household consumption and partly for sale.

- Fodder production per acre increases substantially and lot of biomass is left over after the harvest for grazing of small ruminants

- Enrichment of soil biomass (pulses/ roots and lot of leaf litter)

- Soil cover till Feb/ march in place of the present system that leaves soil barren after November.

- This system is relatively resilient to climate variability and is effective in drought mitigation.

This is suitable for family-farms.

Promotional Strategy in APDMP

Experience suggests that there are 4 main requirements for farmers taking up Navadhanya.

- Easy Availability of seed before the sowing time.

- Promotional campaign explaining the benefits of Navadhanya

- Hand holding at the time of sowing in terms of demonstrating the method of sowing.

- Making the implements (multi-row sowing implements) with bullocks or tractor – available.

Navadhanya must be promoted in all the Living Soil Blocks as it is one of the key strategies of Living Soils.

Activities to be Taken up in the Clusters on Promotion of Navadhanya:

APDMP can work with a target of reaching out to at least 100 acres per Gram Panchayat i.e. 300 acres per FPO or cluster. The following strategic actions may be taken up.

- Initial orientation of FPOs and arriving at crop combinations

  - A meeting of FPO (BOD and the RythuVignana Committee – knowledgeable farmers from different villages)

    - to orient on Navadhanya

    - to arrive at the possible crop combinations with respect to local situations and experiences.

    - To set targets GP or village wise and to fix responsible farmer-volunteers.

- Promotional Campaign:

  - All the FPO members need to be targeted for taking up Navadhanya.

  - Open up a Navadhanya farmers registration process at the CLiCs. For the registered farmers seed packs (on cost basis) of their choice will be made available well ahead of the season.

  - Target small and marginal farmers who have some livestock. And for large farmers – target for limited area.

  - OrganiseNavadhanya video shows / talk at the CLiCs

  - Do wall writings on Navadhanya

  - Can create a navadhanyawhatsapp group and encourage farmers to post their sowing and performance.

  - The Community Organisers in each GP must take the process of registering 100 farmers for their GP for taking up Navadhanya after explaining them in detail. This can also be done in small groups.

- Training of Farmer Resource Persons:

  - Initially identify farmer Volunteers in each village and have a training program for them.

  - These farmer volunteers will take up navadhanya in their own fields and also support CO in mobilizing other farmers and in training them on sowing methods.

- Making Seed Available through CMSS:

  - Constitute a sub-committee in the FPO with interested farmers in steering the Navadhanya program in CMSS.

  - As the crop combinations (and varietal choices) and acreage are finalized, arrive at the crop/ variety wise total seed requirement. Crop duration, canopy structure etc., need to be looked at (these may be different from the notified varieties) while finalizing the varietal choices.

  - In Navadhanya-CMSS only the supplementary crop seeds are provided and not for the main crop.

  - Cost of a seed pack per acre will be around Rs.350; but varies based on the local prices.

  - MVKs procure the seed from different sources- this requires exploring local areas or distant areas based on the type of seed material required; as much as to fulfill the target.

  - The seed is cleaned, conduct germination tests and pack the seed into smaller packs bundled into a larger Navadhanya pack of 5 kg. Seed is packed to meet the indent and not in excess; so that if there is less uptake it can be sold as grain with minimal losses.

  - The work can be assigned to the identified POP households with some one playing the lead role.

  - The seed is sold at the CLiCs and/ or distributed through CMSS if government subsidy is available.

  - If government subsidy is available, then the CMSS protocols of MAO visits/ inspection etc., need to be followed.

- Navadhanya Demonstrations:

  - Organise demonstration of sowing Navadhanya early in the season in each village. Get more farmers for such demonstration. The demonstration must be in the farmers’ fields

  - Through these demonstrations, get at least few farmers skilled in sowing Navadhanya so that they can extend the skills to others.

  - It is important to get Navadhanya practicing farmers for demonstration.

- Making the implements available:

  - The multi-row seed drill (bullocks attached) locally called Jadigem, the blade harrows (Dante) are required for sowing with bullocks. Navadhanya can also be sown with tractors and it requires seed drill.

  - Make these implements available in the Custom Hiring Center. The local implements can be purchased within the Rs.1.50 lakh provision under CHC.

  - These implements will be available for custom hiring.

- Intensive campaign during the sowing season:

  - The period after first rains till the sowing time is most crucial to get more farmers interested and practice Navadhanya.

  - Intensive engagement with farmers (mobile messages, follow up calls from CLiCs, COs – regular visits to registered and other farmers) is much needed. This is the ‘switch’ time for farmers to take a call on navadhanya or not.

- Preparations Required at SPMU & LTA:

  - Communication Material: (to be developed by LTA)

    - A small video that can be shared through whatsapp or for video show at the CLiCs.

    - A brochure on Navadhanya systems explaining the method and benefits.

    - A communication flip-charts for training

    - Design of the Navadhanya Bag (for seeds)

    - A book on Navadhanya (By Sri.Narayanaswamy) is already available; it can be sold at the CLiC centers.

  - Training Requirements:

    - All the LFAs and DPMUs were oriented on Navadhanya during the last year.

    - The following need to be oriented:

      - FA- Agriculture

      - CliC anchor

      - Community organisers

    - Apart from the above each FPO needs to have at least 2 farmer resource persons per Gram Panchayat.

    - Community Organisers need to be trained on the demonstrations as they play a pivotal role at the farmers interface.

    - The following training programs be conducted by each LFA:

      - Orientation program on Navadhanya:

        - for FAs (Ag & NRM), CLiCs anchors and COs

        - Orientation for the FPO BODs or the Committee members (depending on local situation)

      - Intensive training for COs and FA-Ag/NRM

        - This involves field demonstration on navadhanya sowing

        - Resource farmers’ volunteers (2 persons per GP).

    - At the SPMU level :

      - One program strategy meeting with LFAs along with CMSS.

  - Budget Provisions:

    - Community Organiser at the GP level will take responsibility of mobilizing 100 farmers to practice Navadhanya.

    - CHC has already a provision for purchase of local implements

    - LFAs may be allocated some budget for printing communication material.

    - If Dept of Agrl extends subsidy on Navadhanya, the process gets integrated with the CMSS.

    - If subsidy is not extended by the Department, the following budget provisions be made to each FPO towards Navadhanya.

      - Cost of travel for sourcing seed, cleaning and packing of the seed: @ Rs.50 per packet. i.e. for 300 packets. = Rs.  15000 per cluster; total is Rs. 15,75,000/-

      - A provision of Rs.2000 per GP (Rs.6000 per cluster) may be made for the demonstrations (either cost of demos or resource fee as the FA feels appropriate); i.e. a total of 2000 x 315 = Rs.630,000 /- provision be made at the project level for this purpose. This can be treated as capacity building budget.

    - Navadhanya field days:

      - One field day per GP may be organized by the FPO at a locally appropriate time; a provision of Rs. 9000 be made per cluster for the purpose. Total is = 9000 x 105=9,45,000/-

  - A sample of 20 plots in each cluster be taken up for regular monitoring and data collection across the season assessment of the Navadhanya system. This might also include soil sampling.

  - Progress to be assessed as a part of regular MIS.

Summary of the Budget Required

|  |  | Clusters | 105 |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | GPs | 315 |  |  |
| S.No | Details | Description | Per Cluster | Total Clusters | Source |
| 1 | Cost of travel for sourcing seed, cleaning and packing of the seed | Rs.50 per packet. i.e. for 300 packets ( one packet per Acre). | 15000 | 1575000 | bags, labour for processing and packing |
| 2 | A provision of Rs.2000 per GP (Rs.6000 per cluster) may be made for the demonstrations (either cost of demos or resource fee as the FA feels appropriate) | Rs.2000 per GP; total GPs are 315 | 6000 | 630000 | Capacity building |
| 3 | One field day per GP may be organized by the FPO at a locally appropriate time; | Rs. 9000 be made per cluster | 9000 | 945000 |  |
|  | Sub-total |  | 30000 | 3150000 |  |
| 4 | Purchase of local implements for Navadhanya can be done from CHC budget |  |  |  |  |
| 5 | Communication material- parked at LFA? |  |  |  |  |

*****