Minutes of the Meeting -Finalise Living Soil Plans meeting

28th Feb, 2019

Venue: Conference hall, Office of the Commissionerate of Agriculture, Andhra Pradesh, Guntur

Participants: Total 39 participants (List is as Annexure)

Sri VDV Krupadas, COO, APDMP has welcomed all the participants and briefed on Living Soil plans. He has stated that the funds have been received by all the FPOs and L/FAs regarding Q2, Q3 planned budgets. This is right time to start various project related activities immediately with proper plan of action.

Living soils component is one of the major activities in the APDMP. This intervention will improve soil organic carbon, microbial activity, water holding capacity and change the micro climate there by improves the drought resilience.

To develop this component planting of biomass species and horticultural plant saplings is necessary and growing of fruit crops need water and maintaining soil moisture is important. Even additional fund is required to implement activity through NREGS, in this regard COO has initiated negotiation with Mr.Balasubramniam Joint Commissioner, RD Govt. of Andhra Pradesh.  He agreed to support for living soils program through NREGS.

Sri N. Venkateswarlu, TO(Agri.) requested to introduce individual participants and organisation to the forum.

N. Venkateswarlu reviewed all LFAs regarding the understanding on recent visit to ARANYA to observe living soils activity. NGO wise feedback as follows;

APMAS: They said that they have observed Biomass production and regeneration, Aerobic compost, Vegetable cultivation and tree components with limited bore well water availability in the farm also noticed accumulation of organic matter in the soil with the profused bio mass plantation.

HANDS: They understood on Mulching, Soil moisture, Organic Carbon improvement in the soil as well as reduction in irrigations.

AF EC: Tree components are effective which adds financial value- long term values are developed, and poultry birds rearing similarly they also plan to take up trees which are suitable to Anantapuram local situations. Also rearing of poultry birds are important activity.

FES: Planting around the Biomass pit and farmers are interested in improvement of biomass production, some initiative started in the organisation and lot of motivation is required to implement at field level. 18 block identification completed covering 200 farmers & 700 acres

RHGBMSS: Understood the importance of bio mass planting and diversified cropping system which reduced the atmospheric temperature in the field due to covering crops and cropping system. Also started work on identification of living soil blocks in the learning site

EFFORT: Biomass plantation needs clarity and in the project area irrigation is the serious concern Aranya is owned by single farmer and developed over by a period of years. Crop diversification is important learning. Already they started initiation in identification of living soil blocks in two clusters.

RASS: Understood the concept of biomass production strategy, they started initiation on living soil blocks identification through Google map and brown sheet map, which includes small and marginal farmers.

CSA: They learnt that windbreaks, soil moisture conservation measures adopted in Aranya farm. Also, they started work on identification of blocks. Deepak Sachda model may be adopted.

APD Kurnool:  Compost and food crops are effectively grown in the farm.

APD Prakasam: Biomass, cover crops, integration of Agri allied activities are adopted in Aranya farm which are convinced by the group.

APD Ananthapuramu: Farm is divided into different zones, millet cultivation, diversified cropping systems which decrease the temperature, improve soil texture and organic matter where microbes act as catalyst.

Praveena: Soil is not much exposed to the sunlight completely covered with biomass leaves, temperature varies outside to the farm. Variation ranges from 3-4 % less.

Bakka Reddy: Mulching and fruit crops cultivation are better practices adopted, even they managed weeding by machinery and Navadhanya cultivation is also good.

At the end of this discussion on Aranya farm visit COO suggested technology must be worked out with small, marginal and SC and ST farmers. Plans are to be prepared in such a way that convince the farmers; project also helps in limited investment, but NREGS works are open which can be adopted.

Technical and Economic Planning must be adopted by all LFAs in scaling of living soil block plan at field level.

- Ravindra, LTA –WASSAN:

He had given presentation on Living Soil concept by showing video on how roots and soil microbes are interrelated in absorption of nutrients and water. Without improving soils, wasting water is a big concern. The main APDMP Objective to develop soil cover, improve organic matter, recycling of fallen leaf residue. Spend amount on development of fields. While selecting fields criteria given to 80% rainfed & 20% irrigated fields initially.

Also, presentation made to think how it is useful in a strategic mode of analysing dry spells in relation to the concept. Also explained key activities and investments of developing living soil blocks.

K. Padma, Aranya given presentation on Living Soil plans conducted in the Girigetla G.P.  She explained process of selection, conducting planning and activities evolved in developing living soil block. They conducted a campaign for convincing farmers on present soil situation which has to be improved, that can be done only developing living soil blocks.

Post Lunch session:

Sri. Bala Subramanyam Joint Commissioner, R.D.

He explained that the activities which are allowed but not activated in regular MNREGS, that will be made available for APDMP. Discussed on various activities to be undergone in convergence with MGNREGS in APDMP project.  Finally he agreed that for APDMP separate systems can be developed to spend the fund from NREGS activity. He has given details on each and every activites of NREGS and lot of opportunity is left for project in identification and utilisation of MGNREGS in supporting to Living Soil development.

Sri Polappa:

Convergence of APDMP with MGNREGS will give sustainability to living soil blocks. Community participation is most important characteristic for evolving successful blocks.

S. S. Kandgal, LTA –WASSAN: Presented on Living Soils Guidelines

Presentation held and ratified with the participants. Detailed discussion and debate held on various points and few points are suggested by the participants are included in the guideline.  (Please find attached operational Guidelines)

Action points evolved:

- Training Module and Soil campaign material by 2nd March 2019

- Source of saplings few LFAS are not send the list and asked them to submit at earliest

- Exposure visit: Aranya will give the date for three batches of farmers and staff  for visit to Aranya farm, Zaheerabad .Participants are  FAs of 9 LFA from two blocks, 5 farmers from each block.

- COO suggested to take more no. of farmers for visit to Aranya so that they will develop living soil blocks with commitment.

Follow-up of some action points evolved during previous exposure visit to Aranya

- One sample of “Complete living Soil plans” will be submitted by 25th Feb 2019 -----LTA ( completed)

- NREGS meeting along with requirements at RD,HOD: 25.02.19 (Completed)

- Nursery seedlings requirement and availability from LFAs: 25.02.19

- Workshop on Living soils at SPMU: 28.02.19 ( Completed)

- Living Soil campaign - After identification of Living soil Block ---1st week of March 2019

- Training Modules ---28th February 2019

- Campaign material – 28th Feb 2019

- Sourcing of plants: LFAs should take initiative in sourcing of Horticulture/Bio mass plant species                                                                             - by 1st week of March 2019.

- Training and Exposure Visit to ARANYA ( Three Groups)

Each LFA select 2 blocks for living Soil plans

5 farmers x 2 Blocks / cluster x 9 LFAs =90 farmers

NRM+Agri (2) x 9 =18 -1

Total of=107                                                   by 1st week of March, 2019

- Parallely Identify living soil blocks in 150 ha of 3 GPs at Cluster by 2nd Week of March 2019

- Submission of Plans:   a)1 G.P. per FPO (50 ha) complete by 15th March 2019

b) 100 ha   by 30th March 2019

- Approval v/s Budget -As per guidelines

Vote of Thanks: N.Venkateswarulu thanks and appreciated to each of the participants and valuable contributions.