Operational guidelines –Living Soil plans

Objectives is to incorporation of biomass into soils preferably, in situ or on farm, improve organic matter, improve soil moisture and soil microbial population.

- Steps to be followed before the selection Living Soil Blocks:

- Soil campaign needs to be organised in the G.P.s (Annexed a Separate note prepared on soil campaign)

- Conduct Gramsabha and resolution on agreement on selection living soil blocks in the Gram Panchayat (G.P.)

- Conduct a Farmer Producer Organisation (FPO) generalbody meeting and explained them on present problems in soil health and improvement through suggested key interventions by use of posters.

- Once finalise the block in larger group by use of google map and cadastral maps to identify the contiguous field, one after the others proportionately it become a block of area.

- Selection of farmers based on the size of the land holding and social category

- Orientation to the enlisted farmers by transact in the living soil block area and explaining them, various activities to improve soil health.

Criteria for selection of blocks:

- Like in the case of ‘Learning Sites’ – within the Gram Panchayat area can be divided into different Land Management Units (LMUs).

- The exercises followed in delineating LMUs in the learning sites shall be followed to delineate LMUs at GP level.

- For the year 2018-19, a minimum of 50 ha of rainfed area (with an allowance of about 20% irrigated area included) can be taken up in each Gram Panchayat for focused soil health improvement. (50 ha area is inclusive of the area planned in the ‘Learning Site’.)

- Selection of small and marginal farmers will be taken up in @ 10 to 20 ha in each of the block. It may varies between 2-3 blocks in a Gram Panchayat covering 50 ha area and 150 ha in each of the cluster (3 GPs)

Social criteria for selection of Farmers in living Soil blocks:

- Area under rainfed area coverage maximum extent (<20% irrigated area within the block)

- Where >80% of land is owned by small and marginal farmers; preferably from SC and ST community.

- Farmers willing to contribute and have their core interest in Agriculture

- Preferably where NRM / soil conservation actions are complete

- Potential for protection against grazing

- Availability of water, especially during summer, for critical watering of plants.

- At least 80% Farmers provide their consent voluntarily to take up all the measures envisaged/ planned on site and at homestead  ( Avoid taking most difficult areas to start with)

Living Soils Plans and Budgets

- Initially one site at each LFA will be developed in close liaison with experienced resource persons from Aranya and outside.  Sites will be opened up subsequently.

- Provision may be made of some resource person days for the trained farmer resource persons for each cluster to support in implementation and supervision of onsite works.

- For cost estimation and budgeting the norms of IWMP and local sources will be followed including the contribution norms

- Machinery can be used in the project activities

- Budget from APDMP will be at Rs.15000 per ha for the Living Soils Program; various activities can also be converged with the FPO services (protective irrigation, Bio-Resource Centres, Nurseries, silt application, farm ponds etc.) and from MGNREGS. Budgets from APDMP need to be used for components not supported by other programs and for critical interventions such as protection/ watering etc.

- Varying starting points; farmers’ may choose their options A budget require for the various living soil  activities enlisted in the Annexure 1 (Consisting of APDMP budget allocated matching Rupees 6000 per acre)

- Enlisted some of the activities in living soils through NREGS fund in Annexure 2 (Consisting of APDMP budget allocated matching Rupees 6000 per acre). Additional activities can be taken even beyond the mentioned budget per acre, based on the negotiation with the NREGS fund allocation.

- Initial allocation is made @ 50 ha per Gram Panchayat i.e. Rs.7.50 lakhs per GP (Rs.150 ha per cluster at Rs.22.50 lakhs per cluster). Within this budget, all the 50 ha may be planned flexibly as per local requirements in each GP. There is no requirement to have a ceiling of Rs.15000 per ha. Each Living Soil block could be between 10 to 15 ha contiguous area; blocks smaller than 10 ha may not be preferred unless there are compelling reasons for their selection.

- Any purchases for the Living Soils program will from the enterprises of the FPO (BRC, Nursery, custom hiring) etc., to the extent possible.

- SPMU will work with RD to open up a special support stream from MGNREGS for the purpose.

Safeguarding Against Usual Failure Points:

The initiative is biomass intensive and is therefore, challenging. Usual failure points experienced in such programs are:

- Starting the program without adequate preparation/ acceptance of the farmer

- Failure to control grazing / protecting the plants against grazing

- Failure to water the plants more intensely for the initial 3 years and for protection later on.

In the planning and its assessments emphasis be made on ensuring these points are well addressed.

Plan Submission & Approvals:

- The plans must have 3 components viz., a) the activities & budgets b) Watering plans for 2 years with budgets c) Protection of biomass from grazing norms and mechanisms.

- Plans prepared with technical support from designated person from LFA (and Aranya) to support the LFA and after sufficient orientation and acceptance of the farmers.

- The plans be first approved by the Rythu Vignana Committee (sub-committee of FPO formed for CLiCs).

- Plans formally submitted by FPO with support from FA to LFA.

- LFA assesses the technical plans, operational modalities, assess the watering and protection mechanisms arrived at, checks conformity of cost norms, assess farmers’ interest and commitment before formally submitting it to DPMU with a copy to SPMU.

- DPMU randomly (about 10%) check the technicalities of the plans in interaction with farmers, assess conformity of plans with cost norms and provide necessary recommendations to SPMU for sanction and budget release.

- DPMU will support LFA in converging with various Departments.

Release of Budgets and Expenditure:

- SPMU after sanctioning of the Living Soils Plans provides a One Time Sanction for the plans and communicates the same to FPO with copy to DPMU/LFA/FA.

- Against the approved plans, the FPO will include budgets for every quarter under Living Soils Plans in its quarterly plans for budget releases. It follows the normal process of budget discussion, plan, review and releases.

- The NRM-specialist at the FA level will be responsible for recording the Measurements with assistance from the two farmer resource persons. FPO NRM specialist will do 100% verification of the MB and approves the expenditure.

- Designated member of the DPMU will do a random 5% super check on the works.

- The Rythu Vignana Committee (FPO Sub-Committee for CLiCs) will visit the field sites every quarter, make an assessment and submits its report with recommendation to the FPO. This is mandatory for the quarterly plans.

Assessment Indicators:

The initiative will be assessed on the following parameters:

- Increase in biomass and survival rates of the biomass

- Amount of additional organic matter added to the soil per year

- Whether residue burning has stopped and residue management practices initiated.

- Period of extension of soil cover.

Actual increase in Soil Organic Matter etc., would be hard to materialise during short periods. The above process indicators, which contribute substantially to living soils and would be adhered. LTA will develop appropriate metrics and measurement tools for the above assessment indicators.

Action Plans evolved:

- One sample of “Complete living Soil plans” will be submitted by 30th January 2019

- Each LFA select 2 patches  or Blocks                                              by  28th February 2019

- Training to  Farmers  and Staff  :

5 farmers x 2 Patches/ cluster x 9 LFAs =90 farmers

FAs :NRM+Agri  (2) x 9 =18 -1

Total of=107                                                   by 28th February, 2019

LFA level NRM specialist is responsible

Each FA level NRM specialist is responsible

- Parallely Identify living soil blocks 150 ha                                   by 28th February 2019

- Plans :   a)1 G.P. per FPO (50 ha)  complete                                by 15th March 2019

b) 100 ha                                                                             by 30th March 2019

- Approval v/s Budget

- 6 LFA wise biomass plants sourcing  strategies                          by 31st January 2019

Support Activities for the above-mentioned action plan as follows;

1 FPO B.O.D. meeting

+Master farmers

+CO

- Living Soil campaign - After identification of Living soil Block Identification

- Training Modules

- Campaign material

Meeting with;

- MGNREGS and Soil Conservation  for convergence

- Forest and Horticulture

Finalising Plant Species

- 45 days plants (Village)

- Long duration nursery

- Horticulture ( 2 year nursery)

- Seed dibbling / Stumps

Event is concluded with the individual participants feedback. Each of them appreciated the process of organising event, learnings to execute living soil activities, appreciated resource persons efforts and interventions in dryland agriculture.