AP DROUGHT MITIGATION PROJECT

- This Document contacts detailed proposal with budget for the Ground Water collectivization activity for Patch Name: Nallamma Katta Chenlu.

- Detailed Pipeline Estimates and Civil Works estimate Excel sheet is also send over mail

- LFA Name	: 	HANDS

- FA name	: 	RIDS

- District		:	Anantapur

- Mandal Name	:	Singanamala

- GP		:	Akuledu

- Villages		:	Akuledu

Ground Water Collectivization Proposal

SPMU, APDMP

Department of Agriculture, Guntur

Table of content

1. Context of the Patch Chosen	3

1.1. No of Plots:	4

1.2. Total Acreage:	4

2. Plot Map	5

2.1. Plots Demarcated on Google Earth	5

2.2. Pipeline Network with Legends on Google Earth	6

3. Budget Proposed Summary	7

4. CheckList......................................................................................................................................................................................................................................................................9

Annexure 1: Details of Ground water Sharing Farmers	10

Annexure 2: Bore well Discharge Measurement to determine system capacity to provide Critical Irrigation in Kharif	10

Annexure 3 : Proposed Cropping pattern	11

Annexure 4: Hydro marker survey for calculation head of pipeline & class	13

Annexure 5 : Crop water Demand for proposed Kharif crops	13

Annexure 6: Bore well Pooling Pipe Line Network detailed estimation	15

Annexure 7 : Civil Works Estimate…………………………………………………………………………………………………………………………………………………………...…………..16

- Context of the Patch Chosen.

Akuledu village is located at a distance of 5 km form its Mandal and 17 km far from Anantpur district. The agricultural dependency of this village is on rainfed agriculture. Farmers of this village is facing frequent crop loss due to rainfall uncertainty and long dry spells. WASSAN team visited the field on 28th November 2018 and 11th January 2019 along with LFA team for feasibility study and explained the rules and regulation of groundwater sharing norms in the Akuledu village meeting in front of farmers group. The potential bore-wells were identified for water sharing and also formed a water sharing group. Farmers of Akuledu village have requested to FPO for installation of the critical irrigation facility through Groundwater Collectivisation & Sharing. The group of farmers was agreed to all rules and regulations of groundwater management and water sharing norms. The FA “RIDS” identified the area of the group and did detailed surveys with support of WASSAN LTA team. WASSAN technical team did the design and estimation for water sharing pipeline network based on the primary data provided by the FA. The proposal shared with FPO and water sharing group by “RIDS” FA team and taken consent of the community. The FA is further submitting to the department for approval and sanctioned the budget of proposed water sharing network.

The proposed water sharing plan will benefit 9 numbers of total farmers in which 6 numbers of farmer are rainfed and 3 numbers of farmer are the bore-well farmer. The proposed 34.04 acres of water sharing farm land, 22.84 acres of land is rainfed and 11.20 acres of land is irrigated. The bore-wells are in the village which is near to 400 meters. By installing water sharing pipeline network, the farmers will overcome from small to medium drought spells by accessing with assured protective irrigation from water sharing pipeline network in 34.04 acres of rainfed crop like groundnut and redgram. Rainfed farmers will secure crop cultivation investment and get additional benefit of Rs. 3000 per acre to 5000 per acre with improved yield with comparative to non-protective irrigation crops. Bore well farmers will also get the benefit of protective irrigation to their rainfed crops. Apart from the crop security, they are securing their bore wells from defunct due to new bore wells drilling. And mutually agreed norm of ban on new bore-well drilling by water sharing farmers.

  - No of Plots:

The total numbers of patches are 9.

  - Total Acreage:

The total farms area is 34.04 acres, the rainfed land is 22.84 acres and irrigated land is 11.20 acres.

Table 1: Farmers Summary Table

| Description | Number of Farmer | Area (acre) | Remarks |
| --- | --- | --- | --- |
| Total | 9 | 34.04 |  |
| Bore well ownership |  |  |  |
| Number of Bore well Farmers | 3 | 11.20 | All the 3 bore-wells has good yield. |
| Number of Non Bore well Farmers | 6 | 22.84 |  |
| Category wise |  |  |  |
| Small and Marginal Farmers | 2 | 3.10 |  |
| Others | 7 | 30.94 |  |
| Gender |  |  |  |
| Male Farmers | 1 | 1.10 |  |
| Women Farmers | 8 | 32.94 |  |
| Caste Wise |  |  |  |
| SC / ST Farmers | 0 | 0 |  |
| Others Farmers | 9 | 34.04 |  |

- Plot Map

2.1. Plots Demarcated on Google Earth.

  - Pipeline Network with Legends on Google Earth.

- Budget Proposed Summary.

| Sl. No. | Work details | Estimate budget (Rs.) | Source of fund |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | DoA Share (Rs.) | Farmer Share (Rs) | % over DoA |
| 1 | Civil work | 166732 | 123100 | 43632 | 35.44 |
| 2.1 | Pipe line work- PVC pipes | 334374 | 334374 | 0 | 0.00 |
| 2.2 | Pipe line work- Pipe line installation and fittings | 216120 | 160015 | 56105 | 35.06 |
| 3 | Sprinkler Set | 144216 | 144216 | 0 | 0.00 |
| 4 | Construction of compost pit | 110171 | 66788 | 43383 | 39.38 |
| 5 | Compost preparation (3 cycles) | 456959 | 228480 | 228480 | 50.00 |
|  | Total | 1428572 | 1056972 | 371599 | 35.16 |
|  | % of each stake holder | 100.00 | 73.99 | 26.01 |  |

- Cost Benefits

| Sl. No | Benefits | Total Area (acres) / No of Bore wells | Annual additional Income per acre Amount (Rs.) | Total Annual additional Income per acre Amount (Rs.) | Total water sharing agreement period in years | Total Amount at current price (Rs.) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Additional Income | 34.04 | 4000 | 136160 | 10 | 1361600 | Based on current experience of pilot site of RRA |
| 2 | Protecting crop loss and cost of cultivation in major droughts | 34.04 | 4000 | 136160 | 4 | 544640 | Based drought trend |
| 3 | Borewells farmers irrigated crops. | 3 | 7500 | 22500 | 10 | 225000 | Based on current experience of pilot site of RRA |
| 4 | Protecting borewells from defunct | 3 | 100000 | 300000 | 3 | 900000 | Based on current experience of bore well failure |
|  | Total |  |  | 594820 |  | 3031240 |  |
|  | Avg. Annual income |  |  |  |  | 303124 |  |
|  | Total Investment |  |  |  |  | 1428572 |  |
|  | Cost Benefits Ratio |  |  |  |  | 2.122 |  |
|  | Payback Period (years) |  |  |  |  | 4.71 |  |

- Checklist

| Sl. No. | Particulars | Yes /No | Remarks |
| --- | --- | --- | --- |
| 1 | Pipeline estimation | Yes | Attached |
| 2 | Civil work estimation | Yes | Attached |
| 3 | Pipeline plan | Yes | Attached |
| 4 | Location plan (Highlighter map of Cadastral) | No | Not attached |
| 5 | Farmers details | Yes | Attached |
| 6 | Bore well water discharge details | Yes | Attached |
| 7 | Crop water demand estimation | Yes | Attached |
| 8 | Resolution of community on agreement of water sharing | No | Attached |
| 9 | Agreement document on bond paper | No | Attached |

Annexure 1: Details of Groundwater sharing farmers:

Annexure 2: Bore well discharge measurement to determine system capacity to provide Critical Irrigation for Kharif.

Annexure 3: Proposed cropping pattern.

Annexure 4: Ground level cross section map of pipe line alignment for calculation head of pipeline & class.

Annexure 5: Crop water Demand for proposed Kharif crops.

| Sl. No. | Description | Units | Value |
| --- | --- | --- | --- |
| a. | Total Discharge from all bore wells in patch in a day* | Discharge in cum/6hrs |  |
| b. | Total Number of Days requiring Critical Irrigation** | Day |  |
| c. | Total Discharge of no of days of Critical irrigation | cum | (b.) * 10 days |
| d. | One critical irrigation required water quantity per acre*** | Cum/acre | 202.4 |
| e. | Capacity of System Irrigation for the 15 days | acres | (c.) / (d.) |

*Day = average 6hrs usage    ** usually taken 10 days *** 202.40 cubic metre approx. is required in one Critical Irrigation in one acre.

**** Main pipe design with 10LPS carrying capacity at 0.75 meter/sec velocity and maximum head of 5 meter per 1000 meter long distance. Opt PVC pipe dia. 140mm and 4kg/cm^2 pressure capacity.

Annexure 6: Bore well Pooling Pipe Line Network detailed estimation.

| Ground Water Pooling and Sharing Pipe line Network under APDMP supported by IFAD and DoA AP |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DPMU |  | ATMA | LFA | HANDS |  |  |  |  |  |  |
| Name of the FA: |  | RIDS | Mandal: | Singanamala |  | District: | Anantapur |  |  |  |
| Name of the FPO and A/C No: |  | Sri Dona Rameshwara VUPSSS Ltd. SB A/C No: 0979101038323 Canara Bank, Garladinne. IFSC code: CNRB0000979 | Name of the Cluster: |  |  | Singanamala |  |  |  |  |
| Name of the water sharing group: Nallamma Katta Chenlu. |  |  |  |  |  |  |  |  |  |  |
| Village: |  | Akuledu | Grampanmchyat: |  |  | Akuledu |  |  |  |  |
| Total Area in acre | Water Source (Bore wells in Nos) | Survey No: 102,101,102 | Other sources | Energy (Tick "√") | Service connection (Yes) | Service connection (No) |  |  |  |  |
| 34.04 | 3 |  | 0 | 0 | 3 | 6 |  |  |  |  |
| Note: 1.Quantities enter as per site condition & actual measurement for preparation of of estimation 2. Rate applied for estimation CSSR,RSSR and APMIP Rates circular |  |  |  |  |  |  |  |  |  |  |
|  |  | Coloured cells shall be input data enter manually |  |  |  |  |  |  |  |  |
| Estimation of Pipe line |  |  |  |  |  |  |  |  |  |  |
| Sl. No. | SS INO | ITEM | SIZE in mm | UNIT | Qty | Unit Cost (Rs) | Amount (Rs) | APDMP Share Rs. | Farmers share Rs. | No of pipes |
| A | CSSR Year 2018-19, PH page no 67 Item no 20 SOR for PVC pipes | Manufacture and supply of and delivery of Un-plasticised PVCs pipes for potable water supplies conforming to IS 4985/2000 (third revision) with bell ends (socket) as per specification in light grey/Natural Ivory Grey/ any other colour (except white) inclusive of transportation to the sub divisional stores anywhere in AP excluding excise duty and sales tax etc. |  |  |  |  |  |  |  |  |
| i |  | Pvc pipe 140mm *6kg/cm2 | 140 | Mts | 0.0 | 380.00 | 0 | 0 | 0 | 0 |
| ii |  | Pvc pipe 110mm *6kg/cm2 | 110 | Mts | 0.0 | 231.00 | 0 | 0 | 0 | 0 |
| iii |  | Pvc pipe 90mm *6kg/cm2 | 90 | Mts | 996.0 | 160.00 | 159360 | 159360 | 0 | 166 |
| iv |  | PVC pipe 75mm 6k/cm2 | 75 | Mts | 0.0 | 111.00 | 0 | 0 | 0 | 0 |
| v |  | Pvc pipe 110mm *4kg/cm2 | 110 | Mts | 0.0 | 162.00 | 0 | 0 | 0 | 0 |
| vi |  | Pvc pipe 90mm *4kg/cm2 | 90 | Mts | 450.0 | 112.00 | 50400 | 50400 | 0 | 75 |
| vii |  | Pvc pipe 75mm *4kg/cm2 | 75 | Mts | 588.0 | 81.00 | 47628 | 47628 | 0 | 98 |
| viii |  | PVC pipe 25mm of 10kg/cm2 | 25 | Mts | 12.0 | 24.00 | 288 | 288 | 0 | 2 |
| A |  | PVC Pipes sub total amount Rs. |  | Mts | 2046.0 |  | 257676 | 257676 | 0 | 341 |
|  |  | Add GST |  |  |  | 12% | 30921 | 30921 | 0 |  |
|  |  | Total |  |  |  |  | 288597 | 288597 | 0 |  |
| S.No | SS INO | ITEM | SIZE in mm | UNIT | Qty | Unit Cost (Rs) | Amount (Rs) | APDMP Share Rs. | Farmers share Rs. |  |
| B | Pipe line control fitting material |  |  |  |  |  |  |  |  |  |
| 1 | APMIP GORt.NO.1157 item no 29 | Set of PVC / Nylon Air Release Valve. | 1" | No's | 4 | 337 | 1348 | 1348 | 0 |  |
| 2 | Vide page no 114 of Building Sor 2018-19,WS Item Sl.No.250,251 Item code BMW-F.39 and 40 respectively | Supply and fixing of Horizontal check valve ( Non-Return Valve) made up of gun metal heavy duty as per IS 778,I class 50mm NB size including of material cost and labour charges for finished item of work (2990+112=3102) | 50mm | No's | 3 | 2660.00 | 7980 | 7980 | 0 |  |
| 3 | CSSR year 2018-19 , Vide page no 141,SoR building WS Item Sl.no. 1003,1004 BMW-I.409,410 respectively | Supply of PPR ball valve confirming to DIN standards 8077/8092 | 75 | No's | 3 | 1382.00 | 4146 | 4146 | 0 |  |
| 4 |  |  | 90 | No's | 6 | 1975.00 | 11850 | 11850 | 0 |  |
| 5 | vide page no 82 of CSSR Year 2018-19,PHI 29. SoR for Valves confirming to IS for normal usage SL. No. 2 | Supply ,delivery of DI double flanged short/ long body or Wafer lug type Butterfly valve confirming to IS 13095/1991 (with up to date amendments if any) manually operated having body disc with DI shaft, seating ring internal fastenings with stainless steel (IS:6603) external bolting with carbon steel seat with nitrile or EPDM rubber and a test pressure of 2.5MPa excluding of transportation and taxes etc. | 100 | No's | 1 | 16280.00 | 16280 | 16280 | 0 |  |
| 6 |  |  | 150 | No's | 0 | 23980.00 | 0 | 0 | 0 |  |
| 7 | vide page no 82 of CSSR Year 2018-19,PHI 29. SoR for Valves confirming to IS for normal usage SL. No. 3 | Supply, delivery of D.I. double flanged swing check type reflux valves (Non return valves) of confirming to IS 5312/Part 1&2 /1984 (with amendments up to date if any) having body cover door, bearing holder with D.I; hinge pin door pin, door suspension pin with stainless steel (IS 6603); Body seat ring door face ring bearing bushes plugs for hang pin with leaded Tin Bronze (IS318) bolts, nuts with carbon steel gaskets with rubber hinges with cast steel test pressure of 1Mpa excluding of transportation and taxes etc.. complete | 100 | No's | 0 | 15180.00 | 0 | 0 | 0 |  |
| 8 |  |  | 150 | No's | 0 | 21780.00 | 0 | 0 | 0 |  |
| 9 | As JAIN Irrigation Pvt.Ltd rate Sep 2018 | Set of HDPE outlet (HDPE pipe connecting nipple, end plug with GI chain link latches and all necessary fitting materials) | 75 | No's | 15 | 856.00 | 12840 | 12840 | 0 |  |
|  |  | Subtotal of Fitting materials |  |  |  |  | 54444 | 54444 | 0 |  |
| C | Vide page no 121 of Building Sor 2018-19,WS Item Sl.No.486, Item code BMW-G.152 | Labour charges for laying , fixing and commissioning of the PVC pipes including couplers / bends / Tees etc any diameter including fixing necessary fittings like bends , plugs couplers junctions tees etc with solvent jointing as per standard practice |  | 1 Rmt | 1686.0 | 70 | 118020 | 59010 | 59010 |  |
| D |  | VAT |  |  |  | 12% | 13614 | 13614 |  |  |
| E |  | Service tax |  |  |  | 18% | 10622 | 10622 |  |  |
| F |  | Add for LS transportation |  |  |  | 5% | 21507 | 21507 |  |  |
| G |  | LS for unfore seen item of works and over heads |  |  |  | 1% | 2151 | 2151 |  |  |
| H |  | LS for rounding off fig |  |  |  |  | 515 | 515 |  |  |
|  |  | Grand Total |  |  |  |  | 220873 | 161863 | 59010 |  |

Annexure 7: Civil Works Estimate.

| Civil works for Ground water pooling pipe line network under APDMP program supported by IFAD and DoA, AP |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Name of thePFA (NGO): RIDS |  | Name of the mandal: |  | Singanamala |  |  |
| Name of the village : Akuledu |  | Name of the GP: |  | Akuledu |  |  |
| Name of the water sharing group: Nallamma Katta Chenlu |  |  |  |  |  |  |
|  | Note : Do not touch the Green coloured cells shall calculate automatic |  |  |  |  |  |
| Sl. No | Description of work | Pipe line (Main / Sub main) Chain age | Length (m) | Width (m) | Depth (m) | Total quantity |
| 1 | Earth work excavation for pipe line trench by machine in all types of soils including boulders up to 0.30meter dia. except hard stone rock |  |  |  |  |  |
| a | Ordinary soils |  | 454 | 0.6 | 0.75 | 204.3 |
| b | Hard gravel soils |  | 1108 | 0.6 | 0.75 | 498.6 |
| c | Soft disintegrated rocks |  | 160 | 0.6 | 0.75 | 72 |
| d | Hard rocks |  | 0 | 0.6 | 0.75 | 0 |
| 1.1 | Earth work excavation in hard rock boulders above 0.30 and up to 0.90 m diameter for field channel initial lead of 10 meters and lift 2m by Hydraulic machine excavator |  | 0 | 0.6 | 0.75 | 0 |
| 2 | Earth work excavation for pipe line trench by manual labour the different type of soils |  |  |  |  |  |
| a | Ordinary soils |  | 0 | 0.6 | 0.75 | 0 |
| b | Hard gravel soils |  | 307 | 0.6 | 0.75 | 138.15 |
| c | Soft disintegrated rocks |  | 0 | 0.6 | 0.75 | 0 |
| d | Hard rocks |  | 0 | 0.6 | 0.75 | 0 |
|  | Sub total |  | 2029 |  |  |  |
| 3 | Collection and supply of filling sand |  |  |  |  |  |
| a | Soft soils like Black and red clayee soils |  | 454 | 0.6 | 0.1 | 27.24 |
| b | Soft Disintegrated rocks (SDR) |  | 160 | 0.6 | 0.1 | 9.6 |
| d | Hard Rock up to 0.30 m dia boulders |  | 0 | 0.6 | 0.1 | 0 |
| e | Hard rock 0.30 to 0.60 m dia boulders |  | 0 | 0.6 | 0.1 | 0 |
| 4 | Collection and supply of soil for filling of pipe line trench where the hard rock streche |  | 0 | 0.6 | 0.7 | 0 |
| 5 | Refilling of trench with using filling sand under pipe line bed |  | 614 | 0.6 | 0.1 | 36.84 |
| 6 | Refilling of pipe line trench with using excavated soils by machine |  | 1722 | 0.6 | 0.7 | 723.24 |
| 7 | Refilling of pipe line trench with using excavated soils by manual labour |  | 307 | 0.6 | 0.7 | 128.94 |

Agreement document on bond paper.

Resolution of community on agreement of water sharing.