Guideline on

PARTICIPATORY PLANNING CLIMATE RESILIENT AGRICULTURE IN THE 100 ha SITE

CONTENT

| Sl.No. | Particulars | Page No. |
| --- | --- | --- |
| 1 | Planning Teams | 3 |
| 2 | Prerequisite | 3 |
| 3 | Objectives of planning/Outputs/Planning exercise | 4 |
| 4 | Planning Exercise 1 :Preparation of a Base Map | 5-7 |
| 5 | Planning Exercise #2: Improving Soil health | 8-17 |
| 6 | Planning Exercise on Component #2: Water and Protective irrigation | 18-23 |
| 7 | Planning Exercise on Component #3: Crop Systems and Seed | 24-27 |
| 8 | Planning Exercise on Component #4: ZBNF | 28-30 |
| 9 | Planning Exercise on Component #5: Implements and Farm machinery | 31-43 |
| 10 | Tables -All Exercises | 45-61 |
| 11 | Individual Farmer Format | 62 |
| 12 | Sequence of Activities while Planning | 63 |
| 13 | 100 ha consolidation plan | 63-64 |
| 14 | Outline for Proposal to submit | 65 |
| 15 | Guidelines for NRM works in learning site | 66-70 |
|  | Annexure: |  |
| 16 | Farmer wise consolidation plan (working sheet) |  |
| 17 | Consolidation of Chitayala village plan and budget (working sheet) |  |
| 18 | List of Common NRM works |  |
| 19 | List of Common NRM works in Telugu |  |
| 20 | MGNREG plan consolidation sheet |  |
| 21 | Check list for PRA -APDMP |  |
| 22 | Inputs on Chelukulu Eruvu |  |
| 23 | Inputs on Protective irrigation (Flexi) |  |
| 24 | Inputs on Mee Bhumi Bhagunda (Brouchure) |  |
| 25 | Inputs on Compost -Flip Charts |  |
| 26 | Inputs on Groundwater Sharing (Flexi) |  |
| 27 | Inputs on CliC (Photos) |  |
| 28 | Inputs on Crop System (Photos) |  |
| 29 | Inputs on NPM (Photos) |  |
| 30 | Inputs on Soil fertility experience sharing |  |

Participatory Planning Module on

‘Climate Resilient Rainfed Agriculture in the “Learning Site”

Introduction:

A ‘Learning Site’ of around 100 ha area in each cluster of 3 Gram Panchayats is taken up for season long action on climate resilient agriculture under APDMP. Evidence and experience on climate resilient agriculture is expected to be generated in this ‘Learning Site’ during the first year through a comprehensive package of initiatives taken up in the first year.

Experiences in the Learning Site are expected to generate demand from other farmers in the cluster which will be met through other project mechanisms.

This “Participatory Planning Module” guides the planning teams in preparing a comprehensive climate resilient agriculture plan of action with budgets for the Learning Site.

Planning Teams:

The LFA team in addition to carrying this out in their FA, will train FAs on this module and support them on field.

The key responsibility of planning on ground is with the NRM and agriculture team members.

| From LFA | From FA |
| --- | --- |
| - Water Management Specialist/Engineer and NRM - Agronomist/Crop-Horticulture Specialist - Livestock Production and CPR Specialist | - Water resources development & NRM - Agriculture Facilitator - Livestock Facilitator and CPR |

Pre-Requisites:

- The ‘Learning Site’ (of 100 ha area)in the form of a sub-watershed is identified and its borders are delineated on map (cadastral and Google Earth (GE) map). Guidelines for selection of “Learning Site” is at Annexure-1

- Physical copies of the maps (cadastral and Google earth) are available; preferably the Google Earth map printed on a larger size flexi sheet.

- The names of the farmers in the Learning Site are listed along with their Aadhar numbers.

Objectives of the Planning Exercise:

The participatory planning exercise results into a comprehensive climate resilient and growth plan for the learning site.

Outputs:

- Capturing the baseline situation including analysis of issues

- Prepare an action plan that is commonly agreed by the farmers with budgets and detailed activities.

The Planning Exercise is split into the following Sub-Plans:

- Soil health improvement

- Protective irrigation plans including soil moisture conservation

- Cropping systems diversification and developing seed security

- Zero Budget Natural Farming (ZBNF)

- Increasing access to Agriculture Implements and Farm Machinery

Note: Table formats are provided in the module to capture the information from discussion. The information which can’t be captured in the tables should be written in detail.

Planning Exercise 1

Preparation of a Base Map

- Getting the Base Map Ready

  - Identify the proposed areas through Participatory Rural Appraisal (PRA) exercises. 100 ha of Learning site should be identified using the criteria. This criteria and process of conducting PRA to identify the learning site is provided at Annexure-1.

  - Identify the area on the Google Earth (Pro version). Save the image and take print out in maximum view possible.

    - Open Google Earth Pro version

    - Spot the location in Google Earth.

    - Enlarge the view to the desired size

    - Save the area: Go to File >> Save >> save image as >>Select Maximum from Resolution (Next to search) >> Click Save image >> Save as JPEG

    - Take the print out on A0 size sheet (For better view, take the color print)

  - Start at one known point/landmarks and mark the plots of adjoining farmers. The area should be fixed based on the transact walk made and fields visited.

  - Simultaneously, use cadastral maps to check the farmers and survey numbers. The cadastral features can be overlaid later onto GIS platform.

  - Facilitate for identification of some land mark and proceed further with each plot. Each plot can be given numbers (1, 2,….)

  - Prepare the details of farmers in following table

Table # Gen 1: Farmers List in Learning Site

| Sl No | Name of the Farmer | Father/ Husband Name | Aadhar | Area | Survey Number | LMU |
| --- | --- | --- | --- | --- | --- | --- |

  - Most part of the drainage lines are visible on the Google Earth Map. However, identify and mark the drainage lines on the map, if they are extended or not visible.

  - The process of identification of Land Management Unit (LMU) is explained in next session.

Base map is ready

- Demarcating Land Management Units (LMU):

For the purpose of the project, let us use a simple definition for LMU. The plots that are similar in land type, soil, crops, irrigation status and management requirements (they usually have a local name) are marked as a … LMU. The actions required on these LMUs will be mostly similar.

  - Once you have the base map ask the key question:“What are the ways to classify your lands in this area?”

  - Start listing the local names on flash cards; one on each of them.

  - Then ask: “Can any of them be grouped together – as the difference is not substantive”?

  - Group these cards that have high similarities. Finally, we end up with a local classification of land types.

  - Finally arrive at a maximum of 4 to 5 LMUs.

  - Demark the LMUs on the map.

- Identify characteristics of the LMUs identified:

  - Key question: “How are these LMUs identified are different from each other”?

  - In the following discussion: capture the following in a Table, by asking the questions

Table # Gen 2: LMU characteristics

| Sl No | LMU Name | Approximate Area (acres) | Soil Texture (Clayey, loam, silt and sandy) | Soil Color (Red, Black, ??) | Soil Depth (deep: >60cm, medium: 11-60 cm, shallow: <=10cm) | Slope (high, medium, low) | Water holding capacity (high, medium, low) | Specific Problems | Fertility status (good, average, poor) | Crop systems that are generally taken up |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |

- Write description of each of the LMUs

  - LMU1:

  - LMU2:

  - ….

  - ....

- Prepare LMU wise list of farmers:

- Digitising base map (this can be done after the planning exercise is completed)

  - Digitise and geo-reference the cadastral map

  - Overlay the cadastral map onto Google Earth map using GIS platform (Q-GIS)

  - Post the information collected during the exercises

Planning Exercise #2:

Improving Soil health

Purpose:

Soil is key to production. In rainfed situation, amount of rainfall harvested and retained in soil profile contributes directly to drought resilience and productivity. Reduced runoff and higher infiltration helps in better rainfall harvest. Organic matter and life in soil (soil biology) are crucial for a healthy soil.

Planning Exercise Results in:

- Understanding different soils and their constraints

- Plans for increasing organic matter into soils/ soil profile amelioration

- Addressing the issues of problem soils

- Soil testing and understanding soil test results

Tools/methods

- Base map prepared

Soil Health Improvement Plan Process Steps:

- Start with the Base Map and Table in which LMUs are delineated with details.All the discussions and plans should be done for each LMU.

- Explore on Soil Testing:

  - Are there any soil test results available for the area? If yes, gather the Soil Test card results and compile them including survey numbers.

  - Summarise major observations from soil test results? Discussion & report.

    - Status of organic carbon?

    - Status of Macro nutrients

    - Status of micro nutrients

- What are the recommendations?

- Present Practices, Strategic plan in the LMU and Farmer wise detailed plan:

(Ask the Key Questions for each of LMU after brief input session)

  - Application of Manure

- Present Practices

  - What are the trends in application of manure? In these 10 years, 10 years before, 20 years before?

  - What types of manures are applied? What is the quantity? To which type of soils?

  - Any practices in composting? If yes, what are they?

    - At household level

    - At cattle/ animal sheds

  - Did you apply compost to the lands in this LMU?

- StrategicPlan

  - What activities need to be taken up in the area?

    - In situ composting

    - Composting at homesteads or cattle/ livestock sheds

    - Others? (option – get the numbers and location after consulting the individual farmers?)

- Detailed Plan(No of farmers and extent in Acrs)

  - Who wants to apply the manure? To which plot? How many acrs?

  - Where do you want to produce it? What is the cost, how much can you contribute?

  - Tank Silt Application

- Present Practice

  - Was there a practice of Tank Silt application?

  - When was it last done? And by how many farmers; how many acres?

  - What are the sources for tank silt, if needed;

  - Source – Distance – quantity available (sufficient/ moderate / very less)?

  - Is the Tank silt quality good?

- Strategic Plan (this can be done by a small sub-group or committee)

  - Source of tank silt (assure quality)

  - Distance

  - Modalities of tractors for transport

- Detailed Plan

  - Name of the farmer

  - No of trips

  - Contribution and cost sharing per trip

  - Soil Erosion control Works

- Present Practices

  - Were soil conservation works taken up in the “learning site”?

  - If yes, when, under which scheme?

  - What is the status of these works?

  - Which works are more qualitative? Why?

  - Do farmers retain bunds or plough them off?

  - Map the active erosion locations in the 100 ha area; where it is very important to have conservation works to prevent larger erosion.

    - In Streams and common lands

    - In agriculture lands

- Strategic Plan

  - What are the most preferred and suitable works/interventions for soil conservation

  - How many farmers? How many acrs?

- Detailed Plan

  - Who are the farmers need soil conservation or erosion control works?

  - What is the cost? What is the farmers’ contribution?

  - What is the source of scheme?

  - Crop Residues Management

- Present Practices

  - What happens to crop residues? Are they burnt or mixed into soil? If both practices are there, roughly in what % of area crop residues are burnt?

  - Are farmers familiar with Rotovators? Should they be used?

  - Are rotovators available in the village for hiring?

  - What are the rental value and payment practices?

- Strategic Action Plan

  - Campaign to STOP Burning Crop Residues

  - Methods of mixing crop residues into soils

  - If not, should it be available at CLiCs- Custom Hiring Center?

  - Rental value

- Detailed Plan: Farmer wise action plan with budgets and sources

  - Biomass Plantation on Bunds

- Present practices

  - Was/ is there any practice of biomass plantation on bunds/ commons and adding

  - Are there any other practices for adding biomass to the soils?

- Strategic Action Plan

  - What kind of biomass plants are needed?

  - Are there readily available in any nearby nursery? What is the distance? Who is maintaining/running the nursery?

- Detailed plan: Farmer wise action plan with budgets and sources

Possible Action Plans/Points

- Soil testing

- Activities for development of problematic soils

- Activities for improvement of soil fertility

- Activities for production of compost

- Activities for controlling soil erosion

- Tank silt application

- Raising nursery for biomass preparation

- Seed dibbling on bunds for Biomass

- What are the other practices in your experience…….

Compilation of information: Theinformation collected from transect walk, observations, group discussions should be furnished in the following table.

- Table: LMU Wise Situation Analysis

  - Table # Soil 1: Soil Testing

| LMU | Soil Testing Farmer Name | Date of Testing | Soil Testing Report Available? | Status of organic carbon | Status of Macro nutrients | Status of micro nutrients | Key recommendations | What recommendation are implemented |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

  - Table # Soil 2: LMU wise Composting Experiences (Please explain this in all LMUs, in all time periods and for all compost types)

| Sr No | Year | Type of manure | Acres | No of farmers | Approx. Qty/acre (Number and Units) | Is the practice continued | If not why | Should it be revived? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2008-2018(last 10 years) | Compost |  |  |  |  |  |  |
|  |  | FYM |  |  |  |  |  |  |
|  |  | Green Manure |  |  |  |  |  |  |
|  |  | Sheep Penning |  |  |  |  |  |  |
|  |  | Gypsum |  |  |  |  |  |  |
|  |  | Fertilizer |  |  |  |  |  |  |
|  | 1998-2008 (10-20 years back) | Compost |  |  |  |  |  |  |
|  |  | FYM |  |  |  |  |  |  |
|  |  | Green Manure |  |  |  |  |  |  |
|  |  | Sheep Penning |  |  |  |  |  |  |
|  |  | Gypsum |  |  |  |  |  |  |
|  |  | Fertilizer |  |  |  |  |  |  |
|  | 1988-1998 (20-30 years back and before that) | Compost |  |  |  |  |  |  |
|  |  | FYM |  |  |  |  |  |  |
|  |  | Green Manure |  |  |  |  |  |  |
|  |  | Sheep Penning |  |  |  |  |  |  |
|  |  | Gypsum |  |  |  |  |  |  |
|  |  | Fertilizer |  |  |  |  |  |  |

- What are the Constraints at present, in application different types of manures in this patch? Please explain:

- Generally, where do farmers produce the compost? At household, back yard, cattle sheds, in-situ (in fields)? Please explain:

  - Table # Soil 3: LMU wise Tank Silt Application Experience

| Sr No | Year | Type of Input (Silt, Sand, Soil) | Acres covered by application (Acr) | No of farmers | Source of silt | Distance (Km) | Quantity/ acre | Quality (Good/ Not good) | Any Project? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2008-2018 (last 10 years) |  |  |  |  |  |  |  |  |
|  | 1998-2008 (10-20 years back) |  |  |  |  |  |  |  |  |
|  | 1988-1998 (20-30 years back and before that) |  |  |  |  |  |  |  |  |

  - Table # Soil 4: LMU wise Adding Biomass Experience

| Sr No. | Time period | Type of biomass | Source (common land, own fields) | Distance if common land (km) | Area Acres | No of farmers | Any constraints? | Method of adding biomass | Is practice still followed | If no why |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2008-2018(last 10 years) |  |  |  |  |  |  |  | - |  |
|  | 1998-2008 (10-20 years back) |  |  |  |  |  |  |  |  |  |
|  | 1988-1998 (20-30 years back and before that) |  |  |  |  |  |  |  |  |  |

  - Table # Soil 5: LMU wise Crop Residues Management Experience

| Sr No | Time period | Practice | Crop | Area in Acres | No of Farmers |
| --- | --- | --- | --- | --- | --- |
|  | 2008-2018 (last 10 years) | Crop Residue Burning |  |  |  |
|  |  | Incorporating into Soil |  |  |  |
|  |  | Using for compost |  |  |  |
|  | 1998-2008 (10-20 years back) | Crop Residue Burning |  |  |  |
|  |  | Incorporating into Soil |  |  |  |
|  |  | Using for compost |  |  |  |
|  | 1988-1998 (20-30 years back and before that) | Crop Residue Burning |  |  |  |
|  |  | Incorporating into Soil |  |  |  |
|  |  | Using for compost |  |  |  |

  - Table # Soil 6: LMU wise Soil Conservation Works Experience

| LMU | Time period | Which soils had more soil erosion | What were the interventions | How many units | Acrs covered | Scheme | How was the quality | Do farmers Maintain them? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| #1 | In last 10 years | Red | Earthen bunding | 100 rmt | 1 | NREGS | Poor | No |
|  | 10 years back |  |  | 12 | 25 | 2 T loads |  |  |
|  | 20 years back |  |  |  |  |  |  |  |
| #2 | …. |  |  |  |  |  |  |  |
|  | …. |  |  |  |  |  |  |  |

- Do farmers plough off the earthen bunds?

- According to the farmers, Which is the best method to prevent soil erosion?

- LMU wise Strategic Plans

  - Table # Soil 7: Strategic plan for compost production and crop residue management

| Sl No | LMU # | No of farmers for In-situ composting | No of farmers at homestead/ cattle shed | No of farmers for sheep penning |
| --- | --- | --- | --- | --- |

Note:

- Discuss the economic benefit of Sheep penning. Explore whether farmers can take loan for this intervention. Discuss the repayment conditions.

- Compost production will be supported by plantation (around the compost pit and bunds) and crop residues management.

- Crop residues can be cut into small pieces using shredder (Show video). This equipment can be kept in Custom Hiring Centre on rentals.

- Glyricedia plantation can be taken up on bunds and around the compost pits. In first year seed dibbling can be taken up.

  - Table # Soil 8: Strategic plan for Tank Silt Application

| Sl No | LMU # | No of Farmers | Area (Acrs) | Source | Distance (KM) | Tractors/Acr | Cost per Trip | Farmers’ Contribution | Farmers’ Responsibilities |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Note: Discuss the following

- Present Cost of silt application per acre

- Impact of tank silt application in terms of increase in income (main product and bye products)

- Explore can farmers take loan and repay? Discuss repayment conditions

- Discuss operational modalities

- What responsibilities farmers would take up?

- What is the method of contribution?

- How do farmers ensure that the silt is transported to “Learning Site” only?

  - Table # Soil 9: Strategic plan for controlling erosion in key locations

| Sl No | LMU # | Most suitable interventions | No of Farmers | Area (Acrs) | Most suitable scheme | Farmers’ Contribution | Farmers’ Responsibilities |
| --- | --- | --- | --- | --- | --- | --- | --- |

  - Table # Soil 10: Strategic plan for Adding biomass to soils

| Sl No | LMU # | Plants for adding biomass | No of Farmers | Area (Acrs) | Where are the plants available? | How to access them? Any scheme | What green manure crop do you like to grow | No of Farmers | Area (Acrs) | Any constraints in growing these green manure crops? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Greengram |  |  |  |

Planning Exercise on Component #2: Water and Protective irrigation

Purpose:

Overall:Plan for protecting crops against drought spells at sowing and during different stages of crop growth.

Specific:

  - Identify crops cultivated and their drought vulnerability

  - Map and assess water resources in the “learning site” and identify areas that are highly vulnerable to drought spells.

  - Plan for securing crops in the vulnerable areas against drought spells:

    - At sowing stage

    - At crop growth stages

  - Create necessary infrastructure (water bodies or irrigation equipment) to meet the planned requirements

Process:

- Exploration

- Mapping Water Resources in the Learning Site:

  - Use the Base Map with drainage lines

  - Map water bodies on the map:

    - drainage lines, checkdams, tanks, ponds and other water bodies. Note for each water body:

    - Map the borewells and open wells

    - Number each water body (surface and groundwater)

  - For each waterbody (surface and groundwater) ask for the following:

    - Ownership (name of owner(s) & private or common)

    - Last month of water availability (i.e. when it dries up?).

- Mapping Irrigated Areas and Crops irrigated

    - Name of the crop and extent of area presently irrigated by each water body, both for kharif and Rabi (also, map the plots irrigated on the map).

    - Irrigation practices used in each water body: flood flow, channels, sprinklers, drips

- When do drought spells occur? (Types of droughtspells)

    - On a calendar (15 days interval from 15th May to 31st Dec) mark the perception of droughtspells (of about 10 days & of about 15 days); i.e. when does drought spell of these two durations occur.

- At sowing time

- during crop growth

    - Map/ list the water bodies (surface and groundwater) where water is available during the period.

- Map drought vulnerable areas (LMUs)

    - Take three categories of drought vulnerability; severe, medium and low

    - Mark all the plots/ LMUs vulnerable to drought spells on the map and also list them in a Table: LMU number, Crop and Severity of drought vulnerability

- Assess the Losses due to droughtspells& Opportunity of Protective irrigation: (this can be done with key 3 to 5 key farmers and shared with all)

How much water is required per each irrigation?

      - 1 acre = 4046 sq.m

      - 10 mm irrigation (depth) = 10/1000 = 0.01 meters

      - 10 mm irrigation in one acre = 4046 x 0.01 cubic meters = 40.46 cu.m

      - 1 cu.m = 1000 liters i.e.; 40.46 cu.m = 40460 liters of water.

      - 1 tanker is 5000 liters i.e. roughly 8 tankers.

      - A life saving irrigation (expecting crop will survive and catch up with next rains in about a week time) is 10 to 20 mm.

A good irrigation is 40 mm. (1.6 lakh liters of water

Assess losses of drought spells: mild, moderate and severe – per acre and per each LMU

    - Assess scenarios of providing protective irrigation and their economic benefit (yields protected and yield enhanced)

      - One irrigation at sowing enabling timely sowing

      - One or 2 irrigations at critical stages of crop growth

    - What would be the economic benefit per each irrigation?

    - >> the potential economic benefit per cubic meter of water.

    - >>Say if the benefit is Rs.5000 per life saving irrigation i.e. 40 cu.m or 8 tankers of water; it is worthwhile for farmer to invest say, Rs.2000 to 3000 on each irrigation.

    - >>Alternately, the potential loss can also be compared.

    - >>The above exercise is to make a case for investing on protective irrigation.

- Arriving at Strategic Plans:

- Planning for Protective Irrigation from Existing Sources

    - For each LMU area (numbered) identify sources of protective irrigation on the map.

    - Assess if the water bodies will have water during the stage.

- Provide Inputs on Protective Irrigation Options: (Use Flip Chart on Protective Irrigation)

    - Ensuring Timely Sowing: (show the photographs/ flip chart slides)

      - Option 1: Row wetting and seeding. If the forecast is not very negative and when rains are expected within 10 to 15 days; instead of losing the season – farmer can sow row crops like redgram by applying water. Aquaplanter – for groundnut for e.g. enables it.

      - Option 2: Tanker providing irrigation attached with a plough (seeding).

    - Protective Irrigation with Lined Farm Ponds:(discussion with photographs)

      - Each farm pond of size 10 m x 10m x 2.5 m = 250 cu.m volume

      - 5 acres x 100 mm rainfall

      - 5  acres x 4046 sq.m/ac x 100/1000 meter rainfall = 2023 cu.m rain water.

      - Of this even 20% is runoff = 404 cu.m of runoff water that can be collected into farm ponds. This is more than one filling of the farm pond. Experience suggests that such farm ponds (1 in 5 acres drainage area) can fill 2 to 3 times during a season depending on rainfall.

    - Water lifting devises & Diesel / electric Pumps:

    - Mobile Protective Irrigation:

      - Water can also be transported within limited/ economic distances. Explore if such options exist. There are 2 possibilities:

          - Pumping from any water source – tank / borewell / open well and irrigating using sprinklers/ drips.

          - Filling in a tanker from a water source and transporting to the field.

      - Arrive at number of sprinklers, pipes, pumps etc., required to be placed at the Custom hiring Centers (CLiCs). This also includes aquaplanters.

- Plan for Farm Ponds:

    - Mark best locations for farm ponds on the map; along with the names of farmers and plot numbers.

    - Since every plot can’t have farm ponds; agreements have to be reached among neighboring farmers on water sharing  from farm ponds.

    - Site verification and farmers’ consent (including on contribution) to be taken later.

    - How do we prioritize the farm ponds as the total budget available for this purpose is limited. (one way is to allocate within LMUs).

    - Arrive at the list of prioritized farm ponds

- Explore Possibilities of Groundwater Collectivisation:

    - Explain about groundwater collectivization.

    - If there is potential, this can be taken up separately.

    - Get the farmers and area that they would like to bring under collectivization.

- Establishing a Rain-guaze:

    - For monitoring rainfall, drought spells etc., it is important to install a rainguage (even a low cost one) at the FFS sites. This along with weather forecasts help in arriving at decisions on protective irrigation for each LMUs.

    - Identify location, who takes responsibility of recording etc.

- Drinking Water for Livestock:

    - Mark the normal livestock tracks passing through the “Learning Site”

    - Plan and provide for a water trough (with small height for small ruminants) that can be filled with a borewell (or other source) for livestock drinking water.

- Summary of the Protective Irrigation Plans:

    - The LMUs marked on the map (numbered) with their drought vulnerability status.

    - Plan (source) of protective irrigation for each numbered LMU.

    - How many LMUs are covered and how many not covered? Reasons for non-coverage.

    - LMU wise sources for protective irrigation & agreement of the group (and consent for the farmer on sharing water).

    - Sharing agreements and consent letters from farmers on water sharing.

    - What are the protective irrigation related equipment required? Norms for their use.

Table # Water 11: Compilation of information on Surface water bodies:

| Sl No |  | 1 | 2 | 3 | 4 | 5 | 6 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Name of the WHS @ |  |  |  |  |  |  |
| 2 | Location of WHS |  |  |  |  |  |  |
| 3 | Owner Name |  |  |  |  |  |  |
| 4 | Last month of water availability |  |  |  |  |  |  |
| 5 | Whether water is used for irrigation? |  |  |  |  |  |  |
| 6 | Kharif Crops irrigated |  |  |  |  |  |  |
| 7 | Kharif Area Irrigated (Acr) |  |  |  |  |  |  |
| 8 | No of Farmers in Kharif |  |  |  |  |  |  |
| 9 | Rabi Crops |  |  |  |  |  |  |
| 10 | Rabi Area (Acr) |  |  |  |  |  |  |
| 11 | No of Farmers in Rabi |  |  |  |  |  |  |
| 12 | Method of irrigation |  |  |  |  |  |  |
| 13 | Condition of structure |  |  |  |  |  |  |
| 14 | Major Issues, if any |  |  |  |  |  |  |
| 15 | How do you lift water? |  |  |  |  |  |  |
| 16 | At which stage of the crop? |  |  |  |  |  |  |
| 17 | Plan for improving structure |  |  |  |  |  |  |
| 18 | Plan for utilising the structure |  |  |  |  |  |  |

(Farm pond, Irrigation Tank, Percolation Tank, check dam)

Table # Water 12: Mapping Crop stage dates and Dry Spell Dates

| Sl No | Crops | Crop stages and Dates |  |  |  |  |  |  |  |  | Dry Spell dates |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Land Prepa-ration | Sowing | Germi-nation | Crop Growth | Flowering | Peg Formation | Pod/ fruit formation | Maturity stage | Harve-sting | 1st | 2nd | 3rd | 4th |

Table # Water 13: Compilation of information on Groundwater resources:

| Sl No | Name of the owner | Bore/ Open well | Year of digging | Total Depth of the well (Ft) | Water level (ft) | Area under irrigation (Acr) | Crops | Method of irrigation | Number of users (other than owners) | Area under protective irrigation | Whether willing to share water |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Table # Water 14: Plan for protective irrigation Farmer wise in each patch (For those who require only)

| Sl No | Name of the Farmer | Area (Acr) | Crops | Number of irrigations required | Nearest possible Water resource | Method/ means of protective irrigation # | Water saving device $ | Equipment required (Type and Number) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

# 1-Diesel pump, 2-Water tanker, 3-pipe line grid				$ 1- rain gun, 2-sprinkler 3- pipe

Every LMU: Explain more details about the water sharing plan proposed (Min 1 page)

Planning Exercise on Component #3: Crop Systems and Seed

Overall Purpose:  Plan for diversifying the crop systems to increase climate resilience and

Specific Purpose:

- Mapping existing agronomic practices specific to crop systems, patterns and seed availability

- Planning the options to increase climate resilience through reducing diversifying crops

- Create necessary support systems (seed and information)

Process:

- Exploration

  - Mapping Past and present crop systems and management practices

    - Ask the farmers to list the crops during this 10 years, 11-20 years and 21-30 years

    - What is the reason for adapting this cropping systems? What are the advantages?

    - What are the reasons for quitting the previous crop systems

    - Is it good for soil health?

    - Does this consume less water?

    - Is it climate resilient?

    - Is it reducing cost of cultivation?

    - What is the net income?

  - Ask the farmers about options to utilize the rainfall throughout the year

  - Ask the farmers options to get most from the land

    - Food grains

    - Fodder

    - Soil Biomass

    - Expanding the duration of soil cover, etc

- Arriving at Strategic Plans

  - Is the present cropping system drought resilient and most economical?

  - What is the spread of rains in a year

  - Can we diversify the crops to utilize rainfall available throughout the year to cover soils, to get more crops in a single season?

    - What crops can be mixed (straight growing/erect, bushy, creepers, etc)

    - Provide information on alternative crops

    - Share experiences from other villages (photos, charts and videos)

  - If yes, what do we do?

  - If not, why?

  - What needs to be done to reduce the loss, increase income, food grains, fodder, etc.

  - Seed production

    - What seeds are available?

    - What seeds need to be produced?

    - Volunteering farmers to take up “seed production” and supply seed locally.

- Arriving at Detailed Plans

  - List of interested Resource farmers: Identify 2-3 resource farmers and learning plots for FFS

  - Identify the farmers who would adapt Climate resilient cropping systems

Table # Crop systems 15: Mapping existing cropping patterns

| Sl No | Time Period | Season | Main Crop |  |  |  |  |  | Inter crop (s) |  |  |  |  |  | Boarder crop (s) |  |  |  |  |  | Vulnerability to Drought $ | Crop Loss % due to drought |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Name | No of farmer | Area (Acr) | Seed Type@ | Source of seed | Bye products # | Name | No of farmer | Area (Acr) | Seed Type@ | Source of seed | Bye products # | Name | No of farmer | Area (Acr) | Seed Type@ | Source of seed | Bye products # |  |  |
| 1 | Present Practice | Kharif |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Rabi |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Last 10-20 years | Kharif |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Rabi |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Before 20 years | Kharif |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Rabi |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

@ Seed Type: Local/ Improved			# Bye Products: Fodder/ Husk/ Bran		$ (Severe/Medium/Low)

- Reasons for shifting crops (if any)

- Explain the constraints in accessing seed

- Explain the constraints in preserving seed:

- Explain about seed quality and germination

Table # Crop Systems 16: Crop Calendar in rainfed areas

Mention the time period: From date - To date.

| Crop Name | Season | Land Preparation | Sowing | 1st Weeding | 2nd weeding | 3rd weeding | Inter cultivation | Harvesting |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Groundnut | Kharif | May5th -25th | June 7th to20th June | July 15th to july25th | August 5th to 10th |  |  |  |

Table # Crop Systems 17: Strategic Plan for Crop Systems and Seed

| LMU Name |  |
| --- | --- |
| Major issues in present crops and seed |  |
| List of past good practices |  |
| Constraints in following good practices |  |
| Which drought resistant crops you want to grow? |  |
| Which fodder crops you want to grow |  |
| Which food crops you want to grow (Name the crops) |  |
| If you want to grow mixed/ Inter crops, what are they? |  |
| How many farmers want to do “Seed Production”? Which crops? |  |
| What are the Top 3 constraints you want to ease |  |

Planning Exercise on Component #4: ZBNF

Overall Purpose:  Plan for promoting sustainable agriculture practices in ZBNF model through four key practices:

- Extension by a practicing resource farmer

- Dissemination of knowledge and handholding in practice using community video

- Establishing an NPM shop

- Organizing farmers

Specific Purpose:

- Mapping existing agronomic practices specific to Pest/ Disease management and Soil Fertility Enhancement

- Planning the options to increase climate resilience through ZBNF practices

- Create necessary support systems

Process:

- Exploration

  - Mapping crop wise pest problems and management practices

    - Ask the farmers to list the major crops on a chart paper

    - Map the major pest and diseases related problems at every stage (But the pest and disease information should be captured in separate tables)

    - Capture existing practices to manage pests and diseases

  - Mapping Crop/Land wise soil fertility related practices

    - Mapping application of chemical fertilizers

    - Mapping application of compost practices

- Arriving at Strategic Plans

  - Is your problem solved by chemical pesticides?

  - Can we shift to ZBNF practices, this year onwards?

    - Provide alternative/climate resilient ZBNF practices using flip charts and videos

  - If yes, what do we do?

  - If not, why?

  - What needs to be done for improving soil fertility, pest and disease control

- Arriving at Detailed Plans

  - List of interested Resource farmers: Identify 2-3 resource farmers and learning plots for FFS

  - Identify the farmers who would adapt ZBNF practices

Name of the LMU:

Table # ZBNF 18: Mapping Pest problems and management practices

| Crop | Timeline | Seed Storage | After sowing | Seedling | Vegetative Growth | Flowering | Fruit formation | Maturity | harvesting |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Issues |  |  |  |  |  |  |  |  |
|  | Present practices |  |  |  |  |  |  |  |  |
|  | Practices 10 years back |  |  |  |  |  |  |  |  |
|  | Practices 20 years back |  |  |  |  |  |  |  |  |

Table # ZBNF 19: Mapping Disease Problems and Management practices

| Crop | Timeline | Seed Storage | After sowing | Seedling | Vegetative Growth | Flowering | Fruit formation | Maturity | harvesting |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Issues |  |  |  |  |  |  |  |  |
|  | Present practices |  |  |  |  |  |  |  |  |
|  | Practices 10 years back |  |  |  |  |  |  |  |  |
|  | Practices 20 years back |  |  |  |  |  |  |  |  |

Table # ZBNF 20: Proposed ZBNF practices in Pests, Diseases and Soil Fertility

| Crop | Particulars | Seed Storage | After sowing | Seedling | Vegetative Growth | Flowering | Fruit formation | Maturity | Harvesting |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Practice |  |  |  |  |  |  |  |  |
|  | Cost |  |  |  |  |  |  |  |  |

Planning Exercise on Component #5: Implements and Farm machinery

Purpose:

- To assess the existing practices in using farm implements for different purposes

- To assess the need-demand-availability-gap

- To assess the scope for establishing a custom hiring centre

- Exploration

- What is the equipment not available with you, therefore you are missing the timely operations?

- What are the ways and means to reduce drudgery on labour or women?

- What do you do if the material is not available or scarce?

- Is equipment available on rent? If Yes, what are they? What is the rent?

- Is it accessible to you? What do you do if the service/hiring cost is higher?

- Which type of crop operation, the existing farm equipment is not appropriate?

  - Land preparation

  - Seed sowing

  - Weeding

  - Inter cultivation

  - Providing irrigation

  - harvesting

  - Cutting residues

  - Postharvest processing

- Do you know what is the appropriate equipment?

Table # CHC 21:

| Sl No | Operation | Equipment | Number available (own) | Number available (Rent) | Labour friendly (yes/No) | Needed? |
| --- | --- | --- | --- | --- | --- | --- |

Annexure: Indicative list of Farm equipment and costs

| SL No. | Name of Implement | Soil Type | Crop | Operation | Cost | Hiring cost | Maintenance | Remark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Two bottom MB plough | Red and Black soil (dryland) with small pebbles | All crops except Paddy | Tillage operation 35HPor above tractor | 23,000 | Rs 70/hr | Skilled labor required. The maintenance is supported by CRIDA KVK farm | at CHC and KVK farm |
| 2 | Cultivator | All type of soils | All crops | Tillage operation 35HPor above tractor | 18,000 | Rs 100/hr | Skilled labor required. The maintenance is supported by CRIDA KVK farm | at CHC and KVK farm |
| 3 | Disc Harrow | All type of soils (dryland) | All crops except Paddy | Land levelling and green manure mulching.35HPor above tractor | 28,000 | Rs 100/hr | Skilled labor required. The maintenance is supported by CRIDA KVK farm | at CHC and KVK farm |
| 4 | Rotavator | Red and Black soil (dryland) with small pebbles | All crops | Land levelling and green manure mulching. 6ft width of working.45-55HP tractor | 55,000 | Rs 120/hr | Skilled labor required. | At KVK farm |
| 5 | Iron Plough | All type of soils (dryland) | All crops except Paddy | Tillage operation.1 pair of bullock | 2,500 | Rs 25/day | Local trained person, welding shop | at CHC and KVK farm |
| 6 | Fertilizer Broadcastor | NA | All crops | Fertilizer application, maintaining fertilizer dose recommended. 1 person operated by rotating handle. 10kg capacity | 1800 | Rs 20.day | Local trained person | At CHC |
| 7 | Diesel Engine | NA | All crops | 3 HP, used for puming water for irrigation purpose | 23,000 | Rs 150/day | Skilled labor required. The maintenance is supported by CRIDA KVK farm | At CHC |
| 8 | Cotton Picking machine | NA | Cotton | Picking of cotton fibers. Currently in demo mode | 8600 | Rs 200/day | Skilled labor required. The maintenance is supported by CRIDA KVK farm | At CHC |
| 9 | SRI marker | Red and Black soil (wetland) | Paddy | For marking/layout in wet land for transplanting | 3000 | Demo | Local trained person | at CHC and KVK farm |
| 10 | Winnower Fan | NA | Paddy | for winnowing of harvested crop. Operated by electric motor |  | Rs 200/day | Skilled labor required. The maintenance is supported by CRIDA KVK farm | at CHC |
| 11 | small weighing Machine | NA | all crops | Weighing produce. Upto 10 kg load | 4500 | Rs 10/day | Skilled labor required. The maintenance is supported by CRIDA KVK farm | at CHC |
| 12 | Weighing machine | NA | all crops | Weighing produce. Upto 50kg load | 24000 | Rs 100/day | Skilled labor required. The maintenance is supported by CRIDA KVK farm | at CHC |
| 13 | Tool Kit | NA | NA | to carry out maintenance and adjustment of farm machinery | 6000 | NA | Local trained person | at CHC |
| 14 | Taiwan Sprayer | NA | all crops | Pesticide application. Petrol engine operated, 1.5 HP. Covers 1 acre in 1 hr | 15000 | Rs 100/day | Skilled labor required. The maintenance is supported by CRIDA KVK farm | at CHC and KVK farm |
| 15 | Sprinkler set | NA | All crops except Paddy | Irrigation to crop. 4kgf pressure,75mm HDPE pipe, operated with help of 3HP diesel engine | Rs 560/pipe | Rs 5/pipe | Skilled labor required. The maintenance is supported by CRIDA KVK farm | at CHC |
| 16 | Chaff cutter | NA | Maize, Jowar, fodder crops | Fodder preparation for feeding purpose. Operated by electric motor | 25000 | Rs 10/per bundle (100kg) | Local trained person | at CHC |
| 17 | Drum Seeder | Black soil (wetland) | Paddy | Sowing of paddy without transplantation | 4000 | Demo | Local trained person | at CHC and KVK farm |
| 18 | Manual weeder | All soil (dryland) | All crops, vegetables except Paddy | Weeding operation, operated by 1 person, coverage 0.5acre (woman); 0.75 acre (man) | 1000 | Rs 10/day | Local trained person | at CHC and KVK farm |
| 19 | Sprayer | NA | All crops | pesticide application operated by one person | 3000 | Rs 30/day | Skilled labor required. The maintenance is supported by CRIDA KVK farm | at CHC |
| 20 | Bush cutter | NA | Paddy, shrubs | harvesting of paddy, cutting shrubs and bushes. 1.5hp motor (petrol) | 24000 | Rs 500/day | Skilled labor required. The maintenance is supported by CRIDA KVK farm | at CHC and KVK farm |
| 21 | Seed treatment Drum | NA | All crops | Seed treatment of seed before sowing with chemical/bio culture | 1500 | Demo | Local trained person | at CHC |
| 22 | Power Weeder | All soil (dryland) | All crops with row to row spacing; mostly suitable for Redgram | For weeding operation;1.5 HP petrol Engine; Working width adjustable range 45-90cm by removing blade;operation 0.5ft spacing from crops row | 18000 | Rs 75/hr | Skilled labor required. The maintenance is supported by CRIDA KVK farm | at CHC and KVK farm |
| 23 | Power Weeder (small) | All soil (dryland and wetland) | All crops with R-R spacing | For weeding operation;1HP petrol engine;1 Person;fixed working width 30cm |  | NA | Skilled labor | At KVK farm |
| 24 | Power Sprayer | NA | All crops | Pesticide application; 0.5HP motor | 5000 | Rs 50/day | Skilled labor required. The maintenance is supported by CRIDA KVK farm | at CHC |
| 25 | Rotary Sprayer | NA | All crops | Pesticide application; manually operated 1 person; outdated | 3000 | Rs 20/day | Local trained person | at CHC |
| 26 | Foot Sprayer | NA | Orchard crops | Pesticide application; manually operated 1 person;Paddle operated |  | Rs 50/day | Skilled labor required. The maintenance is supported by CRIDA KVK farm | at CHC |
| 27 | Seed drill Plough | All soils (dryland) | All crops except Paddy, small grains crops (chilly, cotton) | Sowing of crops; 1 pair of bullocks with 1 person; made of iron; Seed and fertilizer box; 1acre/day | 950 |  | Local trained person | At KVK farm |
| 28 | 2-Row seed planter | All soils (dryland) | All crops except Paddy, small grains crops (chilly, cotton) | Sowing of crops with 2 row; 1 pair of bullocks with 1 person; made of iron; Separate Seed and fertilizer box with seed metering device;2-2.5acre/day;adjustable row (30-60cm) with seed depth control provision;intercropping sowing also possible | 17000 |  | Local trained person | At KVK farm |
| 29 | 3-Row seed planter | All soils (dryland) | All crops except Paddy, small grains crops (chilly, cotton) | Sowing of crops with 3 row; 1 pair of bullocks with 1 person; made of iron; Separate Seed and fertilizer box with seed metering device;adjustable row (30-90cm) with seed depth control provision;intercropping sowing also possible | 18000 | Rs 200/day | Local trained person | At KVK farm |
| 30 | Bullock weeder | All soils (dryland) | All crops except paddy | Weeding operation;1-pair bullock 1 person;adjustable width of working (30,45,60cm) blades;1-1.5acres/day | 2800 |  | Local trained person | At KVK farm |
| 31 | Vegetable Perservator | NA | Vegetables | for storing vegetables; maintain 12-18°C below outside temp; Manual; can preserve for 4-6 days;water feeding 7 liters per day; capacity 5,15,50 kg | 1600;2800; 3600 |  | Local trained person | At KVK farm |
| 32 | Castor sheller | NA | castor | post harvesting; 700kg/hr capacity;operated by 1Hp electric motor | 55000 |  | Skilled labor | At KVK farm |
| 33 | Orchard Sprayer | NA | Orchard crops mango, orange | Pesticide application;35Hp or above tractor;operate upto 15 ft height | 65000 |  | Skilled labor | At KVK farm |
| 34 | Six row seed planter | All soils (dryland) | All crops except Paddy, small grains crops (chilly, cotton) | Sowing of crops with 6 row;35Hp or above tractor; Separate Seed and fertilizer box with seed metering device;adjustable row (30,45,60,90,120cm) with seed depth control provision;intercropping sowing also possible;6-8 acres/day coverage | 40500 |  | Skilled labor | At KVK farm |
| 35 | 9-Row seed planter | All soils (dryland) | All crops except Paddy, small grains crops (chilly, cotton) | Sowing of crops with 9 row;45Hp or above tractor; Separate Seed and fertilizer box with seed metering device;adjustable row (30,45,60,90,120cm) with seed depth control provision;intercropping sowing also possible;9-10 acres/day coverage | 43500 |  | Skilled labor | At KVK farm |
| 36 | Sheeder | All soils (dryland) | Maize, castor,red gram, crop of height 4-6ft | for mulching left portion of harvested crop in soil;55Hp tractor; PTO driven | Demo |  | Skilled labor | At KVK farm |
| 37 | Herbicide zero Tillage Planter | All soils (dryland) | All crops except paddy | Zero tillage operation;capability of working in land with slopes;sowing,tillage and weedicide application simultaneously;35Hp or above tractor |  |  | Skilled labor | At KVK farm |
| 38 | Bed maker Planter | All soils (dryland) | All crops except small size grain | Sowing on bed prepared and ridge at both side; 35Hp tractor;seed cum fertilizer | Testing Mode |  | Skilled labor | At KVK farm |
| 39 | Zero tillage Maize planter | All soils (dryland) | Maize | Sowing with zero tillage; seed cum fertilizer; based on 295 planter model (Canada);35Hp tractor. |  |  | Skilled labor | At KVK farm |
| 40 | 295 Planter | All soils (dryland) | All crops except paddy | Sowing with seed cum fertilizer;developed by Canada | only for Demo |  | Skilled labor | At KVK farm |
| 41 | Groundnut decorticator | NA | Groundnut | Threshing;manual and 1Hp motor operated; for detaching groundnut from plants | 25000; 35000 |  | Skilled labor | At KVK farm |
| 42 | Paddy Harvestor | All soils (dryland) | Paddy | Harvesting of paddy and binding in bundles; self-operated engine |  |  | Skilled labor | At KVK farm |

TABLES

Climate Resilient Rainfed Agriculture in Leaning Site

District			:					Mandal	:

Gram Panchayat	:					Habitation	:

LFA			:					FA		:

Table # Gen 1: Farmers List in Learning Site

| Sl No | Name of the Farmer | Father/ Husband Name | Aadhar | Area | Survey Number | LMU |
| --- | --- | --- | --- | --- | --- | --- |

Table # Gen 2: LMU characteristics

| LMU Name | Approximate Area (acres) | Soil Texture (Clayey, loam, silt and sandy) | Soil Color (Red, Black, Light) | Depth of Top layer (deep: >60cm, medium: 11-60 cm, shallow: <=10cm) | Slope (high, medium, low) | Soil Type (partly ploughed, Ordinary, Hard, SDR*) | Water holding capacity (high, medium, low) | Specific Problems | Fertility status (good, average, poor) | Crop systems that are generally taken up |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

*SDR: Soft Disintegrated rock			**If multiple characteristics are present, then mention % of each of them (For Ex clay 70%, saline 30%)

LMU Wise Description (commons, vegetation, wild animal’s issue, difficulty in Agri operations etc.)

Table # Soil 1: Soil Testing (on sample basis, 2 farmers/LMU)

| Sl No | Soil Testing Farmer Name | Date of Testing | Soil Testing Report Available? | Status of organic carbon | Status of Macro nutrients | Status of micro nutrients | Key recommendations | What recommendation are implemented |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |

Table # Soil 2: LMU wise Experiences

| Sr No | Year | Type of manure | Acres | No of farmers | Approx. Qty/acre (Number and Units) | Is the practice continued | If not why | Should it be revived? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2008-2018(last 10 years) | Compost |  |  |  |  |  |  |
|  |  | FYM |  |  |  |  |  |  |
|  |  | Green Manure |  |  |  |  |  |  |
|  |  | Sheep Penning |  |  |  |  |  |  |
|  |  | Gypsum |  |  |  |  |  |  |
|  |  | Fertilizer |  |  |  |  |  |  |
|  | 1998-2008 (10-20 years back) | Compost |  |  |  |  |  |  |
|  |  | FYM |  |  |  |  |  |  |
|  |  | Green Manure |  |  |  |  |  |  |
|  |  | Sheep Penning |  |  |  |  |  |  |
|  |  | Gypsum |  |  |  |  |  |  |
|  |  | Fertilizer |  |  |  |  |  |  |
|  | 1988-1998 (20-30 years back and before that) | Compost |  |  |  |  |  |  |
|  |  | FYM |  |  |  |  |  |  |
|  |  | Green Manure |  |  |  |  |  |  |
|  |  | Sheep Penning |  |  |  |  |  |  |
|  |  | Gypsum |  |  |  |  |  |  |
|  |  | Fertilizer |  |  |  |  |  |  |

What are the Constraints at present, in application different types of manures in this patch? Please explain:

Table # Soil 3: LMU wise Tank Silt Application Experience

| Sl No | Year | Type of Input (Silt, Sand, Soil) | Acres covered by application (Acr) | No of farmers | Source of silt | Distance (Km) | Quantity/ acre | Quality (Good/ Not good) | Any Project? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2008-2018 (last 10 years) |  |  |  |  |  |  |  |  |
|  | 1998-2008 (10-20 years back) |  |  |  |  |  |  |  |  |
|  | 1988-1998 (20-30 years back and before that) |  |  |  |  |  |  |  |  |

Table # Soil 4: LMU wise adding Biomass Experience

| Sr No. | Time period | Type of biomass | Source (common land, own fields) | Distance if common land (km) | Area Acres | No of farmers | Any constraints? | Method of adding biomass | Is practice still followed | If no why |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2008-2018 (last 10 years) |  |  |  |  |  |  |  | - |  |
|  | 1998-2008 (10-20 years back) |  |  |  |  |  |  |  |  |  |
|  | 1988-1998 (20-30 years back and before that) |  |  |  |  |  |  |  |  |  |

Table # Soil 5: LMU wise Crop Residues Management Experience

| Sr No | Time period | Practice | Crop | Area in Acres | No of Farmers |
| --- | --- | --- | --- | --- | --- |
|  | 2008-2018 (last 10 years) | Crop Residue Burning |  |  |  |
|  |  | Incorporating into Soil |  |  |  |
|  |  | Using for compost |  |  |  |
|  | 1998-2008 (10-20 years back) | Crop Residue Burning |  |  |  |
|  |  | Incorporating into Soil |  |  |  |
|  |  | Using for compost |  |  |  |
|  | 1988-1998 (20-30 years back and before that) | Crop Residue Burning |  |  |  |
|  |  | Incorporating into Soil |  |  |  |
|  |  | Using for compost |  |  |  |

Table # Soil 6: LMU wise Soil Erosion Control Experience

| Sr No | Time period | Which soils have more Erosion | What were the key activities implemented | Name of Units | Number of Units | No of farmers | Acres covered | Scheme | How was the quality (Good/ Ok/ not good) | If Not good, reasons for that | Do farmers Maintain them? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2008-2018 (last 10 years) |  |  |  |  |  |  |  |  |  |  |
|  | 1998-2008 (10-20 years back) |  |  |  |  |  |  |  |  |  |  |
|  | 1988-1998 (20-30 years back and before that) |  |  |  |  |  |  |  |  |  |  |

Summary Table # Soil 7: Strategic plan for Soil Health Improvement

| LMU Name |  |
| --- | --- |
| Major soil related Issues |  |
| List of good practices |  |
| Reasons for abandoning them |  |
| Major Suggestion for soil health improvement in this LMU |  |

Table # Soil 7: Strategic plan for compost production and crop residue management

| Sl No | LMU | No of farmers for In-situ composting | No of farmers at homestead/ cattle shed | No of farmers for sheep penning |
| --- | --- | --- | --- | --- |

Note:

- Discuss the economic benefit of Sheep penning. Explore whether farmers can take loan for this intervention. Discuss the repayment conditions

- Compost production will be supported by plantation (around the compost pit and bunds) and crop residues management.

- Crop residues can be cut into small pieces using shredder (Show video). This equipment can be kept in Custom Hiring Centre on rentals.

- Glyricedia plantation can be taken up on bunds and around the compost pits. In first year seed dibbling can be taken up.

Table # Soil 8: Strategic plan for Tank Silt Application

| Sl No | LMU | No of Farmers | Area (Acrs) | Source | Distance (KM) | Tractors/Acr | Cost per Trip | Farmers’ Contribution | Farmers’ Responsibilities |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Note: Discuss the following

- Present Cost of silt application per acr

- Impact of tank silt application in terms of increase in income (main product and bye products)

- Explore can farmers take loan and repay? Discuss repayment conditions

- Discuss operational modalities

Table # Soil 9: Strategic plan for controlling Soil erosion in key locations

| Sl No | LMU | Most suitable interventions | No of Farmers | Area (Acrs) | Most suitable scheme | Farmers’ Contribution | Farmers’ Responsibilities |
| --- | --- | --- | --- | --- | --- | --- | --- |

Table # Soil 10: Strategic plan for Adding biomass to soils

| Sl No | LMU | Most suitable plants to grow on bunds | No of Farmers | Area (Acrs) | Where are the plants available? | How to access them? Any scheme | What green manure crop do you like to grow | No of Farmers | Area (Acrs) | Any constraints in growing these green manure crops? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Table # Water 11: Compilation of information on Surface water bodies:

| Sl No |  | 1 | 2 | 3 | 4 | 5 | 6 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Name of the WHS @ |  |  |  |  |  |  |
| 2 | Location of WHS |  |  |  |  |  |  |
| 3 | Owner Name |  |  |  |  |  |  |
| 4 | Last month of water availability |  |  |  |  |  |  |
| 5 | Whether water is used for irrigation? |  |  |  |  |  |  |
| 6 | Kharif Crops irrigated |  |  |  |  |  |  |
| 7 | Kharif Area Irrigated (Acr) |  |  |  |  |  |  |
| 8 | No of Farmers in Kharif |  |  |  |  |  |  |
| 9 | Rabi Crops |  |  |  |  |  |  |
| 10 | Rabi Area (Acr) |  |  |  |  |  |  |
| 11 | No of Farmers in Rabi |  |  |  |  |  |  |
| 12 | Method of irrigation |  |  |  |  |  |  |
| 13 | Condition of structure |  |  |  |  |  |  |
| 14 | Major Issues, if any |  |  |  |  |  |  |
| 15 | How do you lift water? |  |  |  |  |  |  |
| 16 | At which stage of the crop? |  |  |  |  |  |  |
| 17 | Plan for improving structure |  |  |  |  |  |  |
| 18 | Plan for utilising the structure |  |  |  |  |  |  |

(Farm pond, Irrigation Tank, Percolation Tank, check dam)

Table # Water 12: Mapping Crop stage dates and Dry Spell Dates

| Sl No | Crops | Crop stages and Dates |  |  |  |  |  |  |  |  | Dry Spell dates |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Land Prepa-ration | Sowing | Germi-nation | Crop Growth | Flowering | Peg Formation | Pod/ fruit formation | Maturity stage | Harve-sting | 1st | 2nd | 3rd | 4th |

Table # Water 13: Compilation of information on Groundwater resources:

| Sl No | Name of the owner | Bore/ Open well | Year of digging | Total Depth of the well (Ft) | Water level (ft) | Area under irrigation (Acr) | Crops | Method of irrigation | Number of users (other than owners) | Area under protective irrigation | Whether willing to share water |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Table # Water 14: Plan for protective irrigation Farmer wise in each patch (For those who require only)

| Sl No | Name of the Farmer | Area (Acr) | Crops | Number of irrigations required | Nearest possible Water resource | Method/ means of protective irrigation # | Water saving device $ | Equipment required (Type and Number) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

# 1-Diesel pump, 2-Water tanker, 3-pipe line grid				$ 1- rain gun, 2-sprinkler 3- pipe

Every LMU: Explain more details about the water sharing plan proposed (Min 1 page)

Table # Crop systems 15: Mapping existing cropping patterns

| Sl No | Time Period | Season | Main Crop |  |  |  |  |  | Inter crop (s) |  |  |  |  |  | Boarder crop (s) |  |  |  |  |  | Vulnerability to Drought $ | Crop Loss % due to drought |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Name | No of farmer | Area (Acr) | Seed Type@ | Source of seed | Bye products # | Name | No of farmer | Area (Acr) | Seed Type@ | Source of seed | Bye products # | Name | No of farmer | Area (Acr) | Seed Type@ | Source of seed | Bye products # |  |  |
| 1 | Present Practice | Kharif |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Rabi |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Last 10-20 years | Kharif |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Rabi |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Before 20 years | Kharif |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Rabi |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

@ Seed Type: Local/ Improved			# Bye Products: Fodder/ Husk/ Bran		$ (Severe/ Medium/ Low)

- Reasons for shifting crops (if any)

- Explain the constraints in accessing seed

- Explain the constraints in preserving seed:

- Explain about seed quality and germination

Table # Crop Systems 16: Crop Calendar in rainfed areas

Mention the time period: From date - To date.

| Crop Name | Season | Land Preparation | Sowing | 1st Weeding | 2nd weeding | 3rd weeding | Inter cultivation | Harvesting |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

Table # Crop Systems 17: Strategic Plan for Crop Systems and Seed

| LMU Name |  |
| --- | --- |
| Major issues in present crops and seed |  |
| List of past good practices |  |
| Constraints in following good practices |  |
| Which drought resistant crops you want to grow? |  |
| Which fodder crops you want to grow |  |
| Which food crops you want to grow (Name the crops) |  |
| If you want to grow mixed/ Inter crops, what are they? |  |
| How many farmers want to do “Seed Production”? Which crops? |  |
| What are the Top 3 constraints you want to ease |  |

Table # Crop Systems 18: Seed Production

| Sl No | Crop | Variety | Season | Name of the farmer | Area (Acr) | Source of water |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |

Note: Assured irrigation facility is a prerequisite and the farmer should be willing to provide seed to other farmers as decided in the programme.

Name of the LMU:

Table # ZBNF 19: Mapping Pest problems and management practices

| Crop | Timeline | Seed Storage | After sowing | Seedling | Vegetative Growth | Flowering | Fruit formation | Maturity | Harvesting |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Issues |  |  |  |  |  |  |  |  |
|  | Present practices |  |  |  |  |  |  |  |  |
|  | Practices 10 years back |  |  |  |  |  |  |  |  |
|  | Practices 20 years back |  |  |  |  |  |  |  |  |

Table # ZBNF 20: Mapping Disease Problems and Management practices

| Crop | Timeline | Seed Storage | After sowing | Seedling | Vegetative Growth | Flowering | Fruit formation | Maturity | Harvesting |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Issues |  |  |  |  |  |  |  |  |
|  | Present practices |  |  |  |  |  |  |  |  |
|  | Practices 10 years back |  |  |  |  |  |  |  |  |
|  | Practices 20 years back |  |  |  |  |  |  |  |  |

Table # ZBNF 21: Proposed ZBNF practices in Pests, Diseases and Soil Fertility

| Crop | Particulars | Seed Storage | After sowing | Seedling | Vegetative Growth | Flowering | Fruit formation | Maturity | Harvesting |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Practice |  |  |  |  |  |  |  |  |
|  | Cost |  |  |  |  |  |  |  |  |

Table # CHC 22: Mapping the availability of Farm equipment

| Sl No | Operation | Equipment | Number available (own) | Number available (Rent) | Labour friendly (yes/No) | Needed? |
| --- | --- | --- | --- | --- | --- | --- |

Table # CHC 23: Planning for CHC

| Sl No | Operation | Equipment | Number | Importance (high, Medium, Low) | Urgency (high, Medium, Low) |
| --- | --- | --- | --- | --- | --- |

Individual Farmer Format

District				Mandal			Panchayat		Habitation

LMU Name

Farmer:				Father/Husband:			Caste

Job card			Aadhar					Mobile:

- Land details

|  | Under Tank | Under Canal | Under Open Well |  | Under Bore well |  | Rainfed |  | Fallow |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Total Land | Total Land | This LMU | Total Land | This LMU | Total Land | This LMU | Total Land | This LMU | Total Land |
| Survey No |  |  |  |  |  |  |  |  |  |  |
| Extent (Acr) |  |  |  |  |  |  |  |  |  |  |

- Existing livestock

| Cows | Bullocks | Buffalos | Sheep | Goat | Poultry |
| --- | --- | --- | --- | --- | --- |

| - Intervention to control soil erosion at vulnerable location |  |  |  |  |  |  |  | - Water harvesting structures |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl No | Intervention | Unit | No of units | Size |  |  | Sl No |  | Intervention | Unit | No of units | Size |
| 1 |  |  |  |  |  |  | 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |  | 2 |  |  |  |  |  |

- Soil Health Improvement

| Sl No | Intervention | Name of the unit | No of units | Remarks |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |

| - Crop Systems and Seed; ZBNF |  |  |  |  |  | - Protective irrigation |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl No | Present Crop(s) | Proposed Crop(s)@ | Area (Acr) | ZBNF Area (acr) |  | Sl No | Best Option $ | Extent (Acr) |
| 1 |  |  |  |  |  | 1 |  |  |
| 2 |  |  |  |  |  | 2 |  |  |

@ write all crops of that land together			$ Lined Farm Pond, Mobile tanker, Borewell N/w

- Irrigation Sources

| Sl No | Open Well/ Bore well | Year of digging | Total depth (ft) | Pipes (ft) | Motor (HP) | Discharge (Inch) | Own Extent (Acr) | Sharing Extent (Acr) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |

Signature of Farmer						Signature of Surveyor

Sequence of Activities while Planning

1st : PRA Resource Map 100 ha identified.

2nd	: LMU classification

3rd: Transact Walk

4th:	 Google Maps : Land ,farmer, LMU mapping

5th:	 Soil, Water, Crop, Seed, ZBNF, farm equipments plan

6th : Individual Plans

| 100 Hectares Consolidation Plan |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Theme | Type of Intervention | Units | No of Units | Unit Cost | Total Cost |
| Intervention to Control Soil Erosion | Stone Gully Plug (RMT) |  |  |  |  |
|  | Bunding(RMT) |  |  |  |  |
|  | Stone Bunding (RMT) |  |  |  |  |
|  | Vegetative Checks (nos) |  |  |  |  |
|  | To Be added |  |  |  |  |
| Water Harvesting Structures | Farm Ponds (size 10*10 , unit : nos) |  |  |  |  |
|  | To be Added |  |  |  |  |
| Soil Health Improvement | Compost Pit at farm (nos) |  |  |  |  |
|  | Compost Pit at cattle shed(nos) |  |  |  |  |
|  | Bund Plantation at field (nos) |  |  |  |  |
|  | Bund Plantation at compost pit (nos) |  |  |  |  |
|  | Sheep Penning (acres) |  |  |  |  |
|  | To be added |  |  |  |  |
| Proposed Crop Systems | GroundNut K6 (acres) |  |  |  |  |
|  | GroundNut Spread Variety (acres) |  |  |  |  |
|  | Bajra (acres) |  |  |  |  |
|  | Foxtail Millet(acres) |  |  |  |  |
|  | Castor(acres) |  |  |  |  |
|  | Red Gram(acres) |  |  |  |  |
|  | To be Added |  |  |  |  |
|  | Total ZBNF Area Proposed |  |  |  |  |
| Protective Irrigation | Mobile Tanker (acres) |  |  |  |  |
|  | Borewell (acres) |  |  |  |  |
|  | Lining of existing farm ponds (nos) |  |  |  |  |
|  | Farm Ponds with lining (size 10*10 , unit : nos) |  |  |  |  |
|  | AquaSeeder (acres) |  |  |  |  |

Proposal Format

- Submission Letter to SPMU through DPMU

- Title, Details of the Village, Mandal, GP, District, FA, LFA, Submitted To:, Date

- Table of Contents page wise

- GP& FPO Resolution signed by GP members & FPO members

- Village Profile /Background (History, demographics, GPS location, livestock, crops, CIG groups) short description

- PRA Resource Map /Base Google Maps/Cadastral Map, Topo Sheets

- Short Description of Situation Analysis of all 5 themes

- Theme wise & LMU wise Annexure (Formats filled)

- Farmer wise consolidation

- 100 hectare area plan and budget (Activity wise)

- Photos

AP Drought Mitigation Project

Guidelines for NRM Works in “Learning Site”

“పునాది క్షేత్రం”

The first workshop (from 9th to 12th January, 2018 at AF Ecology Center, Anantapuramu) with the NRM and Agriculture team  members of LFAs and FAs (of 4 LFAs) and DPMU resulted in a detailed planning exercise for the Learning Site.

The 2nd workshop with the LFAs, DPMU and SPMU teams based on the field plans prepared was organised on 22nd Feb, 2018 at Anantapuramu. The following guidelines emerged from the discussions collectively. These were facilitated by the LTA.

The project will not spend on

- Activities where mainstream programs budgets are already available

- Activities in saturation mode;

APDMP grants will be spent only to demonstrate successful interventions, pilot innovations and to mobilise demand. As convergence is one of the major objectives and success indicator of the project, funds for scaling up & for saturation of activities has to be mobilised from other mainstream programmes such as MGNREGS and also from various other departments which are working for the same objectives. This is generally followed as a guiding principle while LFAs plan/ recommend the plans for funding by APDMP.

What is “Learning Site” (“పునాది క్షేత్రం”)?

A 100 ha area (a sub-watershed) is to be identified by the community with support from FA. For the first year focused attempt will be made to take up comprehensive drought resilient measures in this area that includes taking up NRM works, year long farmer field schools ( a modified version), among others.

The following guidelines are evolved for the 1st round of work on the subject with 4 LFAs; these will be taken up by the DMPU for assessing the plans/ fund proposals recommended by LFA. The actual cost estimates are as per the watershed works that are in practice. This note sets the limits to which APDMP will invest.

Activities / Interventions for Demonstrations/ pilots that can be funded from APDMP grants:

- Soil Conservation Works:

  - This activity is encouraged to be mobilised from MGNREGS

  - Soil conservation works are much needed in the farms :

    - where tank silt is applied afresh and

    - fields with sever erosion.

  - If convergence efforts were not successful well before the Kharif season, APDMP may spend budgets as grant in such farms where tank silt is applied or those with severe soil erosion problem. (gully-heads).

  - The limit is set to a maximum of 20 acres to be invested from the project grants during the first year in the Learning Site. This is only applicable for first year of implementation; funds have to mobilised through convergence for rest of the period based on demand.

  - The cost norms are as same as MGNREGS

  - Cost-estimates with design has to be submitted along with proposal if this activity is proposed under APDMP grant.

- LINED FARM PONDS FOR PROTECTIVE IRRIGATION: These are taken up as a part of the planning for Protective Irrigation in the Learning Site. The plans have to provide details of the area to be protected through each of these farm ponds. Field level discussion is important to arrive at negotiated ways of farmers sharing the farm ponds (area and water). These must be for harvesting run-off water but not to store water pumped out of borewells. Must be lined in case of red-soils and necessary precautions taken to prevent seepage in case of other soils.

  - A maximum of 10 farm ponds with lining per each Learning Site to be taken up under APDMP funds.

  - These are only to be taken up in rainfed farms

  - Encourage existing farm ponds for lining; a maximum of 5 farm ponds

  - Recommended size of the farm pond is 10m x 10m x 2.5 m with 250 cum volume which can serve 4-5 acres @ 50 cum of water per irrigation for protecting rainfed crops from drought spells.

  - These 10 farm ponds’ digging can be taken up by machines

  - Upper limit of cost of each farm pond with lining with the above size is Rs.13,000 for digging and Rs. 9000 for lining for each farm pond (includes cost of cement and water). A detailed design and estimate will be shared by AF from their experience. Farmer has to contribute labor for lining.

  - If taken up from MGNREGS -the standard estimates as per MGNREGS norms will apply.

  - Standard estimate & design for farm pond with lining will be shared by  Accion Fraterna by 28th Feb’18.

  - AF will provide resource persons for demonstrating one complete farm pond lining per each LFA; the demonstrations have to be complete by April, 2018. LFA has to make all necessary arrangements including arranging for material before the resource person comes.

- Works related to Composing on farms & Residue management:

  - One compost pit per ha is recommended to start with; a pit of 4m x 3m x 0.5m = 6 cum volume. Biomass is filled up to 1 meter. This will give about 1.5 to 2.0 tons manure from each pit that can be applied in one acre. If the farmer is successfully managing it, it can be expanded to cover one pit per each acre in later years along with biomass plantation.

  - Each compost pit comprises of digging, planting (Glyricidia or other plans) around the pit to add biomass and give shade.

  - A maximum of 3 compost pits per farmer can be taken up under APDMP grant

  - Assess biomass availability before proposing Composting activity

  - The cost per pit (including one cycle of compost making) with dimensions 4m x 3m x 0.5 m  is Rs. 5,565/-. The cost includes pitting, biomass plantation and over turning; farmer has to source biomass and fill it.

  - The expected output is 1.5 to 2 tonns of Manure from each pit

  - A detailed estimation has to be submitted for approval under APDMP grant

- Tank Silt Application for soil improvement:

  - Proposed only for farms with poor soils; need to be taken up in convergence with MGNREGS. APDMP funds used only if all attempts to mobilise MGNREGS at district level did not succeed before May, 2018.

  - Maximum silt application with APDMP budgets to be taken up is for 50 acres in the learning site.

  - The cost of silt application per acre is up to Rs.6,500/- (Rs. 2,000/- for silt excavation with machine & filling tractors + Rs. 4,500/- after 50% farmer contribution for transportation and application in field).

  - Assess the quality of silt before applying; It is observed that applying farmyard manure/ compost along with silt is better for quick results.

- Deep Ploughing: Particularly in farm plots which have been uncultivated for some time, deep ploughing is useful to bring the lands back into cultivation. A provision upto 10 acres can be used for deep ploughing in the “learning site”.

- Provision of Supervision costs: For supervision of works implementation, a Community Resource Person (CRP) may be identified. On the job training may be provided for the identified CRP. One of the basic responsibilities of CRP is ensuring quality of works and required book / records keeping. For each learning site, up to  90 days of CRP cost @ Rs. 400 per day; if required.

After planning for NRM works, the FAs need to evolve the yearlong action plans for comprehensive drought resilience measures. This will be arrived at later.

See the Summary Table on Budget provision for NRM works in “Learning Site”. These are budget provisions to be used only in case convergence efforts did not succeed. The provisions are upper limits and the actual consolidated proposals from LFAs need to be based on actual areas on ground, design and estimates. The proposals must be accompanied by a map showing the details of various works. Data entry in the mobile application also need to be complete.

Summary of Budget Provision for NRM Works in “Learning Site”:

| Provision for Works Under APDMP in the “Learning Site” | Unit | Unit Cost | Farmer Contribution (%) | Farmer Contribution Amount (Rs.) | Amount after deducting Farmers Contribution (Rs.) | Number of units | Total Amount (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Soil conservation/ Farm Bunding | Acre | ₹7,700 | 0 | ₹0 | ₹7,700 | 20 | ₹1,54,000 |
| Farm ponds |  |  |  |  |  |  |  |
| Farm ponds with Lining | Number | ₹21,000 | Labor for lining | ₹0 | ₹21,000 | 10 | ₹2,10,000 |
| Lining of existing Farm ponds | Number | ₹9,000 | Labor for lining | ₹0 | ₹9,000 | 5 | ₹45,000 |
| Composting |  |  |  |  |  |  |  |
| Compost pits + Biomass plants + compost preparation (1 cycle per year) | Number | ₹5,565 | 0 | ₹0 | ₹5,565 | 25 | ₹1,39,122 |
| Tank silt application |  |  |  |  |  |  |  |
| Silt excavation & filling tractors | Acre | ₹2,000 | 0 | ₹0 | ₹2,000 | 50 | ₹1,00,000 |
| Transportation & field application | Acre | ₹9,000 | 50 | ₹4,500 | ₹4,500 | 50 | ₹2,25,000 |
| Deep ploughing | Acre | ₹1,600 | 0 | ₹0 | ₹1,600 | 10 | ₹16,000 |
| Sub total |  |  |  |  |  |  | ₹9,45,372 |
| Provision for Field supervision | CRP Day | ₹400 |  |  |  | 90 | ₹36,000 |
| Total |  |  |  |  |  |  | ₹9,81,372 |

Note: these are maximum budget provisions only; actual budgets must be arrived at based on field data.

** **

Columns in the table will be expanded. This table will be used in subsequent exercises too..

Farm Yard Manure, Compost, Vermi Compost