AP DROUGHT MITIGATION PROJECT

- This document details the planning framework for preparing “Learning-Site Plans” at each cluster.

- This guidelines note combines all separate notes circulated so far for different exercise into one single document for the reference of LFAs and DPMU teams. It was evolved after reviewing of various draft plans and consultations including field testing.

“Learning Site” Participatory Plan for Climate Resilient Agriculture

SPMU, APDMP

Department of Agriculture, Guntur

Lead Technical Agency

C O N T E N T S

Background	4

Participatory Planning Module for the Learning-Site	5

	EXPECTED OUTPUTS	5

	PLANNING TEAMS	5

	PLAN THEMES:	5

Preparatory Exercise: Identification of the ‘Learning-Site’	5

	OVERVIEW OF THE PLANNING EXERCISES:	6

o	PLANNING EXERCISE 1:  PREPARATION OF THE BASE MAP	6

o	PLANNING EXERCISE 2:  DEMARCATING LAND MANAGEMENT UNITS (LMU)	7

o	PLANNING EXERCISE 3:  SOIL HEALTH IMPROVEMENT PLANS	9

o	PLANNING EXERCISE 4:  PLANNING FOR WATER AND PROTECTIVE IRRIGATION	19

o	PLANNING EXERCISE 5:  PLANNING FOR CROP SYSTEM AND SEEDS	25

o	PLANNING EXERCISE 6:  PLANNING FOR ZBNF PRACTICES	31

o	PLANNING EXERCISE 7:  PLAN FOR IMPLEMENTS AND FARM MACHINERY FOR TIMELY OPERATIONS	33

LIST OF TABLES

Table 1 : 	Farmers list in 'Learning Site"	7

Table 2:   	LMU Characteristics	8

Table 3:	Details of the previous soil testing records in the learning site	9

Table 4:	 Manure practices in each LMU	10

Table 5: 	Farmer wise manure plans in the learning site	10

Table 6:	Tank Silt Application	11

Table 7: 	Detailed plan of tank silt application	11

Table 8: 	Funding support for tank silt application	12

Table 9:	Detailed Plan	13

Table 10:	Crop Residues Management	13

Table 11:	Biomass Plantation on Bunds	15

Table 12:	 Cost of Planting Material	15

Table 13:	Amelioration of Problem Soils	17

Table 14:	Compilation of information on Surface water bodies:	21

Table 15: 	Compilation of information on Groundwater resources:	22

Table 16: 	Summary of Protective Irrigation Arrangements	24

Table 17: 	Summary of cost of new water harvesting structures	25

Table 18: 	Plan for the Protective irrigation equipment	25

Table 19:	Mapping Crops Calendar	26

Table 20:	An Example of Crop Calendar:	27

Table 21:	Mapping the crop system	28

Table 22:	Tracking changes in the crop systems (using the same Table as above):	28

Table 23:	Need for specific crop pattern changes for drought resilience	29

Table 24:	Seed Requirements	30

Table 25:	Prepare farmer-wise Table with the following details:	30

Table 26:	Input usage, Pest and disease Control & related expenses:	31

Table 27:	Summary picture of the availability of implements/	34

Table 28:	CHC Plan	35

Table 29:	Availability of draught power.	35

Table 30:	Inventory of implements/ machines with farmers	35

Table 31:	Detailed Table of Action Plan for the Learning Site:	39

Table 32:	Detailed Plot data for the learning site: (this can be generated from the FGD with Google Earth Map).	39

Table 33:	Farmer Database for the learning site: (this can be generated from FGD)	40

Table 34:	LMU Details: (This will be obtained in the initial exercises on classification of LMUs.	40

Table 35:	Summary of Budget Provision for NRM Works in “Learning Site”:	45

# Background

Andhra Pradesh Drought Mitigation Project APDMP is operational in 105 clusters  in 5 districts of Andhra Pradesh. A ‘Learning Site’, a sub-watershed of around 100 ha area in each cluster of 3 Gram Panchayats is taken up for season long participatory planning and action to evolve location specific climate resilient agriculture practices.

The expectations from the year long participatory planning and action in the learning site are as follows:

- Baseline situation of the learning site; for evaluation of results later

- Evolving a set of comprehensive package of location specific measures for ‘climate resilience and growth’

- Evidence on ground experienced and

- Demand from rest of the farmers on such practices

- At least 10 practicing resource farmers with understanding and capacity to support expansion

- Expansion of membership in the Farmer Producer Organisation

- Demand for local inputs (bio-inputs/ botanicals) through the CLiCs

The “Learning-Site” Planning and Action in the first year of project complements other initiatives on livestock, agriculture, groundwater, evolving institutional and service delivery mechanisms. Generation of  demand from other farmers in the cluster in the process will be met through other project mechanisms.

There are two major parts of the year long participatory planning & action; viz.,

- Participatory climate resilience and growth plans for the ‘learning-site’

- A year-long ‘participatory learning & action’ (PLA) module where farmers’ groups in the learning site meet every fortnight to experiment, observe, learn, review, analyse, plan and act.

This note details the participatory planning process for climate resilience and growth in agriculture in the ‘learning-site’.

The curriculum for the PLA module will be shared in due course.

# Participatory Planning Module for the Learning-Site

## EXPECTED OUTPUTS

This note guides the planning teams in getting the following outputs:

- Identifying the ‘learning site’

- Preparing a comprehensive plan for action with detailed situation analysis

- Arriving at budgets and proposal for the Learning Site.

- Indicators for evaluating the Plans

## PLANNING TEAMS

- The LFA team is responsible for guiding and training the FA teams using this module and support them on field.

- The key responsibility of planning on ground is with the NRM and agriculture team members of the FAs; while the livestock facilitator involves partly.

- It is important to constitute a small planning team (with 50% women) from out of the farmers in the learning-site who become part of the planning team.

## PLAN THEMES:

The Participatory Planning Exercise focuses on five themes:

- Soil health improvement

- Protective irrigation plans including soil moisture conservation

- Cropping systems diversification and seed security

- Agronomic practices and Zero Budget Natural Farming (ZBNF)

- Increasing access to agriculture implements and farm machinery for timely operations

# Preparatory Exercise: Identification of the ‘Learning-Site’

Before the planning exercise, the “learning site” needs to be identified. This is done using a Resource Mapping exercise in a central location in the village; this is a standard PRA tool that the teams are familiar with.

The criteria for choosing the ‘learning-site’ are:

- Rainfed crops in >75% of the crop area

- A contiguous patch of 250 acres land

- SC&ST, Small and marginal farmers

- Highly vulnerable to droughts

- Preferably a sub-watershed

The team is to narrow down to specific geographical location based on resource mapping exercise followed by a field transect and interaction with farmers. An ad-hoc planning committee if constituted at the 3 GP levels, may take a lead in generating consensus to initiate APDMP field programs in the ‘learning site’.

## OVERVIEW OF THE PLANNING EXERCISES:

The planning process goes in 3 stages:

Preparing the base maps and data base for planning is a starting point. The process also arrives at typologies of the situation in terms of Land Management Units.

Stage - 1 : 	Situation analysis: identifying constraints/ opportunities / issues

Stage - 2 : 	Evolving strategic actions to address issues

Stage - 3 : 	Developing detailed action plans (plot wise & farmer wise) for the strategic actions.

The 3 stage exercises will be taken up for the five Planning Themes detailed above. A compilation of these plans in Stage 3 (with background of stage 1 and 2) gives the final plan with budgets.

### PLANNING EXERCISE 1: 	PREPARATION OF THE BASE MAP

Steps

- Google Earth (Pro version) Map of the Learning Site: Take latitude and longitude during the first visits on the broad boundaries.

Take print out of the maximum view possible.

    - Open Google Earth Pro version (available free).

    - Spot the location in Google Earth using lat/ long.

    - Enlarge the view to the desired size

    - Save the area: Go to File >> Save >> save image as >>Select Maximum from Resolution (Next to search) >> Click Save image >> Save as JPEG

    - Take the colour print out on A0 size sheet – preferably on paper. Best is to fix it on a binders’ cloth so that it can last for longer time.

    - At this scale individual plots will be clearly visible.

  - Simultaneously, take the cadastral maps also along with.

  - Mapping the Plots:

  - Using the larger size google earth map as a base, start at one known point/landmark, identify the plot and the farmer. With this as reference mark plots of adjoining farmers.

  - For each plot also identify the survey numbers cross checking with cadastral map. Continue the exercise till all plots are mapped/ noted.

  - Give numbers to each plot and simultaneously enter them in a Table.Prepare the details of farmers in following Table. Only the Plot serial number, name of the farmer, survey number will be entered at this stage. The other details can be entered later.

Table 1 : Farmers list in 'Learning Site"

| Sl No | Name of the Farmer | Father/ Husband Name | Aadhaar | Area (Acres) | Survey Number | LMU |
| --- | --- | --- | --- | --- | --- | --- |

  - Most part of the drainage lines are visible on the Google Earth Map. However, identify and mark the drainage lines on the map triangulating with the farmers.

  - The process of identification of Land Management Unit (LMU) is explained in next session.

Getting the total area and fixing the boundaries of the Learning Site should be explained.

### PLANNING EXERCISE 2: 	DEMARCATING LAND MANAGEMENT UNITS (LMU)

Much of the crop systems and related problems emanate from the land types and their patterns. Land types of similar nature – with similar constraints or opportunities can be grouped into a particular typology to make the planning easier. LMU is used for this purpose.

The plots that are similar in land type, soil characteristics, crops, irrigation status and management requirements (they usually have a local name) are marked as an LMU. The actions required on these LMUs will be mostly similar. The local land classification / names usually provide a good lead.

Steps

- LMU Identification

- Once you have the base map ask the key question: “What are the ways to classify your lands in this area?”

- Start listing the local names on flash cards; one on each of them.

- Then ask: “Can any of them be grouped together – as the difference is not substantive”?

- Group these cards that have high similarities. Finally, we end up with a local classification of land types. Finally arrive at a maximum of 4 to 5 LMUs.

- For each LMU identified then get the details as per Table 2.

- Ask the farmers to show these LMUs in the map and note them with specific colours. Simultaneously enter the LMU type in Table 1.

- LMU characteristics mapping

Capture the details in the below table

Table 2:   LMU Characteristics

| S.No. | Parameter | Values (given here are as example) | LMU 1 | LMU 2 | LMU 3 | LMU 4 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Approximate Area | Acres |  |  |  |  |
| 2 | Soil Texture | (Clayey, loam, silt and sandy) |  |  |  |  |
| 3 | Soil Color | (Red, Black, etc.) |  |  |  |  |
| 4 | Soil Depth | (deep: >60cm, medium: 11-60 cm, shallow: <=10cm) |  |  |  |  |
| 5 | Slope | (high, med, low) |  |  |  |  |
| 6 | Water holding capacity | (high, medium, low) |  |  |  |  |
| 7 | Specific Problems |  |  |  |  |  |
| 8 | Fertility status | (good, average, poor) |  |  |  |  |
| 9 | Crop systems that are generally taken up |  |  |  |  |  |

>> At the end of this exercise the outputs we have are:

- Google Earth map with plots identified, LMU marked on each plot

- Table with details of farmers for each of the plots (Table 1)

- Detailed characterisation of what farmers identified as LMUs (Table 2).

- Converting the exercises into digital data:

  - The Tables can be entered into excel/ data bases.

  - Digitise plots on the GE Map using QGIS or other GIS software giving each plot a unique polygon number. (A QGIS training will be organised by the LTA for this purpose for all LFA/FAs).

  - Link the database with the map polygons.

  - Digitise and geo-reference the cadastral map and get this overlaid onto the GE Map (Optional).

### PLANNING EXERCISE 3: 	SOIL HEALTH IMPROVEMENT PLANS

Soil is key to production and resilience. In rainfed situation, amount of rainfall harvested and retained in soil profile contributes directly to drought resilience and productivity. Reduced runoff and higher infiltration helps in better rainfall harvest. Organic matter and life in soil (soil biology) are crucial for a healthy soil.

Output of the planning exercises to improve soil health results in

- Understanding different soils and their constraints

- Developing plans for increasing organic matter into soils/ soil profile amelioration

- Addressing the issues of problem soils

- Soil testing and understanding soil test results

Steps

- Start with the Base Map, Table 1 and Table 2  in which LMUs are delineated with details. All the discussions and plans should be done for each LMU separately.

- Explore on Soil Testing

  - Are there any soil test results already available for the area? If yes, gather the Soil Test card results and compile them; map them with respect to the survey numbers (and also enter into Table 1) with additional columns.

  - Summarise major observations from soil test results? Discussion & report; with respect to each LMU.

  - What is the status of organic carbon?

  - What is the status of macro nutrients?

  - What is the Status of micro nutrients?

  - What are the recommendations of the soil tests? What should be the action points to be included in the plan?

Table 3:	Details of the previous soil testing records in the learning site

| S.No. | Soil Testing Farmer Name | Plot No in GE Map | Survey No. | Date of Testing | Organic carbon | N, P, K | Micro Nutrients | Key recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

- Identify Present Practices for each LMU through Focused Group Discussion on the action areas related to this theme.

  - Application of Manure

- Situation Analysis of Manure-Practices

  - What are the practices traditional / recent of manuring the plots? And what are their trends and current status. Find out this with respect to each LMU.

  - What are the practices now of manure preparation/ application:

    - At household level

    - At cattle/ animal sheds

    - Purchase

  - Are there local practices of selling manure; if yes, price of it.

  - What types of manures are applied in each LMU? What is the quantity and frequency? How it varies with respect to each LMU?In the Table below.

Table 4:	 Manure practices in each LMU

| S.No. | LMU Type | Practices followed | Manures applied | Quantity (approx. tons / acre) | Frequency (once in how many years) | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |

- Strategic Plan

  - What activities need to be taken up in the area?

    - In situ composting

    - Composting at homesteads or cattle/ livestock sheds

    - Others?

- Detailed Plan

Table 5: 	Farmer wise manure plans in the learning site

| S.No. | Farmer Name | Plot no. in Learning Site | Total Area (acres) | Quantity presently applied (tons) | Planned manure application (tons) | Source of Manure (own, new, purchase,??) |
| --- | --- | --- | --- | --- | --- | --- |

  - Tank Silt Application

- Present Practice

  - Was there a practice of Tank Silt application? Which LMUs it is used most?

  - When was it last done? And by how many farmers; how many acres?

  - What are the sources for tank silt, if needed;

Table 6:	Tank Silt Application

| Sl. No. | Source Name | Distance (kms) | Quantity available (sufficient / moderate / very less) | Quality (Good, Okay) |
| --- | --- | --- | --- | --- |

  - What would be the benefits of tank silt application (how much productivity increase observed?)

- Strategic Plan (this can be done by a small sub-group or committee)

  - Source of tank silt (assure quality)& distance (mark on google earth map)

  - What is the cost for digging and filling tractors (local practice)

  - Transport of silt:

    - Transport distance

    - Costs involved.

  - What does the committee suggest?

    - What costs should the farmer meet?

    - Any provisions in MGNREGS or others?

    - What costs do the project meet?

- Detailed Plan following the strategic plan arrived at:

Table 7: 	Detailed plan of tank silt application

| Sl No | Farmer Name | Area (ac) | No. of trips/ ac | Total Trips | Source | Distance (km) | Cost/trip | Farmers’ Responsibilities |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

Table 8: 	Funding support for tank silt application

| S.no. | Operation | Source of Fund (tick) |  |  |  | Units | Rate (rs/unit) | Quantity | Amount (Rs.lakhs) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Farmers | MGNREGS | APDMP | Others |  |  |  |  |
|  | Digging & Filling |  |  |  |  |  |  |  |  |
|  | Transport |  |  |  |  |  |  |  |  |
|  | Spreading |  |  |  |  |  |  |  |  |
|  | Soil incorporation |  |  |  |  |  |  |  |  |

[Change the above Table as necessary]

Note: Discuss the following

- Cost of silt application per acre as estimated from any local practice

- Impact of tank silt application in terms of increase in income (main product and bye-products)

- Explore if farmers take loan and repay? Discuss repayment conditions.

- Arrive at operational modalities

- What responsibilities farmers (sub-groups) would take up?

- What is the method of contribution?

Most importantly, how do farmers ensure that silt is applied to “Learning Site” only?

  - Soil Conservation

Soil conservation is the first step to improve soil health. Manure and silt application are effective only in the plots where soil conservation is taken up.

The soil conservation works are integrated into MGNREGS. These plans need to be necessarily integrated with MGNREGS.

Only very critical investments such as conserving active erosion heads (areas) absolutely necessary may be taken up in APDMP, in a limited way.

More important is to shift to biomass based soil conservation measures integrating with crop/ farming systems than mechanical structures.

- Situation Analysis: Key Questions:

  - Were soil conservation works taken up in the “learning site” before? Under which scheme and what’s their status at present? (are they maintained?)

  - Map the active erosion locations in the learning site where it is very important to have conservation works to prevent larger erosion.

  - Any plans related to conservation works in streams or on lands must necessarily come from convergence; given that MGNREGS focuses on these, these be given low priority in APDMP.

- Strategic Plan

  - Given the past experiences, what are the sustainable soil conservation measures?

  - What should the farmers practice? And, what are their responsibilities?

  - How to move towards biomass based soil conservation?

- Detailed Plan :

As mentioned, the plan only needs be of the most critical works to be taken up.

Table 9:	Detailed Plan

| Sl No | Plot No. | Farmer Name | Status of erosion | Activity to be taken up | Units | Rate | Qty | Amount | Source of budget | Farmers’ Responsibilities |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

  - Crop Residues Management

- Present Practices

  - What are the present practices with crop-residues? What are the residues in each crop?

Table 10:	Crop Residues Management

| Sl No | LMU | Crops | Approx Area in the learning site | Present Usage of Residue | Usage of residue in the past | Approx Residue quantity Qt / ac | Rate (if any) Rs/ unit | What is the proposed use? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

- Strategic Action Plan

  - What are the strategies to stop residue burning, if in practice?

  - Methods of mixing crop residues into soils

  - Are rotovators used to incorporate residues into soils? If not, how to promote the practice?

  - How to convert crop residues into useful compost?

    - What are the costs involved in crop burning? (collection of residues, managing burning etc.)

    - Can there be options of composting within the costs?

    - Explore the options with farmers and arrive at plans.

- Detailed Plan:

  - Plans for crop residue management.

  - Develop detailed plans and costing (including farmers’ share) converting crop residues into useful products (fodder/ compost).

  - Explain if the options/ plans are arrived at will continue without project support later on? And, how?

  - Work out detailed plan with budgets as a special program.

  - Biomass Plantation on Bunds

Adequate biomass incorporation into soils is crucial for its health improvement. Experience suggests that in situ biomass generation and incorporation into soils (both from crop systems and plantation) is essential for rainfed lands. Bund plantation, if planned well, also helps in protection against winds.

- Situation Analysis

  - Explore situation for each LMU (remember, if there are any commons in the learning site, they also form one or more LMUs)

  - What is the density of trees in the area in each LMU – approximately how many trees /acre? And, what are those trees?

  - Were there trees earlier? What happened over time?

  - Is there any practice of plantation on bunds or in the  commons within the learning site?

  - Any biomass used to be collected from commons for FYM?

  - Are there any other practices for adding biomass to the soils?

  - What is the grazing pressure in the area (heavy / mild )?

  - Are there fruit plants/ horticulture in the learning site? What was the experience?

- Strategic Action Plan

  - LMU wise options for biomass plantation?

    - Which species, and where to be planted (on bunds, commons.. )

    - Where to get the plants? What’s the sowing method (seed dibbling/ vegetative propagation (stem cuttings) / plantation)? Source of seedlings?

  - What are the nurseries available nearby? Which species are available?

  - Should biomass nursery be taken up in the cluster?

  - What are the protection measures?

Table 11:	Biomass Plantation on Bunds

| Sl No | LMU | Biomass options | Species to be taken up | Seedling or seed dibbling | Where to be planted or dibbled? | Purpose / usage of the plantation | Sources of seed/ seedling? | Other information |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

- Detailed plan:

  - Arrive at plantation (preferably in clusters of contiguous plots) area. (farmer name / plot no. / no. of plants / species). Based on such farmer wise plans arrive at the following Table.

Table 12:	 Cost of Planting Material

| Sl No | Species to be taken up | Seedling or seed dibbling | No. of plants | Sources of seed/ seedling? | Cost of seed/ seedling | Dibbling / planting cost |
| --- | --- | --- | --- | --- | --- | --- |
| A | By seed dibbling |  |  |  |  |  |
| B | By Plantation |  |  |  |  |  |

- Alternatively (to 1 above) if the choice is to raise biomass nursery:

  - What is the plan for nursery? Number of plants, species composition, sale price of plants (with age of seed ling etc.)

  - It must be promoted as an individual or partnership enterprise from whom the project will purchase seedlings.

  - Provide a detailed cost estimate and project

- Costs of watering

  - What are the plans for watering – for survival?

  - What are the costs associated with it?

  - Who bears the costs?

- Costs of protection

  - What are the protection mechanisms for the planted area?

  - Who is responsible for what?

  - What are the costs associated with it?

The biomass plantations are to be taken up only when their protection and survival is assured. This will be an evaluation criteria to be used by DPMU before recommending the plans.

Since biomass plantations are highly prone to failure, there must be higher contribution from farmers in taking up these to ensure their stake.

  - Sheep / livestock penning or other options

Explore if any such practices were in place? If yes, can they be further promoted? If not, can those be introduced?

  - Amelioration of Problem Soils (saline/ sodic / water logging etc.)

- Situation Analysis:

  - Are there any problem soils identified / mapped; these needs to be considered as separate LMUs.

  - Provide each LMU wise problems

  - Were there any previous soil test results available for these soils? If yes, details.

  - Are there any successful examples within the learning site or nearby on amelioration of the problem soils?’

  - If there were no prior soil test results, collect the samples and give them for soil testing.

- Strategic Action Plan?

  - What are the strategic options for soil amelioration for each problem/ LMU?

  - From any local examples, arrive at:

    - What are the benefits of treating the problem (additional productivity, change of crops etc.)

    - What are the costs involved?

    - Is it worth attempting soil problem amelioration?

  - What are the activities involved?

  - For each of the activity – arrive at what the farmer will do and what the project will do?

Table 13:	Amelioration of Problem Soils

| Sl No | LMU Name | Problem Identified | Area (acres) | Treatment method | Activities Involved | Approx Costs involved | Cost sharing |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | By farmer | By project |

- Detailed Plan of Action:

  - Based on the strategic plans, develop individual farmer based plans and present their consolidated budgets.

  - Explain the cost-benefit ratios.

  - Can this be taken up on a loan basis?

SOIL HEALTH ENHANCEMENT OPTIONS:

To help in planning the following is a summary of options for enhancing soil health.  Soil health improvement mainly depends on soil organic matter/ regular addition of organic matter. Addition of 10 tons per ha is the general recommendation. Farmers apply FYM in rotation for different plots. Considering this, even if we can achieve 2 tons of organic matter applied every year per acre would be quite an achievement. This has to be sustained over years to make a credible impact.

In addition to addition of organic matter, keeping the soil covered with a crop for as long a period as possible will help in retaining moisture and prevent desiccation of organic matter. In rainfed situations, organic matter is most essential for harvesting rainfall in to soil profile and retaining it for longer periods.

Of all the measures, in situ measure are the most cost effective and easier.

The following are the options for soil health improvement:

- Crop Systems:  These need to be planned in a way that at least 1/3rd of the biomass need to be recycled into the soil.

    - Substantial addition comes with green manuring. But it is difficult in rainfed situations, as crops need to be sown with first rains. Green manure intercrops and incorporation during crop season is an option.

    - Crop rotations and intercrops with pulses. Crops like redgram adds lot of leaf litter.

    - Intercrops of legumes

    - Navadhanya system by far, is the best option for intense biomass addition to soils. The system adds biomass and keeps the soil covered for many months.

    - Mixing tree crops

    - Avoiding crop residue burning, and promoting composting/ soil incorporation of biomass using rotovators are good strategies.

    - Use of bio-decomposers may help in faster composting.

- Bund plantation and incorporation of green leaf manure; species like Gliricidia, pongamia are extensively used for this purpose.

- Tree based crop systems are also practiced.

- Sheep penning is a traditional practice.

- FYM : traditionally farmers used collect biomass, spread it on the cattle sheds and add the litter to the FYP. This has multiple advantages. One can target the present availability of FYP at the homestead and aims at doubling or trebling the quantity by adding more biomass to dung.

- Composting: This happens at the homestead or at cattle shed or can also be at the farm. Most important is the availability of biomass, water and labor. There are different composting methods. One that is most appropriate for biomass constrained rainfed situation is the aerobic composting. Vermicomposting is an option but water and labor intensive.

- Increasing the quantity of FYM: The strategy is to add more biomass so that the household FYM quantity gets 2 to 3 times.

- Planting glyricidia around the compost pit provides useful fresh leaf biomass for composting

- Mulching and/ or conservation agriculture without chemicals: covering the soil with biomass and/ or no-till agriculture are also an option.

- Integration of livestock into crop/ farming systems : makes rich animal dung available for addition to soil.

- There are several other ways and exploring them locally may provide valuable insights for planning.

- ZBNF practices also are mix of several strategies above along with application of bio-manures for improving soil biology and emphasises on in situ measures. Multi-tier cropping like Navadhanya improves soils substantially with addition of biomass and also as it covers the soil for longer periods.

The above are indicative and not exhaustive.  Exploring local traditions provides much better tested options.

### PLANNING EXERCISE 4: 	PLANNING FOR WATER AND PROTECTIVE IRRIGATION

Purpose: Plan for protecting crops against drought spells at sowing and during different stages of crop growth

Specific Objective:

  - Identifying crops cultivated in each LMU and understanding their drought vulnerability

  - Mapping and assessing water resources in the “learning site” and identify areas that are highly vulnerable to drought spells.

  - Planning for securing crops in the vulnerable areas against drought spells:

    - At sowing stage

    - At crop growth stages

  - Creating necessary infrastructure (water bodies or irrigation equipment) to meet the planned requirements

Steps

- Situation Analysis:

- Mapping Water Resources in the Learning Site:

  - Use the Base (Google Earth) Map with drainage lines

  - Map water bodies on the map:

    - Drainage lines, check dams, tanks, farm ponds (lined and unlined) and other water bodies.

    - Map the bore wells and open wells

    - Number each water body (surface and groundwater)

  - For each water body (surface and groundwater) ask for the following:

    - Ownership (name of owner(s) & private or common)

    - Last month of water availability (i.e. when it dries up?).

- Mapping Irrigated Areas and Crops irrigated

    - Name of the crop and extent of area presently irrigated by each water body, both for Kharif and Rabi (also, map the plots irrigated on the map using a colour mark/ symbol).

    - Irrigation practices used in each water body: flood flow, channels, sprinklers, or drips

- When do drought spells occur? (Types of drought spells)

    - In focused group discussion, identify the months (weeks in a month) when probability of dry spells (short – 10 days; long >15 days) occur; based on farmers’ perception.

    - Map/ list the water bodies (surface and groundwater) where water is available during the most probable dry spell period.

How much water is required per each irrigation?

      - 1 acre = 4046 sq. mtr

      - 10 mm irrigation (depth) = 10/1000 = 0.01 meters

      - 10 mm irrigation in one acre = 4046 x 0.01 cubic meters = 40.46 cu.m

      - 1 cu.m = 1000 litres i.e.; 40.46 cu.m = 40460 litres of water.

      - 1 tanker is 5000 litres i.e. roughly 8 tankers.

      - A lifesaving irrigation (expecting crop will survive and catch up with next rains in about a week time) is 10 to 20 mm.

A good irrigation is 40 mm. (1.6 lakh litres of water

- Map drought vulnerable areas (LMUs)

    - Take three categories of drought vulnerability; severe, medium and low

    - Mark all the plots/ LMUs vulnerable to drought spells on the map and also list them in a Table: LMU type, Crop and Severity of drought vulnerability

- Assess the Losses due to drought spells& Opportunity of Protective irrigation: (this can be done with key 3 to 5 key farmers and shared with all)

    - Assess losses of drought spells: mild, moderate and severe – per acre and per each LMU

    - Assess scenarios of providing protective irrigation and their economic benefit (yields protected and yield enhanced)

      - One irrigation at sowing enabling timely sowing

      - One or 2 irrigations at critical stages of crop growth

    - What would be the economic benefit per each irrigation?

      - The potential economic benefit per cubic meter of water.

      - Say if the benefit is Rs.5000 per acre (one additional qt of redgram) per life saving irrigation i.e. 40 cu.m or 8 tankers of water; it is worthwhile for farmer to invest say, Rs.2000 to 3000 on each irrigation.

      - Alternately, the potential loss can also be compared.

      - The above exercise is to make a case for investing on protective irrigation.

The Information collected above should be captured in the below format

Table 14:	Compilation of information on Surface water bodies:

| Sl No |  | 1 | 2 | 3 | 4 | 5 | 6 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Name of the GWS @ |  |  |  |  |  |  |
| 2 | Location of GWS |  |  |  |  |  |  |
| 3 | Owner Name |  |  |  |  |  |  |
| 4 | Last month of water availability |  |  |  |  |  |  |
| 5 | Whether water is used for irrigation? |  |  |  |  |  |  |
| 6 | Kharif Crops irrigated |  |  |  |  |  |  |
| 7 | Kharif Area Irrigated (Ac) |  |  |  |  |  |  |
| 8 | No of Farmers in Kharif |  |  |  |  |  |  |
| 9 | Rabi Crops |  |  |  |  |  |  |
| 10 | Rabi Area (Acr) |  |  |  |  |  |  |
| 11 | No of Farmers in Rabi |  |  |  |  |  |  |
| 12 | Method of irrigation |  |  |  |  |  |  |
| 13 | Condition of structure |  |  |  |  |  |  |
| 14 | Major Issues, if any |  |  |  |  |  |  |
| 15 | How do you lift water? |  |  |  |  |  |  |
| 16 | At which stage of the crop? |  |  |  |  |  |  |
| 17 | Plan for improving structure |  |  |  |  |  |  |
| 18 | Plots that can be provided critical irrigation |  |  |  |  |  |  |

(Farm pond, Irrigation Tank, Percolation Tank, check dam)

Table 15: Compilation of information on Groundwater resources:

| Sl No | Details | 1 | 2 | 3 | 4 |
| --- | --- | --- | --- | --- | --- |
|  | Name of the WHS @ |  |  |  |  |
|  | Location of WHS (Plot No in GE Map) |  |  |  |  |
|  | Owner Name |  |  |  |  |
|  | If shared no. of partners? |  |  |  |  |
|  | Last month of water availability |  |  |  |  |
|  | Type (bore or open well/ in-well bore) |  |  |  |  |
|  | Year of digging |  |  |  |  |
|  | Depth |  |  |  |  |
|  | Discharge (good / average / poor |  |  |  |  |
|  | Pump used Diesel/ electric |  |  |  |  |
|  | Area irrigated (ac) |  |  |  |  |
|  | Plots Irrigated (plot nos.) |  |  |  |  |
|  | Crops irrigated |  |  |  |  |
|  | Method of irrigation |  |  |  |  |
|  | Plot numbers that can be provided critical irrigation. |  |  |  |  |

- Arriving at Strategic Plans:

- Planning for Protective Irrigation from Existing Sources

    - For each LMU area (plots numbered) identify sources of protective irrigation on the map.

    - Assess if the water bodies will have water during the stage.

- Provide Inputs on Protective Irrigation Options: (Use Flip Chart on Protective Irrigation)

    - Ensuring Timely Sowing: (show the photographs/ flip chart slides)

      - Option 1: Row wetting and seeding. If the forecast is not very negative and when rains are expected within 10 to 15 days; instead of losing the season – farmer can sow row crops like redgram by applying water. Aqua-planter – for groundnut for e.g. enables it.

      - Option 2: Tanker providing irrigation attached with a plough (seeding).

      - After assessing the need and arriving at the options, develop the proposal for infrastructure to be kept at CLiCs and its feasibility.

    - Protective Irrigation with Lined Farm Ponds: (discussion with photographs of lined farm ponds)

      - Storage capacity of each farm pond of size 10 m x 10m x 2.5 m = 250 cu.m volume’ say 200 cu.m

      - For 5 acres of land x 100 mm rainfall (assume)

      - Total rainfall available in 5 acres : 5  acres x 4046 sq.m/ac x 100/1000 meter rainfall = 2023 cu.m rain water

      - Of this even 20% is runoff = 404 cu.m of runoff water that can be collected into farm ponds. This is more than one filling of the farm pond. Experience suggests that such farm ponds (one in 5 acres drainage area) can fill 2 to 3 times during a season depending on rainfall.

    - Water lifting devises & Diesel / electric Pumps:

      - Depending on the number of surface water bodies and the open wells, figure out how many mobile diesel pumps need to be there for effectively covering the designated protective irrigated area within one week.

      - These many diesel pumps are required on custom hiring basis at CLiCs.

    - Mobile Protective Irrigation:

      - Water can also be transported within limited/ economic distances. Explore if such options exist. There are 2 possibilities:

          - Pumping from any water source – tank / borewell / open well and irrigating using sprinklers/ drips.

          - Filling in a tanker from a water source and transporting to the field.

      - Arrive at number of sprinklers, pipes, pumps etc., required to be placed at the Custom hiring Centers (CLiCs). This also includes aqua-planters.

- Plan for Farm Ponds:

    - Mark best locations for farm ponds on the map; along with the names of farmers and plot numbers.

    - Since every plot can’t have farm ponds; agreements have to be reached among neighbouring farmers on water sharing  from farm ponds.

    - Site verification and farmers’ consent (including on contribution) to be taken later.

    - If there is demand for many, prioritize the farm ponds as the total budget available for this purpose is limited. (One way is to allocate farm ponds for each LMUs based on their area).

    - Arrive at the list of prioritized farm ponds

- Explore Possibilities of Groundwater Collectivisation:

    - Explain about groundwater collectivization.

    - If there is potential, this can be taken up separately.

    - Get the farmers and area that they would like to bring under collectivization.

    - If such potential sites are identified LFA/ LTA will support separately in developing the proposals.

- Exploring status of water use efficiency and ways to improve

    - What is the status of usage of irrigation equipment (pipes, sprinklers, drips etc.).

    - How to improve these?

- Establishing a Rain-gauge:

    - For monitoring rainfall, drought spells etc., it is important to install a raingauge (even a low cost one) at the FFS sites. This along with weather forecasts help in arriving at decisions on protective irrigation for each LMUs.

    - Identify location for installing a rain gauge along with a person who takes responsibility of recording etc.

- Drinking Water for Livestock:

    - Mark the normal livestock tracks passing through the “Learning Site”

    - Plan and provide for a water trough (with small height for small ruminants) that can be filled with a bore well (or other source) for livestock drinking water.

- Water allocation for composting: Water is a critical input in composting. Ensure water is allocated to each  in situ compost pits planned. Also plan for the compost pits nearer the water bodies.

- Summary of the Protective Irrigation Plans:

Table 16: Summary of Protective Irrigation Arrangements

| Sl No | LMU Name | Plot No. (GE Map) | Farmer Name | Major crop | Drought Vulnerability | Protective irrigation arranged (yes/no) | Source of Protective Irrigation (Id.no. of waterbody) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

    - Organising data in the above Table helps in summarising it LMU wise or farmer wise and also helps to map.

    - Describe the protective irrigation arrangements arrived at; modalities of using the equipment (such as pipes, drips, sprinklers, pumps) on hire basis.

    - Provide an estimate of the value of avoidable crop looses in comparison with the protective irrigation; as a rationale for the investment (cost-benefit)

Table 17: 	Summary of cost of new water harvesting structures

| Sl No | LMU Name | Type of New structure proposed | Plot No. | Cost item | Unit | Rate | Qty | Amount | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Table 18: 	Plan for the Protective irrigation equipment

| Sl No | PI equipment details | Purpose | Cost item | Unit | Rate | Qty | Amount | FPO contribution | Project Cost |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

### PLANNING EXERCISE 5: 	PLANNING FOR CROP SYSTEM AND SEEDS

Drought and vulnerability in rainfed systems is a complex phenomenon; crop systems evolve over time with respect to the varying topography, climate patterns, soil types and specific constraints. Understanding this complexity is important to appreciate the traditional coping strategies and build in new understanding.

Crop systems diversification is an important means of security against climate variability. It’s one of the focal areas of APDMP. Diversification also may provide a basis for integrating livestock and to ensure diverse food supply at homesteads, an important aspect of nutrition security.

The exercises detailed here will help in:

- Understanding the present crop patterns, trends and their vulnerability.

- Arrive at plans for diversification

- Assess and plan for seed requirements

- Situation Analysis

  - Crop Calendars:

Mapping the crop calendars against the LMUs is an useful tool to understand the crops in relation with soils and local rainfall patterns. Table 19 details the Crop Calendars.

Table 19:	Mapping Crops Calendar

| S.No. | LMU Type/ soil type | Irrigated / rainfed | Crop(s) | Month | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  | Jan |  | Feb |  | Mar |  | Apr |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Fortnight | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 |

Can give numbers or symbols for crops that are cultivated as pure crops and those that are intercrops or mixed crops (have 3 different notations)

Notes on how to fill up the Crop Calendar:

| Use LMU Type or soil type. harvesting Mark the sowing window by an arrow (starting week and end week – i.e. beyond that fortnight the crop is not sown. - Mark any other major operations involved (avoid marking weeding and other agronomic practices) – to avoid making it clumsy. - If there are different varieties having different crop schedules – treat them as separate. (very important). - The crop calendars also give an idea of the local contingency cropping systems i.e. if the rains are delayed beyond a point, crop shifts takes place. | - The crop calendars are very useful reference visual for planning and future use in APDMP in evolving drought management plans. Once done these can be done on a larger flexy sheet and pasted in the CLiCs for easy reference. - Whenever a new crop or variety is thought about – this calendar can become the basis of where and how it has to be introduced. - Best is to mark the ‘Kaarte’ and ‘Nakshatra’ (on the calendar) which are the traditional reference points for farmers in crop calendars. |
| --- | --- |

Table 20:	An Example of Crop Calendar:

| Crop | Telugu name | Rohini | Mirugu | Arudra | Pushyami | Punarvasu | Aslesha | Makha | Pubba | Uttara | Hasta | Chitta | Swati | Vishaka | Anuradha |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 25th May | 8th June | 22nd June | 6th July | 20th July | 3rd Aug | 17th Aug | 31st Aug | 13th Sep | 27th Sep | 11th Oct | 24th Oct | 6th Nov | 19th Nov |
| Green Gram1 | Pesarlu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cowpea1 | Bebberlu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Black Gram2 | Minumlu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sorghum1 | PachaJonnalu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Little Millet1 | Samalu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Red Gram1 | ErraKandulu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | TellaKandulu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | NallaKandulu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground Nut1 | Palli |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cotton2 | Patti |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Maize2 | Mokka Jonna |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Paddy1 | Vadlu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Finger Millet1 | Tydalu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tymol Seeds1 | Vamu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Pearl Millet1 | Sajjalu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Foxtail Millet1 | Korralu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Niger1 | Gaddi Nuvvulu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sunflower1 | NallaKusmalu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Horse Gram1 | TellaUlavalu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | NallaUlavalu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | BhootaUlavalu | 1. crops grown in sandy soils 2. crops in black soils |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Safflower1 | TellaKusumalu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bengal Gram | ManchiSenegalu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sesame1 | ManchiNuvvulu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sorghum2 | TellaJonnalu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Index |  |  | Karthe in which Sowing takes place |  |  |  |  | Karthe in which harvesting takes place |  |  |  |  |  |  |  |

  - Is contingency plan discussed? While each has a sowing window and the rainfall does not occur within this window, you should have contingency plan.

  - Mapping the crop systems: While the crop calendars provide insights on the types of crops/ varieties, the systems in which these crop (combinations) are cultivated is important to understand. After the Crop Calendar exercise, the following matrix can be filled in with the same key informants:

Table 21:	Mapping the crop system

| S.No | Land Management Units (LMUs) | Soil Type | Crop System (crops and their system of sowing) | Crop ratios followed | Description of the crops sowing system (capture descriptive details separately) – border rows, inter crops ratios, intra crop ratios etc. | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  | Rainfed: |  |  |  |  |  |
|  | Irrigated |  |  |  |  |  |

Table 22:	Tracking changes in the crop systems (using the same Table as above):

| S.No | Land Management Units (LMUs) | Soil Type | Crop System (crops and their system of sowing) | Acreage under this system (acres) | Traditional or new (approx year of starting, if new) | Level of vulnerability to rainfall aberrations? High/ Medium/ Low; & describe | Outputs of the Crop systems (mark H:high/ M:medium / L: Low / N: nil |  |  | Should this be changed? | Reasons for continuing the tradition or for the change |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Income | Fodder | Grains for family |  |  |
|  | Rainfed: |  |  |  |  |  |  |  |  |  |  |
|  | Irrigated |  |  |  |  |  |  |  |  |  |  |

The above Tables (FGD with matrix exercises – each column is a key question) with a mix of young and old aged farmers will provide crucial understanding of the dynamics of crop systems.

- Arriving at Strategic Plans

  - Need for specific crop pattern changes for drought resilience?

    - LMU- wise changes in crop patterns to be explored.

      - Crop pattern shifts that can be taken up largely

      - Crop pattern shifts that need to be tried / experimented before spreading

    - What are the suggested shifts?

    - What are the specific strategies for promotion of desired crop pattern shifts?

From out of the discussion, summarise the action points arrived at:

Table 23:	Need for specific crop pattern changes for drought resilience

| S.No. | LMU | Present Status of crop systems | Vulnerabilities | Action points for Change |
| --- | --- | --- | --- | --- |

  - What are the seed requirements (for ensuring quality seed in time and of the locally adapted variety and for the chosen crop systems)?

    - Seed production to be taken up

    - Traditional varieties that need to be purified and multiplied

    - Quality seeds that need to be sourced from outside.

The above listing will help in CMSS plans. From the crop pattern discussion, also capture the information on seeds:

Table 24:	Seed Requirements

| S.No. | Crop | Variety / hybrid - name (including indigenous) | Duration (days) | Source of seed 1.Farm saved 2. Input dealer 3. Dept of Agrl 4.Others. | Issues related to seed availability | Whether the seed is to be included in CMSS? | Is seed treatment practiced? |
| --- | --- | --- | --- | --- | --- | --- | --- |

- Arriving at Detailed Plans for Climate Resilient Crop Systems

Table 25:	Prepare farmer-wise Table with the following details:

| S.No. | Farmer Name | LMU | New crop systems to be tried | Area (acres) | Seed Requirement (Kg.) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Crop 1 | Crop 2 | Crop 3 | Crop 4 |

The above is farmer-wise indent for the seed required for the farmer to try-out a climate resilient crop system arrived at before. This will be the plan for CMSS. This also gives the list of farmers and acreage for crop pattern shifts. Include demos also in the above Table itself.

### PLANNING EXERCISE 6: 	PLANNING FOR ZBNF PRACTICES

Purpose:  An important element of mitigating drought risks is to reduce the costs; primarily of external paid out costs. Replacing the external chemical inputs is important. Also, there is increasing evidence of organic/ natural farming practices (ZBNF) supporting drought resilience.

Plan for promoting sustainable agriculture practices including ZBNF through the following key strategies:

- Extension by practicing resource farmers

- Promote natural farming practices; develop master farmers locally for scaling up.

- Establishing a Bio-Resource Centre – as an enterprise for supply of raw materials or ready to apply products or for training.

Situation Analysis:

  - Mapping crop wise input use and costs;

In a matrix exercise with key informant farmers the following Table can be filled in:

Table 26:	Input usage, Pest and disease Control & related expenses:

| S.No. | Details | Crop 1 |  | Crop2 |  | Crop3 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Item &Qty applied per acre | Costs Rs. / acre | Item &Qty applied per acre | Costs Rs. / acre | Item &Qty applied per acre | Costs Rs. / acre |
| 1. | Name of the Crop |  |  |  |  |  |  |
| 2 | Seeds |  |  |  |  |  |  |
| 3 | Fertiliser application: |  |  |  |  |  |  |
| 3.1 | Manure application |  |  |  |  |  |  |
| 3.2 | Basal doses |  |  |  |  |  |  |
| 3.3 | During crop growth 1. 2. 3. |  |  |  |  |  |  |
| 4 | Pests & Diseases |  |  |  |  |  |  |
| 4.1 | Main pests observed: | Pests | Pesticides/ fungicides used | Pests | Pesticides/ fungicides used | Pests | Pesticides/ fungicides used |
| 4.2 | Approx cost per acre on pest/disease control | Rs/ac |  |  |  |  |  |
| 4.3 | Source of chemical inputs |  |  |  |  |  |  |

Bio Resource Centre:

The proposal is to promote one entrepreneur attached to CLiC.  This is a household having family labour and some land at the homestead.

The entrepreneur will do 3 things:

- Maintains and sell any mother solutions/ cultures to anyone wanting (including animal urine for concoctions)

- Prepares and supplies/ sells Ready-to-Apply inputs -for use in agriculture. (NSKE, Jeevamrutam.. etc)

- Will train anyone wanting to learn on making any botanical or other formulations.

Project will support in the following manner:

- Provides training and technical and business handholding support.

- Provide capital equipment (partly mechanised) – on nominal -rent basis for 2 years

- Guaranteed purchase of xxx lts of the preparations (to be used in ZBNF promotional activities); in case the products could not be sold. i.e. ensure viability for 2 years.

- Provides trainers’ fee for each farmer trained.

This will be a private enterprise but under the governance of FPO. CLiC will find market for the products. This will ensure availability of any inputs for ZBNF locally, if any farmer wants to buy and apply.

  - Are there any natural / organic/ NPM experiences in the GP? Any experienced farmers? If yes, list them. What are the previous experiences?

Strategic Plans:

A detailed FFS or ‘Farmer Learning and Action’ (FLA) program will be initiated at the Learning site spread over the entire year. Natural Farming practices will be taken up systematically in the course of the year. Similarly, a Bio-Resource Centre will also be established as an enterprise.

During planning exercise, the following needs to be finalised:

- Dividing the farmers into two FFS/ FLA program groups; names of the farmers and boundaries on map of each of the group.

- Identifying two farmers (one male and one female) along with their designated plots for taking up FLA measures and conduct of the program throughout the season. Mark the FLA sites on the map.

- Resource Farmers’ selection must be based on their enthusiasm to innovate, their potential as resource person (willing to give time for extension) etc.

Action Plans

Later during the course of implementation a structured exposure to natural farming measures be taken up for all farmers; a visit and interaction with practicing farmer or field visit. After this exposure, prepare a list of farmers who are willing to try out ZBNF and other programs.

### PLANNING EXERCISE 7: 	PLAN FOR IMPLEMENTS AND FARM MACHINERY FOR TIMELY OPERATIONS

Timely operations within the available moisture window is of utmost importance in Rainfed agriculture. Soil moisture window available after a rainfall event is very narrow and the operations like land preparation, sowing, weeding etc., needs to be completed quickly.

Small and marginal farmers often suffer from lack of required draught power or access to machinery services to complete works in time. Having access to required draught power with appropriate implements is a requirement for drought preparedness.

In this exercise

              - The gap in availability of farm implements, draught power (including bullocks) and farm machinery services is to be assessed and adequate measures to fill this gap will be planned.

              - Any machines/ implements that increase labour productivity (i.e. out turn of work of a labour day) and enhance their wage incomes can also be planned.

              - Any machines/ implements that reduce workload/ effort / drudgery of women labour can be identified and sourced.

Any equipment required will be provisioned in APDMP through the Custom Hiring Centre (CHCs) – owned and managed by the FPO. The plans for provisioning of equipment services here will also be through the CHCs part of CLiCs.

Situation Analysis:

- Inventory of draught power, machines, implements available with farmers in the Learning site:

A participatory exercise with farmers resulting into the following Table:

Table 27:	Summary picture of the availability of implements/

| S.No. | Operations | Scarcity | Equipment (implements/ machines/ power source) Used |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Bullock drawn |  |  |  | Tractor Operated |  |  |  | Engine operated/ Others |  |  |
|  |  | High/ med/ low/ nil | Name | No. | Rate (Rs/ac) Hiring | Name |  | Nos. | Rate (Rs/ac) Hiring | Name |  | No.s | Rate (Rs/ac) Hiring |
|  | No. available with the farmers |  | Bullocks |  |  | Tractors |  |  |  |  |  |  |  |
| 1 | Land preparation |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Seed sowing |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Weeding |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Inter cultivation |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Providing irrigation |  | Covered in Prot. irrigation |  |  |  |  |  |  |  |  |  |  |
| 6 | harvesting |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Shredding residues |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | Threshing |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | Others |  |  |  |  |  |  |  |  |  |  |  |  |
|  | …. |  |  |  |  |  |  |  |  |  |  |  |  |

A detailed farmer-wise data on farm implements/ machines/ draught animals/ tractors etc., owned by each of the farmer can be collected.

Strategic Plans: After a summary picture of availability of draught power/ tractors/ machinery, their present hiring costs and scarcity situation, the Planning Group need to workout strategies for meeting the gaps to ensure timely sowing. These are essentially local solutions. The planning committees/ farmers groups may deliberate and come up with the following CHC plan:

Table 28:	CHC Plan

| S.No. | Operations | Present Scarcity situation | Suggested implements/ machines to be made available through CLiCs | Approximate Number required. | Amount | What would be the demand estimated per year for hiring Rs/ yr. |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | High/ med/ low/ nil |  |  |  |  |
|  | Total no. of Bullock pairs available with farmers |  |  |  |  |  |
|  | No. of Tractors available |  |  |  |  |  |
| 1 | Land preparation |  |  |  |  |  |
| 2 | Seed sowing |  |  |  |  |  |
| 3 | Weeding |  |  |  |  |  |
| 4 | Inter cultivation |  |  |  |  |  |
| 5 | Providing irrigation |  |  |  |  |  |
| 6 | harvesting |  |  |  |  |  |
| 7 | Shredding residues |  |  |  |  |  |
| 8 | Threshing |  |  |  |  |  |
| 9 | Others |  |  |  |  |  |

The above plans feed into the CLiCs- CHC plans.

It will be useful to have an inventory of the

Table 29:	Availability of draught power.

| S.No. | Farmer Name | No. of Bullocks | No. of Tractors |
| --- | --- | --- | --- |

Table 30:	Inventory of implements/ machines with farmers

| S.No. | Farmer Name | Implement Name | Number available |
| --- | --- | --- | --- |

**have multiple rows for each farmer, if s/he has more implements.

The above Tables with farmer wise inventory will be useful in identifying farmers without access to farm implements/ machinery and target them for CHCs.

Chapter: 2	Indicative Structure For Compilation & Presenting Learning Site Plan & Its Assessment

A consultations was organised by LTA on 13th April, 2018 with 5 LFAs to provide feed back on one of their FA plans for the Learning Site. The following structure of presenting the plans were arrived at.

The following must be ensured:

- Plans also must be in Telugu prepared along with the farmers’ groups in the Learning Site.

- Though an advance copy is submitted by the FA, the FPO must submit it eventually to DPMU after discussion and approval.

- Overall writeup of the plan should not exceed maximum of 10 pages.

- Avoid long descriptions of APDMP in the plans

- Keep the plan document simple and focused on the subject.

WHAT IS EXPECTED IN THE PLANNING EXERCISE:

# There are five themes in addition to the work related to institutions viz.,

- Soil health improvement

- Crop systems diversification and meeting seed requirements

- Protective irrigation for securing crops

- Natural farming/ zbnf practices

- Farm implements/ mechanisation for timely sowing.

It was observed in the presentations that the list of works identified along with budgets are considered as ‘plans’. It was explained that the planning exercise must follow the following sequence:

- A theme being explored

- Situation analysis

- Identification of the specific issues/ problems to be addressed

- Setting up the objectives of the plan

- Strategic Plan: Arriving at the strategies to achieve the objectives; based on the situation analysis.

- Action Plan: Given the strategy what are the activities to be taken up, time lines, responsibilities

- Detailing of the Activities, costs, cost sharing and budgets

- What are the success criteria? To measure the effectiveness of the interventions.

The framework was explained to the LFAs during the training program initially by the LTA. It was reiterated that LFA must ensure that the objectives, strategies and activities are well planned before arriving at works/ budgets.

The structure of the report detailed below follows the above framework.

STRUCTURE OF THE ‘LEARNING-SITE PLAN’ : అభ్యాస క్షేత్రం :

- Identification:

District, Mandal, GP, LFA, FA

Lat / Long of the Learning Site.

- Brief description of the Cluster: just give the details in bullet points or in Tables.

  - GPs, hamlets,

  - Basic demographic description

  - Basic bio-physical description (Lat/ long)

- Brief Description of the GP where Learning site is located.

- Process of selection of the Learning Site:

  - Activities taken up, Dates, photo & any resource map photo

  - Resolution from the GP(s)

- Learning Site description

  - Learning site map: google earth map (drainage, plots, boundary) and cadastral map, LMUs boundaries, drainage lines, existing water bodies, borewells, irrigated area, any existing infrastructure.

  - Summary details of the Learning Site

area – (rainfed, irrigted), type of lands, farmers – caste, size class (economic),  (brief description).

- Land Management Unit :

  - Process of identification of the LMU; map of the Learning site with map.

  - Description of the LMU and their characteristics, area etc. (Table)

  - What are the drought vulnerabilities of each of the LMU & critical constraints for production?

- Thematic plans: Status and Strategic Plans on each theme for each of the LMU.

Theme 1: title (similarly for all themes..).

  - Situation Analysis of the LMU

  - What are the problems you are trying to solve?

  - What are the objectives to be acheieved for this year?

  - What are the strategies you arrived at?

  - What are the activities planned as per the strategy? Critical mile stones for assessment? Time lines for the critical milestones? Responsibilities.

  - What are the  budgets for each of the activity? How costs are shared across farmers’ investment, APDMP and convergence.

For themes that do not have much variation across LMUs; a compiled work plan for all the LMUs together can be presented.

- Map with LMUs and physical activities planned & other details with description.

- Consolidated action plan for all the themes for the Learning Site (in a Table)

  - LMU/ Theme/ Problem / Objective / Strategy / Activity Planned

  - Activities, Time lines and Budgets

    - Consolidated Activity Plan:  LMU / Theme / Activity Planned / Time Line/  Budget / source of budget

- Annexure: Detailed – Plot wise and/or Farmer wise Activity plans, with budget and source (APDMP/ Convergence) (see the Table structure in Annexure 1). This will be submitted as an excel sheet.

- Expected Impacts and Monitoring Indicators

  - Describe theme wise & LMU wise –

    - targets to be achieved in terms of activities

    - expected impact on productivity, production, income, food, fodder or any other expected areas of impact.

  - Workout the following Table:

    - S.NO / LMU Type / Crops / Present System/ Avt Yield / Net Income // proposed changes / Expected Yield increase / Expected increase in net income/ expected increase in fodder / Expected increase in household food from farm

  - What are the monitoring indicators that describe success of each of the planned Themes with respect to production and drought preparedness? (how do you want the DPMU to assess your success in this Learning Site?)

- Institution Assessment:

  - brief report on FPO formation

  - Details of the FPO; registration number, date of registration, no. of members, share capital, Bank and bank account details, names and contact info of the key office bearers.

- All other details in Annexures

3.	DATABASES TO BE MAINTAINED FOR EACH LMU: (TO BE UPLOADED INTO THE PROJECT WEBSITE).

Table 31:	Detailed Table of Action Plan for the Learning Site:

| SNo. | FA | Learning Site | LMU Type | Plot No. | Farmer Name | Theme | Activity | Details of cost estimation | Units | Rate (Rs/unit | Quantity | Amount (Rs.) | Farmers’ Cost sharing | From Convergence | From APDMP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  | Rs | Rs. | Rs. | Rs. |

All planned activities need to be filled into this Table. If there are multiple activities in a plot, there will be multiple lines, each activity in a line.Do not change the structure. Once you have all these activities in the above Table, you can use ‘Pivot Tables’ utility in Excel to come up with any summary Table. This structure needs to be maintained at all levels of aggregation (Cluster, FA, LFA, DPMU and SPMU). Dash boards can be created at different levels, if we all follow the same structure.

Table 32:	Detailed Plot data for the learning site: (this can be generated from the FGD with Google Earth Map).

| SNo. | FA | Learning Site | Plot No. | Farmer Name | LMU Type | Area (acres) | Irrigated (Yes/No) | Source (if irri) | Own/ Tenancy | Crop | Variety | No. of Trees in the plot | Protective irrigation required Yes/no | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Table 33:	Farmer Database for the learning site: (this can be generated from FGD)

| SNo. | FA | Learning Site | Farmer Name | Adhar No. | Habitation | Caste (Sc/St/BC /OC) | Member of FPO | Paid Share capital? | Owner/ Tenant | Total Land Irri | Total Land RF | Land owned in the LS | Has Tractor Yes/no | No. of Bullocks | No. of Sheep | No. of Goat | No. of Poultry |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Table 34:	LMU Details: (This will be obtained in the initial exercises on classification of LMUs.

| S.No. | Parameter | Values (indicative) | LMU 1 | LMU 2 | LMU 3 | LMU 4 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Approximate Area | Acres |  |  |  |  |
| 2 | Soil Texture | (Clayey, loam, silt and sandy) |  |  |  |  |
| 3 | Soil Color | (Red, Black, etc.) |  |  |  |  |
| 4 | Soil Depth | (deep: >60cm, medium: 11-60 cm, shallow: <=10cm) |  |  |  |  |
| 5 | Slope | (high, med, low) |  |  |  |  |
| 6 | Water holding capacity | (high, medium, low) |  |  |  |  |
| 7 | Specific Problems |  |  |  |  |  |
| 8 | Fertility status | (good, average, poor) |  |  |  |  |
| 9 | Crop systems that are generally taken up |  |  |  |  |  |

The above Tables forms the database for the project i.e. the FA needs to keep them for uploading into the project website.

4.	ASSESSMENT OF THE PLANS BY DPMU& RECOMMENDATION NOTE:

DPMU team can assess the plans on the following aspects before recommending these (with their comments) to SPMU for sanction.

The plans need to be assessed for 4 Broad aspects:

  - Participation and ownership of the community

  - Plan against the objective: at the outset would the plan result in the objective i.e. securing crops and livelihood

  - Rigor of the plans : Theme Situation Analysis  Problem/ opportuntity/ issue identification  Arriving at Strategy after evaluating strategic options  operational modalities  & work plans  budgets. Assess if this sequence is followed.

  - Relevance / appropriate of the works to the strategy, prioritization and value for investment and if what is proposed will sustain post-project.

  - Works & budgets – if followed cost norms in arriving at the budgets.

  - Is the plan implementable/ feasible.

DPMU may send their recommendation in a note as per the following checklist of questions. Some key questions are:

- Is there GP resolution for the learning site?

- Have the FPO submitted the plan & is there a Telugu copy that farmers have gone through before submitting?

- Level of participation and ownership of the farmers in the learning site.

- Are the Land Management Units identified rightly? Did it capture the variability correctly?

- Did the plan identify specific constraints in each of the LMU; especially related to drought vulnerability?

- Have the strategies been worked out to deal with the issues identified (or just planned for works and budgets?) and are pertinent to the situation analysed / problems identified?

- Your summary observations on how the plans address drought vulnerability?

- Are  the activities planned come from adequate exploration and discussion/ evaluation of various options?

- Are the budgets proposed for investment from APDMP – arrived at after total exploration of all other possibilities with convergence?

- Are the farmers prepared to contribute and own the program?

- Is there adequate rate of return on total investments? i.e. the investments proposed commensurate with the benefits (to farmers, ecological or restoration of land? )

- In your assessment:

  - Considering the total budget to be spent, the budget to be spent under APDMP and are the benefits to be accrued commensurate with the investments? What is the simple cost-benefit analysis?

- Do the plan submitted describe indicators for assessing success of the program?

- Is the project level data (detailed earlier) is available for uploading to the site?

- Summary of the budget to be released.

THE DPMU team leader has to give her/his observations as per the above check list before recommending them to SPMU. This is a list that mentions key points to be looked at while approving the action plans. In case not satisfied, they may work with LFA about the needed changes.

If there is any disagreements with LFA, the same may be mentioned in the recommendation report- including the different points of view.

Chapter: 3	Guidelines for Works from Project Fund

The first workshop (from 9th to 12th January, 2018 at AF Ecology Center, Anantapuramu) with the NRM and Agriculture team  members of LFAs and FAs (of 4 LFAs) and DPMU resulted in a detailed planning exercise for the Learning Site.

The 2nd workshop with the LFAs, DPMU and SPMU teams based on the field plans prepared was organised on 22nd Feb, 2018 at Anantapuramu. The following guidelines emerged from the discussions collectively. These were facilitated by the LTA.

The project will not spend on

- Activities where mainstream programs budgets are already available

- Activities in saturation mode: APDMP grants will be spent only to demonstrate successful interventions, pilot innovations and to mobilise demand. As convergence is one of the major objectives and success indicator of the project, funds for scaling up & for saturation of activities has to be mobilised from other mainstream programmes such as MGNREGS and also from various other departments which are working for the same objectives. This is generally followed as a guiding principle while LFAs plan/ recommend the plans for funding by APDMP.

What is “Learning Site”?

A 100 ha area (a sub-watershed) is to be identified by the community with support from FA. For the first year focused attempt will be made to take up comprehensive drought resilient measures in this area that includes taking up NRM works, year long farmer field schools ( a modified version), among others. The following guidelines are evolved for the 1st round of work on the subject with 4 LFAs; these will be taken up by the DMPU for assessing the plans/ fund proposals recommended by LFA. The actual cost estimates are as per the watershed works that are in practice. This note sets the limits to which APDMP will invest.

ACTIVITIES / INTERVENTIONS FOR DEMONSTRATIONS/ PILOTS THAT CAN BE FUNDED FROM APDMP GRANTS:

- SOIL CONSERVATION WORKS:

  - This activity is encouraged to be mobilised from MGNREGS

  - Soil conservation works are much needed in the farms :

    - where tank silt is applied afresh and

    - fields with sever erosion.

  - If convergence efforts were not successful well before the Kharif season, APDMP may spend budgets as grant in such farms where tank silt is applied or those with severe soil erosion problem. (gully-heads).

  - The limit is set to a maximum of 20 acres to be invested from the project grants during the first year in the Learning Site. This is only applicable for first year of implementation; funds have to mobilised through convergence for rest of the period based on demand.

  - The cost norms are as same as MGNREGS

  - Cost-estimates with design has to be submitted along with proposal if this activity is proposed under APDMP grant.

- LINED FARM PONDS FOR PROTECTIVE IRRIGATION: These are taken up as a part of the planning for Protective Irrigation in the Learning Site. The plans have to provide details of the area to be protected through each of these farm ponds. Field level discussion is important to arrive at negotiated ways of farmers sharing the farm ponds (area and water). These must be for harvesting run-off water but not to store water pumped out of borewells. Must be lined in case of red-soils and necessary precautions taken to prevent seepage in case of other soils.

  - A maximum of 10 farm ponds with lining per each Learning Site to be taken up under APDMP funds.

  - These are only to be taken up in rainfed farms

  - Encourage existing farm ponds for lining; a maximum of 5 farm ponds

  - Recommended size of the farm pond is 10m x 10m x 2.5 m with 250 cum volume which can serve 4-5 acres @ 50 cum of water per irrigation for protecting rainfed crops from drought spells.

  - These 10 farm ponds’ digging can be taken up by machines

  - Upper limit of cost of each farm pond with lining with the above size is Rs.13,000 for digging and Rs. 9000 for lining for each farm pond (includes cost of cement and water). A detailed design and estimate will be shared by AF from their experience. Farmer has to contribute labor for lining.

  - If taken up from MGNREGS -the standard estimates as per MGNREGS norms will apply.

  - Standard estimate & design for farm pond with lining will be shared by  AccionFraterna by 28th Feb’18.

  - AF will provide resource persons for demonstrating one complete farm pond lining per each LFA; the demonstrations have to be complete by April, 2018. LFA has to make all necessary arrangements including arranging for material before the resource person comes.

- WORKS RELATED TO COMPOSING ON FARMS & RESIDUE MANAGEMENT:

  - One compost pit per ha is recommended to start with; a pit of 4m x 3m x 0.5m = 6 cum volume. Biomass is filled up to 1 meter. This will give about 1.5 to 2.0 tons manure from each pit that can be applied in one acre. If the farmer is successfully managing it, it can be expanded to cover one pit per each acre in later years along with biomass plantation.

  - Each compost pit comprises of digging, planting (Glyricidia or other plans) around the pit to add biomass and give shade.

  - A maximum of 3 compost pits per farmer can be taken up under APDMP grant

  - Assess biomass availability before proposing Composting activity

  - The cost per pit (including one cycle of compost making) with dimensions 4m x 3m x 0.5 m  is Rs. 5,565/-. The cost includes pitting, biomass plantation and over turning; farmer has to source biomass and fill it.

  - The expected output is 1.5 to 2 tonns of Manure from each pit

  - A detailed estimation has to be submitted for approval under APDMP grant

- TANK SILT APPLICATION FOR SOIL IMPROVEMENT:

  - Proposed only for farms with poor soils; need to be taken up in convergence with MGNREGS. APDMP funds used only if all attempts to mobilise MGNREGS at district level did not succeed before May, 2018.

  - Maximum silt application with APDMP budgets to be taken up is for 50 acres in the learning site.

  - The cost of silt application per acre is up to Rs.6,500/- (Rs. 2,000/- for silt excavation with machine & filling tractors + Rs. 4,500/- after 50% farmer contribution for transportation and application in field).

  - Assess the quality of silt before applying; It is observed that applying farmyard manure/ compost along with silt is better for quick results.

- DEEP PLOUGHING: Particularly in farm plots which have been uncultivated for some time, deep ploughing is useful to bring the lands back into cultivation. A provision upto 10 acres can be used for deep ploughing in the “learning site”.

- PROVISION OF SUPERVISION COSTS: For supervision of works implementation, a Community Resource Person (CRP) may be identified. On the job training may be provided for the identified CRP. One of the basic responsibilities of CRP is ensuring quality of works and required book / records keeping. For each learning site, up to  90 days of CRP cost @ Rs. 400 per day; if required.

After planning for NRM works, the FAs need to evolve the yearlong action plans for comprehensive drought resilience measures. This will be arrived at later. See the Summary Table on Budget provision for NRM works in “Learning Site”. These are budget provisions to be used only in case convergence efforts did not succeed. The provisions are upper limits and the actual consolidated proposals from LFAs need to be based on actual areas on ground, design and estimates. The proposals must be accompanied by a map showing the details of various works. Data entry in the mobile application also need to be complete.

Table 35:	Summary of Budget Provision for NRM Works in “Learning Site”:

| Provision for Works Under APDMP in the “Learning Site” | Unit | Unit Cost | Farmer Contribution (%) | Farmer Contribution Amount (Rs.) | Amount after deducting Farmers Contribution (Rs.) | Number of units | Total Amount (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Soil conservation/ Farm Bunding | Acre | Rs7,700 | 0 | Rs0 | Rs7,700 | 20 | Rs1,54,000 |
| Farm ponds |  |  |  |  |  |  |  |
| Farm ponds with Lining | Number | Rs21,000 | Labor for lining | Rs0 | Rs21,000 | 10 | Rs2,10,000 |
| Lining of existing Farm ponds | Number | Rs9,000 | Labor for lining | Rs0 | Rs9,000 | 5 | Rs45,000 |
| Composting |  |  |  |  |  |  |  |
| Compost pits + Biomass plants + compost preparation (1 cycle per year) | Number | Rs5,565 | 0 | Rs0 | Rs5,565 | 25 | Rs1,39,122 |
| Tank silt application |  |  |  |  |  |  |  |
| Silt excavation & filling tractors | Acre | Rs2,000 | 0 | Rs0 | Rs2,000 | 50 | Rs1,00,000 |
| Transportation & field application | Acre | Rs9,000 | 50 | Rs4,500 | Rs4,500 | 50 | Rs2,25,000 |
| Deep ploughing | Acre | Rs1,600 | 0 | Rs0 | Rs1,600 | 10 | Rs16,000 |
| Sub total |  |  |  |  |  |  | Rs9,45,372 |
| Provision for Field supervision | CRP Day | Rs400 |  |  |  | 90 | Rs36,000 |
| Total |  |  |  |  |  |  | Rs9,81,372 |

Note: 	These are maximum budget provisions only; actual budgets must be arrived at based on field data.

SPECIFICATION REPORT

- Soil moisture conservation measure with using trench cum bunding. Earth work excavation in ordinary and gravelly soils or hard gravelly soils from barrow pit size 1 meter width and 0.50 meter depositing for bund with a clear berm of 0.30meter, breaking clods and neat banking and sectioning.  Cross section of bund 0.50 square meters and maximum length of bund   per acre is 100 RMT.

- Creating new or renovating of farm ponds of 200 to 250 cum volume rain water storage capacity for providing critical irrigation to rainfed crops during dry spells of monsoon.

- Earth work excavation in ordinary and hard gravels soils up to 2.5meter depth with a side slope of 1:1 by hydraulic machine as per Standard data sheet 2017-18. Top width may be verifying from 10x10 to 8x8m size with a clear berm of 2m between pond pit and bund all round.

- The bund sectioning by manual labour as per MGNREGS latest rates.

- Provision of inlet and outlet with using dry stone packing

- Provision of silt trap of 2x2 meter size and 1 depth before 2meter of the inlet.

- Water proofing with cement and mud mortar (1:6) prop plastering for pond bottom bet and all round sides.

- Making compost and application with using farm residues and biomass of trees around the farm by using semi aerobic method.

- Earth work excavation in ordinary or hard gravel soils for compost pit size of 3x2x0.5 cum and neat banking of excavated soils on banks with 0.5 meter berm.

- Biomass plantation around the pit in 3 rows on bund the compost pit 50 no of (5”x9” bag) plants.

- Collection of 6 cum of dry and wet biomass and deposit near by the compost pit.

- Filling the biomass in 9”thick layers in compost with sprinkling of dung slurry to of 5 to 6 layers.

- Covering with 1”thick top soil on the compost bed.

- Wetting the compost bed with 100 to 120 litre of water once in a week up to 7 weeks.

- Over turning of compost bed after 21 days and 45 days

- Harvesting of compost after 70 to 75 days at semi decomposed stage and application on farm.

- Tank silt application

- Excavation of tank silt and loading of tractor load by hydraulic machine.

- Transportation of silt from tank to farm and unloading with hydraulic jack of tractor/ by manual labour.

- Breaking of clods and spreading of silt on farm.

Columns in the table will be expanded. This table will be used in subsequent exercises too..

Farm Yard Manure, Compost (different types including Vermi Compost, NADEP)