Minutes of  meeting

on

Core team members workshop to design FLA

Date: 18th July 208  Venue: APDMP, SPMU Office Guntur; Organized by: SPMU and LTA- WASSAN

Agenda of Workshop:

- Finalization of content for first four FLAs

- Finalization of themes for Year-long 24 FLAs

- Session plan for each FLA

- Finalisation of date and schedule for Training of Master trainers

- Formation of team of resource persons for Training of master trainers programme

- Plan for next 6 months

Participants:

- VDV. Krupadas , COO, SPMU, APDMP, Guntur

- Nunna Venkateshwarulu, SPMU, APDMP, Guntur

- M. Subramanyeswar Rao, DPMU Chittoor

- Murali, DPMU, Kadapa

- Dr T. Yellamandha Reddy, AF EC, Anantapur

- A. Ravindra, LTA-WASSAN

- M. Bhakthar Vali, LTA-WASSAN

- K. Padma, LFA-Aranya, Kurnool

- G. Chandra Sekhar, CSA, Hyderabad

- Jayaram Killi, APMAS, Hindupur, Anantapuram

- S.S. Kandagal, WASSAN

- Y. Sankar Naik, SPMU, APDMP

- N. Praveena, SPMU, APDMP

- V.S. Chandrasekhar, WASSAN

- Sri Ram Iyer, WASSAN

The process held in the meeting:

- Welcome and need for Famers Learning and Action (FLA): Sri. VDV. Krupadas, COO, SPMU welcomed all participants for the Core team members-FLA meeting.  He briefly explained the purpose of the meeting. He suggested arriving at a better and easy title in Telugu Language for “Farmer Learning and Action (FLA)” as farmers should mention it easily. He hopes that this day’s meeting will finalise the content for forthcoming 6 FLA sessions, He suggested to prepare the content keeping the three levels of training in view, i.e. farmers, master farmers and master trainers. He also suggested finalizing the framework for session plan keeping the delayed onset of monsoon in this Kharif season, which drastically hit the sowing operations. There is a need to prepare contingency plans for Kharif cropping as sowing is not taken place in at least 80% of the APDMP project villages. Since, representatives of most of the LFAs are present in this workshop, it is suggested to immediately respond to drought condition on a priority basis and plan for mitigating the negative impact caused by delayed onset of monsoons. LFA representatives also shared the details of their discussion with farmers on the drought condition, strategies to ensure sowing operations and contingency plans.

- Introduction of participants: Participants introduced themselves.

- Brief overview of FLA

| Sl No | Item | Particulars |
| --- | --- | --- |
| 1 | FLA sessions |  |
|  | No of LFAs | 9 |
|  | No of FAs | 35 |
|  | No of learning sites | 105 |
|  | Frequency: No of FLA sessions in 100 ha of learning site | 24 (Once in every fortnight) |
| 2 | Master Farmers |  |
|  | No of FLA groups in each learning site | 2 (One for 50 ha covering 20-50 farmers) |
|  | No of Master farmers required for organising FLAs in Learning site | 2 (1 for each FLA group) |
|  | No of farmers to be trained as Master farmers | 3 (Considering 1 person extra to substitute in case of absence/urgency or any other need) |
|  | Total no. of master farmers to be trained | 315 (@ 3 per Learning Site) |
|  | No of Agriculture facilitators and CB Facilitators who need to be participated in FLAs | 70 (1+1 from 35 FAs) |
|  | Thus, the total participants for Master farmers’ training | 385 (315+70) |
|  | Frequency of Events on Training Master Farmers | Once in 3 Months (covering the content of 4 FLAs) |
| 3 | Master Trainers |  |
|  | No of Master trainers required to train the master farmers (ToT) | 36 (4 from each LFA) |
|  | No of Communication and CB Experts of LFAs to be associated with ToT on master trainers | 9 |
|  | Total number of participants in ToT of Master Trainers | 45 (36 Resource Persons and 9 CCB experts of LFAs) |
|  | Frequency of Events on ToT to Master Trainers | Once in 3 Months (covering the content of 4 FLAs) |

- Suggestions from participants on nature of FLA sessions

- This FLA should be useful to the farmers in converting knowledge inputs into action. Therefore, this should be an improved version to traditional FFS where action is generally depending on individual’s interest. In FLAs of APDMP it is must that the knowledge should lead to action. Hence, FLAs should facilitate farmers in doing this.

- FLA makes serious efforts to enhance farmers’ knowledge and action. However, it may be noted that it is not the responsibility of FLA to find solutions to all problems. Ideas may emerge from FLAs. Therefore, it encourages innovation and alternative methods.

- It is important to integrate water concerns in FLA sessions. Considering the importance of rain in rainfed areas, rainfall and water related data must be kept available to facilitate better decisions and actions. Therefore, LFAs should collect data and prepare information related to Learning sites on local specific rainfall data, local cropping pattern, etc. A comparison of data related to previous years would help in understanding rainfall trends and take better, informed decisions.

- A broad framework of indicative topics/themes for FLA as per the season/fortnight would be prepared. It is the responsibility of LFAs to make suitable modifications to use in their local context. The core team will prepare content for FLA sessions keeping the cropping practices in all APDMP district/LFA areas. LFAs can add any additional topic in the FLA sessions if it is relevant and important.

- Few topics are relevant in all FLAs. These common topics would be discussed regularly in all FLAs.

- Earlier it was decided that Training of Master Farmers or ToT of Master Trainers will be conducted for the content of 4 FLA sessions. Now, it is decided that content of 6 FLA sessions could be considered for training master farmers and master trainers.

- List of topics for FLAs for July -December 2018:

Mr SS Kandagal presented the list of topics for all 24 sessions. After discussion, following is the finalized list. The details of core team members who volunteered to contributed content is also mentioned in this table.

| Session | Month | Theme | Topics | Responsibility |
| --- | --- | --- | --- | --- |
| # | All Fn | Weather Advisory | Regular topics | Dr T. Yellamanda Reddy |
| # | All Fn | Agro Eco System Analysis | Regular topics | N. Venkateswarulu S.S. Kandagal |
| # | All Fn | Weather Advisory, Forecasting, Utilization of weather information through APP | Regular topics | Dr T. Yellamanda Reddy |
| # | All Fn | Pest and disease mgmt through ZBNF | Regular topics | G. Chandrasekhar |
| # | All Fn | Group Dynamics | Regular topics | S.S. Kandagal |
| # | All Fn | Protective irrigation | Regular topics | Dr T. Yellamanda Reddy |
| 1 | July 1st fn | Rainfed Mango | Canopy management | Dr T. Yellamanda Reddy |
| 1 | July 1st fn | Soil health Management | Integrated nutrient management including reclamation of soils | N. Praveena |
| 1 | July 1st fn | Soil health Management | Preparation and application of Ghana/Dhrava Jeevamrutham | N. Praveena |
| 1 | July 1st fn | Moisture | Grid-lock systems of in situ soil moisture management | G. Chandrasekhar |
| 1 | July 1st fn | Moisture | ZEBA |  |
| 1 | July 1st fn | Moisture | Understanding rainfall and soil moistures, water loss | Dr T. Yellamanda Reddy |
| 1 | July 1st fn | Crop Diversity | Integrating Navadhanya cropping system | A. Ravindra |
| 1 | July 1st fn | Seeds and sowing | SRI method in millets | G. Chandrasekhar |
| 1 | July 1st fn | Seeds and sowing | High density Cotton | G. Chandrasekhar |
| 1 | July 1st fn | Seeds and sowing | Row water sowing | Dr T. Yellamanda Reddy |
| 1 | July 1st fn | Protective Irrigation | Farm Pond Lining | Dr T. Yellamanda Reddy |
| 1 | July 1st fn | Seeds and sowing | Seed priming or Seed hardening | G. Chandrasekhar |
| 2 | July Second FN | Weed Management | Weed management | Jayram Killi |
| 2 | July Second FN | Moisture stress management | Soil Moisture Management-Mulching practices | Dr T. Yellamanda Reddy |
| 2 | July Second FN | Moisture stress management | Soil Moisture Management-Other practices | Dr T. Yellamanda Reddy |
| 3 | August 1st fn | Crop Mgmt | Crop growth and development | S.S. Kandagal |
| 3 | August 1st fn | Biomass plantation | Bund Plantation | K. Padma |
| 3 | August 1st fn | Biomass plantation | Seed Dibbling | K. Padma |
| 3 | August 1st fn | Moisture | Dry spell management | Dr T. Yellamanda Reddy |
| 4 | August-2nd fn | Harvesting and Post harvest | Harvesting short duration crops | M. Subramanyeswar Rao and I. Murali |
| 4 | August-2nd fn | Harvesting and Post harvest | Utilisation of appropriate tools for crop operations | M. Subramanyeswar Rao and I. Murali |
| 5 | September-1st fn | Farm pond Technology | Assessing irrigation requirements, designing and planning the farm ponds, execution of farm ponds, different methods of lining, utilization of water, etc | Dr T. Yellamanda Reddy |
| 5 | September-1st fn | Protective Irrigation | Skill building on Operation and maintenance of different types of Irrigation Equipment | Dr T. Yellamanda Reddy |
| 6 | September-2nd fn | Pest and Disease Mgmt | Lifecycle of different pests and insects | G. Chandrasekhar |
| 7 | October-1st fn | Harvesting and Post harvest | Precautions for harvesting and post harvest | M.Subramanyeswar Rao and I. Murali |
| 7 | October-1st fn | Moisture | Measure to address terminal soil moisture | Dr T. Yellamanda Reddy |
| 7 | October-1st fn | Convergence planning | Planning for MGNREGS works | Y. Shanker Naik |
| 8 | October-2nd fn | Preserving seed | Seed collection and Storage | K. Padma and Jayram Killi |
| 8 | October-2nd fn | Preserving seed | Seed certification | Uttappa and Jayram Killi |
| 8 | October-2nd fn | Marketing | Marketing Options/Business Development | G. Chandrasekhar |
| 8 | October-2nd fn | Marketing | Market price Analysis | G. Chandrasekhar |
| 8 | October-2nd fn | Marketing | Aggregating produce, Exploring options for collective marketing | G. Chandrasekhar |
| 8 | October-2nd fn | Protective Irrigation | Protective irrigation-mobile irrigation | Dr T. Yellamanda Reddy |
| 8 | October-2nd fn | Harvesting and Post harvest | Protecting crop harvest from high rainfall | M.Subramanyeswar Rao and I. Murali |
| 8 | October-2nd fn | Second crop | Crop Planning | Jayram Killi |
| 9 | November-1st fn | Harvesting and Post harvest | Harvesting pulses | M.Subramanyeswar Rao and I. Murali |
| 9 | November-1st fn | Protective irrigation | Mobile irrigation | Dr T. Yellamanda Reddy |
| 9 | November-1st fn | Harvesting and Post harvest | Field Day | M.Subramanyeswar Rao and I. Murali |
| 9 | November-1st fn | Pest and Disease Management | Flower drop in Red gram | Dr T. Yellamanda Reddy |
| 10 | November-2nd fn | Harvesting and Post harvest | Harvesting | M.Subramanyeswar Rao and I. Murali |
| 10 | November-2nd fn | Crop Residue Management | Crop Residue Management | K. Padma |
| 10 | November-2nd fn | Second crop | Seed Sowing | Jayram Killi |
| 10 | November-2nd fn | Chick pea | Protective Irrigation | Dr T. Yellamanda Reddy |
| 11 | December-1st fn | Yield Estimation | Standing crop | Jayram Killi |
| 11 | December-1st fn | Rainfed Mango Orchard | Protective Irrigation to Mango | Dr T. Yellamanda Reddy |
| 12 | December-2nd fn | Harvesting and Post harvest | Harvesting | M.Subramanyeswar Rao and I. Murali |

Note: fn =fortnight

- Budget:

A detailed budget was worked out earlier by LTA and SPMU according to the approved cost norms. Few suggestions are given by the participants on the budgets.

- It is expected that for 1st year, FLAs would be organised for the present cropping period (Kharif 2018).

- Starting from July, the cropping period would remain till December

- Total number of FLAs to be organised is 12 during this 6 months of period

- On average 30 participants would participate in each FLA.

- Training to Master farmers and ToT to master trainers would be organised once in 3 months covering the content of 6 FLA sessions.

- There will be resource kit at each FLA. During the first year, Resource kit for farmers/ participants is not planned.

- Budget for Training 45 Master Trainers

- Number of bathes 2

- Number of participants/ batch: 22-23

- No of days/batch: 3

- No of rounds of trainings: 2 (one per every 6 FLAs)

- Place of Training: District (All residential trainings should be conducted where accommodation is available)

| Sl No | Particulars | 3 days Residential @ Dist |  |  | Amount |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Unit | Unit Cost |  |  |
| 1 | Food and Refreshment Cost (Participants + RP + Support staff | Participant | 950 | 20900 |  |
| 2 | Hall Rent and Logistics | 3 Days | 15000 | 15000 |  |
| 3 | Resource Persons Hon and travel | Res Person | 5100 | 5100 |  |
| 4 | Travel Allowance (S/DPMU, LTA, L/FA, FPO staff should claim travel from their project budgets) | Participant | 200 | 4400 |  |
| 5 | Stationary, Material, etc | Training Day | 1000 | 3000 |  |
| 6 | Night Stay | Participant | 700 | 15400 |  |
| 7 | Field Demonstration: Cost of travel and other | Lumpsum |  | 10000 |  |
| 8 | Honorarium to participants (Other than APDMP staff) @ Rs 300 per day | Participant | 900 | 15400 |  |
|  | Total |  |  | 63800 |  |

- Total Training cost of 1st batch (22 participants)		: 	Rs 93,600

- Total Training cost of 2nd batch (23 participants)		: 	Rs 96,350

- Total cost of 2 batches per round				: 	Rs 189,950

- Total cost for 3 rounds (6 trainings)				: 	Rs 3,79,900

- Budget for Training the Master Farmers 385 (approximately 25 in each batch)

- Number of participants/ batch: 25

- Number of bathes 15 (it would cover 375 participants)

- No of days/batch: 3

- Place of Training: District

| Sl No | Particulars | 3 days Residential @ Dist |  |  |
| --- | --- | --- | --- | --- |
|  |  | Unit | Unit Cost | Amount |
| 1 | Food and Refreshment Cost (Participants + RP + Support staff | Participant | 950 | 23750 |
| 2 | Hall Rent and Logistics | 3 Days | 15000 | 15000 |
| 3 | Resource Persons Hon and travel | Res Person | 5100 | 5100 |
| 4 | Travel Allowance (S/DPMU, LTA, L/FA, FPO staff should claim travel from their project budgets) | Participant | 200 | 5000 |
| 5 | Stationary, Material, etc | Training Day | 1000 | 3000 |
| 6 | Night Stay | Participant | 700 | 17500 |
| 7 | Field Demonstration: Cost of travel and other | Lumpsum |  | 10000 |
| 8 | Honorarium to participants (Other than APDMP staff) @ Rs 300 per day | Participant | 900 | 22500 |
|  | Total Cost/ Batch |  |  | 101850 |

- Total Training cost of 1 batch (25 participants)		:	Rs 1,01,850

- No of batches to cover 385 participants			:	Approximately 15

- Total cost of 15 batches per round (to cover content of 4 FLAs):	Rs 15,27,750

- Total cost of 15 batches training for 3 rounds (45 Trainings):		Rs 30,55,500

- Budget for Conducting FLA events (approximately 30 farmers in each event)

- Number of participants/ event/batch: 30

- Number of batches/Learning Site: 2

- Number of FLA events/batch in a year: 24

- Total number of events in each learning site per year: 48

- Number of Learning sites across APDMP: 105

- Number of events in all APDMP learning sites in a year: 5200 (48*105)

- Place of Event: Learning Site

| Sl No | Particulars | Unit | No of units | Unit Cost | Amount |
| --- | --- | --- | --- | --- | --- |
| 1 | Refreshment | Participant | 30 | 30 | 900 |
| 2 | Resource Fee | FLA | 1 | 600 | 600 |
|  | Total |  |  |  | 1500 |

- Total cost of 1 FLA (30 participants)					: Rs 1500

- Total cost of 2 FLAs in Learning Site per fortnight			: Rs 3000

- Total cost of 6 months*2= 12 FLAs in each Learning site/ Season	: Rs 36,000

- Total cost of FLAs in 105 sites					: Rs 37,80,000

- Cost of Experimentation budget/Learning site/Season @ Rs 7000/FLA Group: Rs 14000

- Cost of Experimentation in 105 Learning Sites/Season		: Rs 14,70,000

- Total Cost of conducting FLAs					: Rs 52,50,000

Discussion and decisions of meeting:

- All the core team members will prepare and submit allocated topics as training modules or material for FLA sessions by 30 July 2018

- LTA will consolidate training material received from the members by 7 August 2018

- Each LFAs will have to conduct 1st and 2nd FLA Session from 1st August 2018 onwards by involving their experienced team till training of master trainers is conducted at project level.

- Rs 10,000 of Cost for organising travel/exposure visit to the participants (both master farmers and master trainers) during training is included

- Rs 300/- of Honorarium to participants/day in training is fixed to attend training of master farmers and master trainers (Excluding to APDMP regular staff)

- Experimentation budget: Rs.7000/- per season (material, labor, experiment cost) are included for each of the FLA batch

- All the core team members are asked to submit list of Participatory experiment by 25th of July 2018

- The core team will finalise minimum of Six FLA session topics and communicate to LFAs who can decide based on local needs.

- Telugu Name of FLA is Raithu Badi

- Total budget required (Revised as per the discussions in core group meeting)

| # | Item | Unit Cost | Quantity | Amount |  |
| --- | --- | --- | --- | --- | --- |
| Budget 1 | Training of Master Trainers/Month batch | 189950 | 2 | 379900 | By LTA |
| Budget 2 | Training of Master Farmers/15 Batches @ 1 for 4 FLAs | 1527750 | 2 | 3055500 | By LFA |
| Budget 3 | Conducting FLAs/Month | 630000 | 6 | 3780000 | By FA |
| Budget 3a | Cost of Experimentation/Learning site/Season @ Rs 7000 per FLA group | 14000 | 105 | 1470000 | By FA |
| Budget 4a | Resource Material/Farmer wise | 3 | 75600 | 226800 |  |
| Budget 4b | Resource Material/Learning Site | 3000 | 105 | 315000 |  |
| Budget 5 | Resource Kit/FLA | 2000 | 210 | 420000 |  |
| Budget 6 | Resource Kit/Participant Farmer | 30 | 6300 | 189000 |  |
|  | Total |  |  | 98,36,200 |  |
|  | Provisioned in AWPB |  |  | 7700000 |  |

*************