AP Drought Mitigation Project

Guidelines for NRM Works in “Learning Site”

“పునాది క్షేత్రం”

The first workshop (from 9th to 12th January, 2018 at AF Ecology Center, Anantapuramu) with the NRM and Agriculture team  members of LFAs and FAs (of 4 LFAs) and DPMU resulted in a detailed planning exercise for the Learning Site.

The 2nd workshop with the LFAs, DPMU and SPMU teams based on the field plans prepared was organised on 22nd Feb, 2018 at Anantapuramu. The following guidelines emerged from the discussions collectively. These were facilitated by the LTA.

The project will not spend on

- Activities where mainstream programs budgets are already available

- Activities in saturation mode;

APDMP grants will be spent only to demonstrate successful interventions, pilot innovations and to mobilise demand. As convergence is one of the major objectives and success indicator of the project, funds for scaling up & for saturation of activities has to be mobilised from other mainstream programmes such as MGNREGS and also from various other departments which are working for the same objectives. This is generally followed as a guiding principle while LFAs plan/ recommend the plans for funding by APDMP.

What is “Learning Site” (“పునాది క్షేత్రం”)?

A 100 ha area (a sub-watershed) is to be identified by the community with support from FA. For the first year focused attempt will be made to take up comprehensive drought resilient measures in this area that includes taking up NRM works, year long farmer field schools ( a modified version), among others.

The following guidelines are evolved for the 1st round of work on the subject with 4 LFAs; these will be taken up by the DMPU for assessing the plans/ fund proposals recommended by LFA. The actual cost estimates are as per the watershed works that are in practice. This note sets the limits to which APDMP will invest.

Activities / Interventions for Demonstrations/ pilots that can be funded from APDMP grants:

- Soil Conservation Works:

  - This activity is encouraged to be mobilised from MGNREGS

  - Soil conservation works are much needed in the farms :

    - where tank silt is applied afresh and

    - fields with sever erosion.

  - If convergence efforts were not successful well before the Kharif season, APDMP may spend budgets as grant in such farms where tank silt is applied or those with severe soil erosion problem. (gully-heads).

  - The limit is set to a maximum of 20 acres to be invested from the project grants during the first year in the Learning Site. This is only applicable for first year of implementation; funds have to mobilised through convergence for rest of the period based on demand.

  - The cost norms are as same as MGNREGS

  - Cost-estimates with design has to be submitted along with proposal if this activity is proposed under APDMP grant.

- LINED FARM PONDS FOR PROTECTIVE IRRIGATION: These are taken up as a part of the planning for Protective Irrigation in the Learning Site. The plans have to provide details of the area to be protected through each of these farm ponds. Field level discussion is important to arrive at negotiated ways of farmers sharing the farm ponds (area and water). These must be for harvesting run-off water but not to store water pumped out of borewells. Must be lined in case of red-soils and necessary precautions taken to prevent seepage in case of other soils.

  - A maximum of 10 farm ponds with lining per each Learning Site to be taken up under APDMP funds.

  - These are only to be taken up in rainfed farms

  - Encourage existing farm ponds for lining; a maximum of 5 farm ponds

  - Recommended size of the farm pond is 10m x 10m x 2.5 m with 250 cum volume which can serve 4-5 acres @ 50 cum of water per irrigation for protecting rainfed crops from drought spells.

  - These 10 farm ponds’ digging can be taken up by machines

  - Upper limit of cost of each farm pond with lining with the above size is Rs.13,000 for digging and Rs. 9000 for lining for each farm pond (includes cost of cement and water). A detailed design and estimate will be shared by AF from their experience. Farmer has to contribute labor for lining.

  - If taken up from MGNREGS -the standard estimates as per MGNREGS norms will apply.

  - Standard estimate & design for farm pond with lining will be shared by  Accion Fraterna by 28th Feb’18.

  - AF will provide resource persons for demonstrating one complete farm pond lining per each LFA; the demonstrations have to be complete by April, 2018. LFA has to make all necessary arrangements including arranging for material before the resource person comes.

- Works related to Composing on farms & Residue management:

  - One compost pit per ha is recommended to start with; a pit of 4m x 3m x 0.5m = 6 cum volume. Biomass is filled up to 1 meter. This will give about 1.5 to 2.0 tons manure from each pit that can be applied in one acre. If the farmer is successfully managing it, it can be expanded to cover one pit per each acre in later years along with biomass plantation.

  - Each compost pit comprises of digging, planting (Glyricidia or other plans) around the pit to add biomass and give shade.

  - A maximum of 3 compost pits per farmer can be taken up under APDMP grant

  - Assess biomass availability before proposing Composting activity

  - The cost per pit (including one cycle of compost making) with dimensions 4m x 3m x 0.5 m  is Rs. 5,565/-. The cost includes pitting, biomass plantation and over turning; farmer has to source biomass and fill it.

  - The expected output is 1.5 to 2 tonns of Manure from each pit

  - A detailed estimation has to be submitted for approval under APDMP grant

- Tank Silt Application for soil improvement:

  - Proposed only for farms with poor soils; need to be taken up in convergence with MGNREGS. APDMP funds used only if all attempts to mobilise MGNREGS at district level did not succeed before May, 2018.

  - Maximum silt application with APDMP budgets to be taken up is for 50 acres in the learning site.

  - The cost of silt application per acre is up to Rs.6,500/- (Rs. 2,000/- for silt excavation with machine & filling tractors + Rs. 4,500/- after 50% farmer contribution for transportation and application in field).

  - Assess the quality of silt before applying; It is observed that applying farmyard manure/ compost along with silt is better for quick results.

- Deep Ploughing: Particularly in farm plots which have been uncultivated for some time, deep ploughing is useful to bring the lands back into cultivation. A provision upto 10 acres can be used for deep ploughing in the “learning site”.

- Provision of Supervision costs: For supervision of works implementation, a Community Resource Person (CRP) may be identified. On the job training may be provided for the identified CRP. One of the basic responsibilities of CRP is ensuring quality of works and required book / records keeping. For each learning site, up to  90 days of CRP cost @ Rs. 400 per day; if required.

After planning for NRM works, the FAs need to evolve the yearlong action plans for comprehensive drought resilience measures. This will be arrived at later.

See the Summary Table on Budget provision for NRM works in “Learning Site”. These are budget provisions to be used only in case convergence efforts did not succeed. The provisions are upper limits and the actual consolidated proposals from LFAs need to be based on actual areas on ground, design and estimates. The proposals must be accompanied by a map showing the details of various works. Data entry in the mobile application also need to be complete.

Summary of Budget Provision for NRM Works in “Learning Site”:

| Provision for Works Under APDMP in the “Learning Site” | Unit | Unit Cost | Farmer Contribution (%) | Farmer Contribution Amount (Rs.) | Amount after deducting Farmers Contribution (Rs.) | Number of units | Total Amount (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Soil conservation/ Farm Bunding | Acre | ₹7,700 | 0 | ₹0 | ₹7,700 | 20 | ₹1,54,000 |
| Farm ponds |  |  |  |  |  |  |  |
| Farm ponds with Lining | Number | ₹21,000 | Labor for lining | ₹0 | ₹21,000 | 10 | ₹2,10,000 |
| Lining of existing Farm ponds | Number | ₹9,000 | Labor for lining | ₹0 | ₹9,000 | 5 | ₹45,000 |
| Composting |  |  |  |  |  |  |  |
| Compost pits + Biomass plants + compost preparation (1 cycle per year) | Number | ₹5,565 | 0 | ₹0 | ₹5,565 | 25 | ₹1,39,122 |
| Tank silt application |  |  |  |  |  |  |  |
| Silt excavation & filling tractors | Acre | ₹2,000 | 0 | ₹0 | ₹2,000 | 50 | ₹1,00,000 |
| Transportation & field application | Acre | ₹9,000 | 50 | ₹4,500 | ₹4,500 | 50 | ₹2,25,000 |
| Deep ploughing | Acre | ₹1,600 | 0 | ₹0 | ₹1,600 | 10 | ₹16,000 |
| Sub total |  |  |  |  |  |  | ₹9,45,372 |
| Provision for Field supervision | CRP Day | ₹400 |  |  |  | 90 | ₹36,000 |
| Total |  |  |  |  |  |  | ₹9,81,372 |

Note: these are maximum budget provisions only; actual budgets must be arrived at based on field data.

** **