# Climate Resilient Agriculture Production Systems (CReAPS) Plan

Name of the District	: Kurnool 		Name of the Mandal	: C. Belagal

Name of the GP		: Budandoddi

Facilitating Agency: Centre for Sustainable Agriculture (CSA)

Lead Facilitating Agency: Centre for Sustainable Agriculture (CSA)

Submitted to:

State Project Management Unit, APDMP

Through

District Project Management Unit, APDMP

Date: 30th April 2018

Contents

1.	Learning site identification	6

1.1.	Name of the District : Kurnool	6

1.2.	Name of the Mandal : C. Belagal	6

1.3.	Name of the GP : Budandoddi	6

1.4.	Name of the village : Byatholi	6

1.5.	Facilitating Agency: Centre for Sustainable Agriculture (CSA)	6

1.6.	Lead Facilitating Agency: Centre for Sustainable Agriculture (CSA)	6

1.7.	Geographically location of the Learning Site (LS)	6

a.	Northern latitudes: 150 47' 07.88" N and 150 47' 49.97" N	6

b.	Eastern longitudes: 770 42' 42.57" E and 770 41' 53.68" E	6

c.	Survey of India (SOI) toposheet No: 57E/9	6

2.	Brief description of the Cluster	6

a.	List of habitations in the C. Belagal cluster	6

b.	Basic demographic description	6

c.	Basic bio-physical description	7

i.	Farmers details	7

ii.	Land use pattern	7

iii.	Crop details	7

iv.	Geographic location of the cluster	8

v.	Farmers wise land details	9

vi.	Category wise land area details in ha	9

3.	Brief Description of the GP where Learning site is located	10

4.	Process of selection of the Learning Site	10

a.	Important activities and dates	10

b.	Photo	11

c.	Resource map	12

d.	Gramapanchayat resolution	13

5.	Learning Site description	14

a.	Learning site Google map	14

i.	LMU boundaries	14

ii.	Farmer’s plots	15

iii.	 Cadastral map of the village	16

b.	Summary details of the Learning Site	16

6.	Land Management Units (LMU)	16

a.	Process of identification of the LMU	16

b.	Description of the LMU and their characteristics and area	17

c.	Drought vulnerabilities and critical constraints for production	17

7.	Thematic plans: Status and Strategic Plans on each theme for each of the LMU	17

7.a.	Theme 1: Soil health improvement of LMU of red soils	17

7.a.1.	LMU-1-Red Soils	17

7.a.1.1.	Situation Analysis of the LMU of red soils	17

7.a.1.2.	What are the Problems trying to solve	18

7.a.1.3.	What are the objectives to be achieved for this year	18

7.a.1.4.	What are the strategies for soil health improvement	18

7.a.1.5.	What are the activities planned as per the strategy for soil health improvement	18

7.a.1.6.	What are the budgets for each of the activity? How costs are shared across farmers investment, APDMP and convergence	19

7.a.2.	LMU unit-Saline soils	20

7.a.2.1.	Situation Analysis of the LMU of saline soils	20

7.a.2.2.	What are the Problems trying to solve	20

7.a.2.3.	What are the objectives to be achieved for this year	20

7.a.2.4.	Water are the strategies for soil health improvement	20

7.a.2.5.	What are the activities planned as per the strategy for soil health improvement	20

7.a.2.6.	What are the budgets for each of the activity? How costs are shared across farmers investment, APDMP and convergence	21

7.a.3.	LMU unit-Sandy loam soils	22

7.a.3.1.	Situation Analysis of  the LMU of sandy loam	22

7.a.3.2.	What are the Problems trying to solve	22

7.a.3.3.	What are the objectives to be achieved for this year	22

7.a.3.4.	Water are the strategies for soil health improvement	23

7.a.3.5.	What are the activities planned as per the strategy for soil health improvement	23

7.a.3.6.	What are the budgets for each of the activity? How costs are shared across farmers investment, APDMP and convergence	23

7.b.	Theme 2: Crop systems diversification and meeting seed requirements	25

7.b.1.	Situation Analysis of all LMUs	25

7.b.2.	What are the Problems trying to solve	25

7.b.3.	What are the objectives to be achieved for this year	25

7.b.4.	Water are the strategies for crop system diversification and seed requirement	26

7.b.5.	What are the activities planned as per the strategy for crop system diversification and seed requirement	26

7.b.6.	What are the budgets for each of the activity? How costs are shared across farmers investment, APDMP and convergence	27

7.c.	Theme 3: Protective irrigation for securing crops	27

7.c.1.	Situation Analysis of all LMUs	27

7.c.1.1.	Dry spells	27

7.c.1.2.	Groundwater resources	27

7.c.2.	What are the Problems trying to solve	28

7.c.3.	What are the objectives to be achieved for this year	28

7.c.4.	Water are the strategies for providing protection irrigation	28

7.c.5.	What are the activities planned as per the strategy for critical irrigation	28

7.c.6.	What are the budgets for each of the activity? How costs are shared across farmers investment, APDMP and convergence	29

7.d.	Theme 4: Natural farming/ ZBNF practices	30

7.d.1.	Situation Analysis of all LMUs	30

7.d.2.	What are the Problems trying to solve	32

7.d.3.	What are the objectives to be achieved for this year	33

7.d.4.	Water are the strategies for ZBNF	33

7.d.5.	What are the activities planned as per the strategy for ZBNF	33

7.e.	Theme 5: Farm implements/ mechanization for timely sowing	33

7.e.1.	Situation Analysis of all LMUs	33

7.e.2.	What are the Problems trying to solve	34

7.e.3.	What are the objectives to be achieved for this year	34

7.e.4.	Water are the strategies for farm implementations/mechanisation	34

7.e.5.	What are the activities planned as per the strategy for critical irrigation	34

7.e.6.	What are the budgets for each of the activity? How costs are shared across farmers investment, APDMP and convergence	36

8.	Map with LMUs and physical activities planned & other details with description	37

9.	Consolidated action plan for all the themes for the learning site (in table)	38

9.a.	Theme wise problems, objectives, strategies and action plan	38

9.b.	Consolidated activity plan	41

10.	Annexure: Detailed- pilot wise and/or farmer wise activity plans, with budget and source (APDMP/Convergence)	43

11.	Expected impact and monitoring indicators	43

11.a.	Describe theme wise and LMU wise	43

11.a.1.	Targets to be achieved in terms of activities: Targets in terms of farmers and area and numbers provided in the Section 7 in the Plan	43

11.b.	Workout the table:	43

11.c.	Monitoring Indicators	43

11.c.1.	Monitoring indicators for soil health	43

11.c.3.	Protective irrigation for securing crops	43

11.c.4.	Natural farming/ ZBNF practices	43

11.c.5.	Farm implements	44

# Climate Resilient Agriculture Production Systems (CReAPS) Plan

# Learning site identification

## Name of the District	: Kurnool

## Name of the Mandal	: C. Belagal

## Name of the GP	: Budandoddi

## Name of the village	: Byatholi

## Facilitating Agency: Centre for Sustainable Agriculture (CSA)

## Lead Facilitating Agency: Centre for Sustainable Agriculture (CSA)

## Geographically location of the Learning Site (LS)

### Northern latitudes: 150 47' 07.88" N and 150 47' 49.97" N

### Eastern longitudes: 770 42' 42.57" E and 770 41' 53.68" E

### Survey of India (SOI) toposheet No: 57E/9

# Brief description of the Cluster

## List of habitations in the C. Belagal cluster

| Sl. No | Gramapanchayat | Revenue village | Habitations |
| --- | --- | --- | --- |
| 1 | Burandoddi | Burandoddi | Buran Doddi |
| 2 |  |  | Byatholi |
| 3 |  |  | Krishna Doddi |
| 4 |  |  | Moran Doddi |
| 5 | Kambadahal | Kambadahal | Kambadahal |
| 6 | Bramhanadoddi | Brahmandoddi | Bramhana Doddi |
| 7 |  |  | Merugu Doddi |

## Basic demographic description

| Sl. No | Gramapanchayat | Male | Female | SC | ST | BC | OC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Burandoddi | 2790 | 2752 | 475 | 16 | 4690 | 361 |
| 2 | Bramhanadoddi | 1776 | 1682 | 704 | 0 | 2524 | 230 |
| 3 | Kambadahal | 1681 | 1739 | 593 | 16 | 2661 | 150 |

## Basic bio-physical description

### Farmers details

| Sl. No | Gramapanchayat | Male | Female | SC | ST | BC | OC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Burandoddi | 627 | 500 | 215 | 8 | 797 | 107 |
| 2 | Bramhanadoddi | 781 | 672 | 462 | 0 | 851 | 140 |
| 3 | Kambadahal | 576 | 113 | 152 | 8 | 482 | 49 |

### Land use pattern

| Sl.No | Particulars in ha | Burandoddi | Bramhanadoddi | Kambadahal |
| --- | --- | --- | --- | --- |
| 1 | Total cropped area in Kharif | 1476.3 | 1621 | 838.1 |
| a | Total Net Area Sown | 1312 | 1746 | 834 |
| b | Barren & Uncultivable land | 41 | 150 | 118 |
| c | Cultivable waste land | 153 | 174 | 42 |
| d | Other fallow lands | 10 | 332 | 834 |
| 2 | Total cropped area In Rabi | 377.9 | 731 | 202.7 |
| a | Forest Area | 0 | 0 | 0 |
| b | Land put to non-agriculture uses | 1205 | 898 | 0 |
| c | Permanent Pasture & Grazing land | 0 | 0 | 0 |
| d | Current fallows | 149 | 317 | 50 |

### Crop details

| Sl.No | Crops (Area in ha) | Varieties | Burandoddi | Bramhanadoddi | Kambadahal |
| --- | --- | --- | --- | --- | --- |
| 1 | Major crops in Kharif |  |  |  |  |
| a | Cotton | Bt Cotton | 420 | 198 | 220 |
| b | Ground nut | K6 | 210 | 289 | 135 |
| c | Castor | Hybrids | 190 | 231 | 190 |
| d | Red gram | Asha, LRG 31, PRG 100 | 142 | 702 | 119 |
| e | Others | - | 100 | 0 | 0 |
|  | Total |  | 1062 | 1420 | 664 |
| 2 | Major crops in Rabi |  |  |  |  |
| a | Ground nut | K 6, TMV 2 and Tag 24 | 45 | 160 | 70 |
| b | Bengal gram | Public sector | 195 | 60 | 30 |
| c | Sorghum | Private hybrids | 40 | 106 | 10 |
| d | Others |  | 70 | 0 | 55 |
|  | Total |  | 350 | 326 | 165 |

### Geographic location of the cluster

| Sl. No | Gramapanchayat | Revenue village | Habitations | Longitude | Latitude |
| --- | --- | --- | --- | --- | --- |
| 1 | Burandoddi | Burandoddi | Buran Doddi | 77°41'15.76"E | 15°47'12.77"N |
| 2 |  |  | Byatholi | 77°42'14.59"E | 15°47'5.19"N |
| 3 |  |  | Krishna Doddi | 77°41'22.46"E | 15°48'14.61"N |
| 4 |  |  | Moran Doddi | 77°43'3.00"E | 15°46'38.64"N |
| 5 | Kambadahal | Kambadahal | Kambadahal | 77°37'11.48"E | 15°49'46.05"N |
| 6 | Bramhanadoddi | Brahmandoddi | Bramhana Doddi | 77°43'2.43"E | 15°46'36.78"N |
| 7 |  |  | Merugu Doddi | 77°41'55.41"E | 15°46'19.39"N |

### Farmers wise land details

| Dry land farmers | Burandoddi |  |  |  | Total | Brahmanadoddi |  |  |  | Total | Kabandahal |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | SC | ST | BC | Others |  | SC | ST | BC | Others |  | SC | ST | BC | Others |  |
| Marginal Farmer* | 54 | 2 | 150 | 0 | 206 | 76 | 0 | 375 | 0 | 451 | 50 | 3 | 339 | 10 | 402 |
| Small Farmers** | 10 | 2 | 283 | 29 | 324 | 50 | 1 | 200 | 10 | 261 | 30 | 0 | 100 | 20 | 150 |
| Other Farmers*** | 14 | 1 | 100 | 35 | 150 | 13 | 0 | 50 | 30 | 93 | 0 | 0 | 10 | 20 | 30 |
| Total | 78 | 5 | 533 | 64 | 680 | 139 | 1 | 625 | 40 | 805 | 80 | 3 | 449 | 50 | 582 |
| Wet land farm | Burandoddi |  |  |  | Total | Brahmanadoddi |  |  |  | Total | Kabandahal |  |  |  | Total |
|  | SC | ST | BC | Others |  | SC | ST | BC | Others |  | SC | ST | BC | Others |  |
| Marginal Farmer* | 11 | 0 | 135 | 5 | 151 | 30 | 0 | 450 | 0 | 480 | 0 | 0 | 40 | 0 | 40 |
| Small Farmers** | 16 | 3 | 162 | 20 | 201 | 90 | 1 | 110 | 15 | 216 | 10 | 2 | 80 | 20 | 112 |
| Other Farmers*** | 9 | 0 | 67 | 10 | 86 | 10 | 0 | 70 | 25 | 105 | 0 | 0 | 0 | 0 | 0 |
| Total | 36 | 3 | 364 | 35 | 438 | 130 | 1 | 630 | 40 | 801 | 10 | 2 | 120 | 20 | 152 |

*: cultivation land less than 1 ha; **: cultivation land 1 -2 ha; ***: above 2 ha

### Category wise land area details in ha

| Dry land area | Burandoddi |  |  |  | Total | Brahmanadoddi |  |  |  | Total | Kabandahal |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | SC | ST | BC | Others |  | SC | ST | BC | Others |  | SC | ST | BC | Others |  |
| Marginal Farmer | 25.5 | 1.95 | 152 | 0 | 179.42 | 57 | 0 | 321 | 0 | 377.5 | 210 | 7 | 420 | 60 | 697 |
| Small Farmers | 12.8 | 3.41 | 263.1 | 56.2 | 335.59 | 115 | 2 | 400 | 50.5 | 567.2 | 160 | 0 | 387 | 60 | 607 |
| Other Farmers | 9.16 | 2.61 | 220 | 87.5 | 319.27 | 37.3 | 0 | 200 | 148.5 | 385.8 | 0 | 0 | 110 | 130 | 240 |
| Total | 47.5 | 7.97 | 635.1 | 143.7 | 834.28 | 209 | 2 | 921 | 199 | 1330 | 370 | 7 | 917 | 250 | 1544 |
| Wet land area | Burandoddi |  |  |  | Total | Brahmanadoddi |  |  |  | Total | Kabandahal |  |  |  | Total |
|  | SC | ST | BC | Others |  | SC | ST | BC | Others |  | SC | ST | BC | Others |  |
| Marginal Farmer | 14.2 | 0 | 115 | 3.41 | 132.57 | 22.1 | 0 | 526 | 0 | 547.6 | 0 | 0 | 50 | 0 | 50 |
| Small Farmers | 17.4 | 3.41 | 141 | 20.14 | 181.97 | 126 | 2 | 40 | 30.5 | 198.2 | 30 | 6 | 110 | 35 | 181 |
| Other Farmers | 11.4 | 0 | 75.41 | 11.73 | 98.52 | 32.3 | 0 | 360 | 50.5 | 442.8 | 0 | 0 | 0 | 0 | 0 |
| Total | 43 | 3.41 | 331.4 | 35.28 | 413.06 | 180 | 2 | 926 | 81 | 1189 | 30 | 6 | 160 | 35 | 231 |

# Brief Description of the GP where Learning site is located

- The Panchayat is falling in the Survey of India (SOI) toposheet no 57E/9., bounded between Northern latitudes 150 45' 25.61" and 150 48' 41.55" and Eastern longitudes 770 45' 01.99" and 770 41' 03.61".

- GP comprises of four villages such as Buran Doddi, Byatholi, Krishna Doddi, Moran Doddi.

- Total number farmers falls under LS is 122

- Croppig pattern of the LS: Karif Cotton inter crop with Redgram, Grounut intercrop with redgram. Rabi: Groundnut, Bengal gram and Sorghum. Farmers have access to public sector OP varieties and also cultivating private sector hybrids

- Predominant soils: Red soils and problematic soils (saline).

- Total seasonally functional bore wells of the LS are 34; farm ponds are14; seasonal open wells are 27; water storage tanks are 8; checkdams are 3.

# Process of selection of the Learning Site

## Important activities and dates

| Sl.No | Activity | Date |
| --- | --- | --- |
| 1 | Identification of village for learning site | 13th February |
| 2 | Focused group discussions | 3rd March |
| 3 | Meeting with village organizations | 3rd March |
| 4 | Meeting with opinion leaders | 3rd March |
| 5 | Street corner meetings | 3rd March |
| 6 | Secondary data collection | 4th March |
| 7 | Identification of LS | 4th March |
| 8 | Google map preparation | 5th March |
| 9 | PRA | 6th March |
| 10 | Farmer wise plots identification | 6th March |
| 11 | Transact walk in the farmers plots | 7th March |
| 12 | Situation analysis | 7th March |
| 13 | Farmer wise data collection | 7th to 12th March |

## Photo

## Resource map

## Gramapanchayat resolution

# Learning Site description

## Learning site Google map

### LMU boundaries

### Farmer’s plots

### Cadastral map of the village

## Summary details of the Learning Site

- Total area of the learning site is 265 acres including rain fed area is 198.23 acres and irrigated dry land is 66.77 Acres.

- Land type:  Red shallow soils, saline soils, low slope.

- Of the 122 farmers who belong to the learning site, 27 farmers (23%) are to SCs ,90 farmers (74%) are BCs and 4 farmers (3%) are OCs

- Of the 265 acres, 48.75 acres having SC farmers (19%), BC have 203.19 acres (77%) and 11.60 acres (4%) have OC community.

# Land Management Units (LMU)

## Process of identification of the LMU

- The learning site has been classified into 3 categories based on the soil type, texture and soil problem.

- Map of the learning site- ref 5.a.i

- These categories are classified in PRA exercise with farmers in participatory way

## Description of the LMU and their characteristics and area

| Sl.No | LMU type | Area in Acres | No. of farmers | Vulnerability |
| --- | --- | --- | --- | --- |
| 1 | Red soils | 90.71 | 53 | Low organic in carbon |
|  |  |  |  | Soil erosion |
|  |  |  |  | Low Soil fertility |
|  |  |  |  | Low Soil moisture holding capacity |
|  |  |  |  | Lack of sufficient irrigation source |
|  |  |  |  | Water scarcity for irrigation |
| 2 | Saline soils | 50.17 | 51 | Saline soils |
|  |  |  |  | Soils with gravel and subsurface rock |
|  |  |  |  | Lack of sufficient irrigation source |
|  |  |  |  | Water scarcity for irrigation |
| 3 | Sandy loam | 123.41 | 52 | Low organic carbon |
|  |  |  |  | Prone to soil erosion |
|  |  |  |  | Soil fertility |
|  |  |  |  | Low Soil moisture holding capacity |
|  |  |  |  | Lack of sufficient irrigation source |
|  |  |  |  | Water scarcity for irrigation |

## Drought vulnerabilities and critical constraints for production

- LMU 1 ( Red soils) :  Low soil carbon and water holding capacity, bed rock at 1 to 2 meters below ground level

- LMU 2 (Saline Soils) : Salinity (bondu choudu, Karu choudu, Banka coudu, Ganji choudu and erra choudu), barren for last 20 years,

- LMU 3 (Sandy loam) : Sand with pebbles, low soil carbon content, deeper water levels compared to red soils

# Thematic plans: Status and Strategic Plans on each theme for each of the LMU

# Theme 1: Soil health improvement of LMU of red soils

# LMU-1-Red Soils

# Situation Analysis of the LMU of red soils

- Shallow depth  with low water holding capacity and low fertility

- Texture of the LMU is silt and sandy

- Area under silt application has been increased.

- Application of Green manuring and GLM is almost negligible

- Cotton and red gram residues are burning in the field itself. Residues of Bengal gram and other pulse crops are mixing in the soils; and Leaves, stems are mixing in the FYM in the preparation of compost

- Two types of activities have been adapted for controlling of soil erosion in the LS like ploughing across the slope and deep ploughing

- Mono-cropping

# What are the Problems trying to solve

- Increasing soil fertility

- Control soil erosion

- Increasing soil moisture holding capacity.

- Changing in cropping pattern.

- Composting of crop residues.

# What are the objectives to be achieved for this year

- To increasing soil health in terms of soil organic content and soil fertility

- To control the soil erosion

- To Increase the soil moisture holding capacity.

- To diversify cropping pattern.

# What are the strategies for soil health improvement

- Tank silt Application

- Farm Yard Manure

- Bund plantation for bio mass generation

- Sheep penning

# What are the activities planned as per the strategy for soil health improvement

| Sl.No | Activities | Critical mile stones | Timeline | Responsibilities |
| --- | --- | --- | --- | --- |
| 1 | Tank silt application (As per the MGNREGS 50 cum per acre) | 74.8 Ac | May | FA |
| 2 | Compost Pit at field (6 cum (3*4*0.5 mts as per MG NREGS; @Rs 5565/pit including saplings) | 19 Nos | June-October | FA-Agri facilitator |
| 3 | Compost Pit at cattle shed (6 cum (3*4*0.5 mts as per MG NREGS; @Rs 5565/pit including saplings) | 13 Nos | June-October | FA-Agri facilitator |
| 4 | Bund Plantation at field ( As per the watershed programme Rs 2533 cum per acre including watering, watch and ward) | 59.49 Ac | June-July | FA-Agri facilitator |
| 5 | Sheep Penning (Rs 2000 per Acre; 1000 sheep flock/3 night | 24.56 Ac | May | FA-Agri facilitator |
| 6 | Bunding (As per the MGNREGS 80 cum per acre; Rs 86.22/Cum) | 59.49 Ac | June-Sep | FA-Agri facilitator |

# What are the budgets for each of the activity? How costs are shared across farmers investment, APDMP and convergence

| Sl.No | Activity | Units | Unit cost in Rs | Red soils-Amount in Rs |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | No of units | Farmer contribution | Convergence | APDMP funds | Total |
| 1 | Tank silt application (As per the MGNREGS 50 cum per acre) | Acres | 10728.95 | 74.8 | 0 | 802525 | 0 | 802525.46 |
| 2 | Compost Pit at field (6 cum (3*4*0.5 mts as per MG NREGS; @Rs 5565/pit including saplings) | Nos | 5565 | 19 | 0 | 105735 | 0 | 105735 |
| 3 | Compost Pit at cattle shed (6 cum (3*4*0.5 mts as per MG NREGS; @Rs 5565/pit including saplings) | Nos | 5565 | 13 | 0 | 72345 | 0 | 72345 |
| 4 | Bund Plantation at field (As per the watershed programme Rs 2533 cum per acre including watering, watch and ward) | Acres | 2533 | 59.49 |  | 466938 | 0 | 466938.372 |
| 4a | Sheep Penning (Rs 2000 per Acre; 1000 sheep flock/3 night | Acres | 2000 | 24.56 | 0 | 0 | 49120 | 49120 |
| 5 | Bunding (As per the MGNREGS 80 cum per acre; Rs 86.22/Cum) | Acres | 6898 | 59.49 | 0 | 410338.224 | 0 | 0 |

# LMU unit-Saline soils

# Situation Analysis of the LMU of saline soils

- Shallow depth  with low water holding capacity and low fertility

- Saline soils kept barren for last 20 years

- Most of the area is kept as fallow land

- Application of Green manuring and GLM is almost negligible

- Around 40% area is covered by sarkar thumma (prosopis juliflora)

- Part of area also consisting boulders and pebbles.

# What are the Problems trying to solve

- Decrease  soil salinity

- Increasing soil moisture holding capacity.

# What are the objectives to be achieved for this year

- To increasing soil health in terms of soil organic content and soil fertility

- To Increase the soil moisture holding capacity

- To reduce salinity of the soils

- To bring into cultivation.

# Water are the strategies for soil health improvement

- Tank silt Application

- Green manure

- Bund plantation for bio mass generation

- Sheep penning

- Millets and other suitable cropping pattern will be proposed.

# What are the activities planned as per the strategy for soil health improvement

| Sl.No | Activities | Critical mile stones | Timeline | Responsibilities |
| --- | --- | --- | --- | --- |
| 1 | Tank silt application (As per the MGNREGS 50 cum per acre) | 48.87 Ac | May | FA |
| 2 | Compost Pit at field (6 cum (3*4*0.5 mts as per MG NREGS; @Rs 5565/pit including saplings) | 9 Nos | June-October | FA-Agri facilitator |
| 3 | Compost Pit at cattle shed (6 cum (3*4*0.5 mts as per MG NREGS; @Rs 5565/pit including saplings) | 9 Nos | June-October | FA-Agri facilitator |
| 4 | Bund Plantation at field ( As per the watershed programme Rs 2533 cum per acre including watering, watch and ward) | 59.49 Ac | June-July | FA-Agri facilitator |
| 5 | Sheep Penning (Rs 2000 per Acre; 1000 sheep flock/3 night | 17.88 Ac | May | FA-Agri facilitator |
| 6 | Bunding (As per the MGNREGS 80 cum per acre; Rs 86.22/Cum) | 29.14 Ac | June-Sep | FA-Agri facilitator |

# What are the budgets for each of the activity? How costs are shared across farmers investment, APDMP and convergence

| Sl.No | Activity | Units | Unit cost in Rs | Red soils-Amount in Rs |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | No of units | Farmer contribution | Convergence | APDMP funds | Total |
| 1 | Tank silt application (As per the MGNREGS 50 cum per acre) | Acres | 10728.95 | 48.87 | 0 | 524324 | 0 | 524323.7865 |
| 2 | Compost Pit at field (6 cum (3*4*0.5 mts as per MG NREGS; @Rs 5565/pit including saplings) | Nos | 5565 | 9 | 0 | 50085 | 0 | 50085 |
| 3 | Compost Pit at cattle shed (6 cum (3*4*0.5 mts as per MG NREGS; @Rs 5565/pit including saplings) | Nos | 5565 | 9 | 0 | 50085 | 0 | 50085 |
| 4 | Bund Plantation at field ( As per the watershed programme Rs 2533 cum per acre including watering, watch and ward) | Acres | 2533 | 59.49 | 0 | 151747 | 0 | 151747.2 |
| 5 | Sheep Penning (Rs 2000 per Acre; 1000 sheep flock/3 night | Acres | 2000 | 17.88 | 0 | 0 | 35760 | 35760 |
| 6 | Bunding (As per the MGNREGS 80 cum per acre; Rs 86.22/Cum) | Acres | 6898 | 29.14 | 0 | 200996 | 0 | 200996.064 |

# LMU unit-Sandy loam soils

# Situation Analysis of  the LMU of sandy loam

- Shallow depth  with low water holding capacity and low fertility

- Texture of the LMU is sandy loam

- Area under silt application has been increased

- Application of Green manuring and GLM is almost negligible

- Cotton and red gram residues are burning in the field itself. Residues of Bengal gram other pulse crops are mixing in the soils; and Leaves, stems are mixing in the FYM in the preparation of compost

- Two types of activities have been adapted for controlling of soil erosion in the LS like ploughing across the slope and deep ploughing

- Mono-cropping

# What are the Problems trying to solve

- Increasing soil fertility

- Control soil erosion

- Increasing soil moisture holding capacity.

- Changing in cropping pattern.

- Composting of crop residues.

- Reducing salinity

# What are the objectives to be achieved for this year

- To increasing soil health in terms of soil organic content and soil fertility

- To control the soil erosion

- To Increase the soil moisture holding capacity

- To reduce salinity of the soils at parts of LS

- To diversify cropping pattern

# Water are the strategies for soil health improvement

- Tank silt Application

- Green manure

- Bund plantation for bio mass generation

- Sheep penning

# What are the activities planned as per the strategy for soil health improvement

| Sl.No | Activities | Critical mile stones | Timeline | Responsibilities |
| --- | --- | --- | --- | --- |
| 1 | Tank silt application (As per the MGNREGS 50 cum per acre) | 122.25 Ac | May | FA |
| 2 | Compost Pit at field (6 cum (3*4*0.5 mts as per MG NREGS; @Rs 5565/pit including saplings) | 20 Nos | June-October | FA-Agri facilitator |
| 3 | Compost Pit at cattle shed (6 cum (3*4*0.5 mts as per MG NREGS; @Rs 5565/pit including saplings) | 15 Nos | June-October | FA-Agri facilitator |
| 4 | Bund Plantation at field ( As per the watershed programme Rs 2533 cum per acre including watering, watch and ward) | 111.08 Ac | June-July | FA-Agri facilitator |
| 5 | Sheep Penning (Rs 2000 per Acre; 1000 sheep flock/3 night | 17.89 Ac | May | FA-Agri facilitator |
| 6 | Bunding (As per the MGNREGS 80 cum per acre; Rs 86.22/Cum) | 111.08 Ac | June-Sep | FA-Agri facilitator |

# What are the budgets for each of the activity? How costs are shared across farmers investment, APDMP and convergence

| Sl.No | Activity | Units | Unit cost in Rs | Red soils-Amount in Rs |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | No of units | Farmer contribution | Convergence | APDMP funds | Total |
| 1 | Tank silt application (As per the MGNREGS 50 cum per acre) | Acres | 10728.95 | 48.87 Ac | 0 | 1311614 | 0 | 1311614.138 |
| 2 | Compost Pit at field (6 cum (3*4*0.5 mts as per MG NREGS; @Rs 5565/pit including saplings) | Nos | 5565 | 20 Nos | 0 | 111300 | 0 | 111300 |
| 3 | Compost Pit at cattle shed (6 cum (3*4*0.5 mts as per MG NREGS; @Rs 5565/pit including saplings) | Nos | 5565 | 15 Nos | 0 | 83475 | 0 | 83475 |
| 4 | Bund Plantation at field ( As per the watershed programme Rs 2533 cum per acre including watering, watch and ward) | Acres | 2533 | 111.08 Ac | 0 | 281366 | 0 | 281365.64 |
| 5 | Sheep Penning (Rs 2000 per Acre; 1000 sheep flock/3 night | Acres | 2000 | 17.89 Ac | 0 | 0 | 35780 | 35780 |
| 6 | Bunding (As per the MGNREGS 80 cum per acre; Rs 86.22/Cum) | Acres | 6898 | 111.08 Ac | 0 | 766185 | 0 | 766185.408 |

# Theme 2: Crop systems diversification and meeting seed requirements

# Situation Analysis of all LMUs

- Cropping pattern in the learning site is varying periodically. Since last 30 years farmers have been cultivating single crop in kharif.

- 20 years back farmers use to cultivate Bajra, Jowar, Foxtail millets, Castor, Horse gram (own seeds).

- Over the period, Cropping pattern is shifted  Groundnut, sunflower and kusuma

- Present cropping pattern: Cotton, Redgram, Groundnut, Rabi jowar and Begnalgram. Cultivating private sector hybrids and public sector OPVs.

- Cropping pattern: Cotton inter crop with Redgram ( 6: 2);

- Cropping pattern gradually shifting from intercrop to mono-cropping

- Area under inter crop is reducing from 100 acres by 50 farmers to 30 acres by 20 farmers. There is no boarder crop practicing in the learning site.

- Due to climate change and frequent drought incidents vulnerability has been increased

Reasons for shifting crops

- Erratic rainfall

- Drought

- Lack of irrigation

- Increasing input amount

- Interest towards commercial crops

Constraints in accessing seed

- Timely availability and high price.

Constraints in preserving seed

- Seed quality and germination

# What are the Problems trying to solve

- Enhancing productivity by increasing soil fertility

- Availability of  local seed production and distribution system

- Climate resilient cropping system

- Mono cropping

# What are the objectives to be achieved for this year

- To increase soil organic matter

- To control the pest and diseases

- To Establish  Mana Vithana Kendram

- To make available community management seed system (CMSS)

- To make available local seed system

- To enhance quality and productivity of vegetables

# Water are the strategies for crop system diversification and seed requirement

- Establishment of Mana Vithana Kendram

- Establishment of Community Managed Seed System (CMSS)

- Farmer Field School

# What are the activities planned as per the strategy for crop system diversification and seed requirement

Seed production system will be established with the collaboration of agriculture department, supported by regional agriculture research station or agriculture research station. Local seeds will developed with concept of community based sees system which was developed by the Centre for Sustainable Agriculture (CSA); collaborate with the SERP, AP. These seeds will available at Mana Vithana Kemdram which will be established in the CLiC centre that will be established in the C. Belagal cluster.

| Sl.No | Seed | Red Soil |  | Saline Soils |  | Sandy loam soils |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Farmers | Area | Farmers | Area | Farmers | Area |
| 1 | Groundnut seed production | 4 | 4 | 1 | 1 |  |  |
| 2 | Millet seed production | 5 | 5 |  |  |  |  |
| 3 | Red gram seed production | 2 | 2 |  |  |  |  |
| 4 | Onion seed production |  |  | 1 | 1 |  |  |
| 5 | Onion Storage Structure | 2 | 4.2 |  |  |  |  |
| 6 | Vegetable Shade nets (With horticulture department contribution) | 2 | 2 |  |  | 1 | 1 |

# What are the budgets for each of the activity? How costs are shared across farmers investment, APDMP and convergence

| Sl.No | Variety of seed | Unit | No. of unit | Unit cost | Farmer contribution | Convergence | APDMP funds | Total amount |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Groundnut seed production | Acres | 4 | 4000 | 1600 | 16000 | 14400 | 32000 |
| 2 | Millet seed production | Acres | 5 | 1,000 | 500 | 5000 | 4500 | 10000 |
| 3 | Red gram seed production | Acres | 2 | 1,000 | 200 | 2000 | 1800 | 4000 |
| 4 | Onion seed production | Acres |  | 5,000 | 500 | 5000 | 4500 | 10000 |
| 5 | Onion Storage Structure | No | 2 | 175000 | 20933.264 | 104666.32 | 83733.056 | 209332.64 |
| 6 | Vegetable Shade nets (With horticulture department contribution) | No | 2 | 75000 | 75000 | 562500 | 112500 | 750000 |

# Theme 3: Protective irrigation for securing crops

# Situation Analysis of all LMUs

# Dry spells

Dry spells has experienced in stages at germination stage, pod/ fruit formation and maturity stage for the principal crops like cotton, groundnut, caster and red gram.

# Groundwater resources

In the learning about 31 bore wells and one open well is functioning for irrigation. First bore well was drilled in the year 2000. Depth of the bore well ranges from 120 feet to 300 feet whereas depth of the open well is 12 feet to 60 feet. Depth of the water levels in the bore wells ranges from 40 feet to 250 feet. One farmer is accepting to share the water to the neighboring farmer for 1 acre. Total 51.23 acres are cultivating under these well through flooding method.

# What are the Problems trying to solve

- Survival of crops during dry period

- Address scarcity of the water requirement of the crop

- Timely sowing of seeds

- Local seed availability

# What are the objectives to be achieved for this year

- To make available community management seed system (CMSS)

- To provide critical irrigation to the crops during drought period

- To Establish Mana Vithana Kendram

# Water are the strategies for providing protection irrigation

- Construction of lined farm ponds

- Repairing of existing farm pond

- Providing water use efficiency equipment

- Tank silt applications to the fields

# What are the activities planned as per the strategy for critical irrigation

| Sl.No | Activities | Critical mile stones | Timeline | Responsibilities |
| --- | --- | --- | --- | --- |
| 1 | Farm pond | 10 | June-November | FA-NRM facilitator |
| 2 | High speed motor for sprinklers | 10 | July | FA-Agri facilitator |
| 3 | Sprinklers | 9 | July | FA-Agri facilitator |
| 4 | Existing Dug well Rejuvenation (Deepening) | 5 | June | FA-NRM facilitator |
| 5 | Dried-up Bore well Recharge structure | 2 | June | FA-NRM facilitator |

| Sl.No | Intervention | Red Soil |  | Saline Soils |  | Sandy loam soils |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Farmers | No. of units | Farmers | No. of units | Farmers | No. of units |
| 1 | Farm pond | 10 | 10 | 1 | 1 | 1 | 1 |
| 2 | High speed motor for sprinklers | 3 | 3 |  |  |  |  |
| 3 | Sprinklers | 9 | 9 |  |  |  |  |
| 4 | Existing Dug well Rejuvenation (Deepening) | 1 | 1 | 3 | 3 | 1 | 1 |
| 5 | Dried-up Bore well Recharge structure |  |  |  |  | 2 | 2 |

# What are the budgets for each of the activity? How costs are shared across farmers investment, APDMP and convergence

| Sl.No | Work description | Unit | No. of units | Unit cost in Rs | APDMP project |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Farmer Contribution in Rs | Departmental Subsidy in Rs | Project Grant in Rs | Amount in Rs |
| 1 | Farm pond ( As per Dept of Ag scheme 45% Subsidy, 15% Farmer Contribustion, 40% APDMP grant) | No | 12 | 55000 | 82500 | 247500 | 220000 | 550000 |
| 2 | High speed motor for sprinklers | No | 3 | 15000 | 15000 | 0 | 135000 | 150000 |
| 3 | Sprinklers ( As Per APMIProject 90% subsidy, 5% Farmer Contri, 5% APDMP | No | 9 | 25000 | 11250 | 202500 | 11250 | 225000 |
| 4 | Existing Dug well Rejuvenation (Deepening), ( As per APDMP Design and estimate 10% farmer contribution, 90% APDMP grant) | No | 5 | 10000 | 3000 | 0 | 27000 | 30000 |
| 5 | Dried-up Bore well Recharge structure | No | 2 | 35000 | 7000 | 35000 | 28000 | 70000 |

# Theme 4: Natural farming/ ZBNF practices

# Situation Analysis of all LMUs

It is proved that cost of cultivation has been increased for applying pesticides and pesticides. ZBNF is a method which deal the reducing the cost by applying the organic pesticides and fertilizers from seed storage to harvesting. The present practices for addressing the pest management are shown in the table.

| Crop | Time line for pest | Seed Storage | After sowing | Seedling | Vegetative Growth | Flowering | Fruit formation | Maturity | Harvesting |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| All crops | Present practices | Put in godown, apply gamaxin | Root grub, Neem cake application | Hoppers, grubs application granules | Mites, Sucking pest control with bio extracts | Math (fly) control with pheromone traps | Pod control with insecticides Borer | Fruit & seed borer control with insecticides | Penku purugu control with gamaxin |  |
|  | Practices 10 years back | kept in a specific place apply gamaxin | Root grub neem cake application | Hoppers, grubs application granuls | Sucking pest control with bio extracts | Math control with trap crops | Pod control with insecticides Borer | Fruit & seed borer control with insecticides |  | Penku purugu its control with gamaxin |
|  | Practices 20 years back | Traditional practices for bugs | Root grub neem cake application | Hoppers, grubs application granuls | Sucking pest control with bio gamaxin | Math, control with trap crop | Pod control with insecticides Borer | Fruit & seed borer control with insecticides |  | Penku purugu its control with gamaxin |

| Crop | Timeline for diseases | Seed Storage | After sowing | Seedling | Vegetative Growth | Flowering | Fruit formation | Maturity | Harvesting |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| All crops | Present practices | Seed Treatment, Safe storage Places | Spraying Fungicides | Spraying Fungicides | Spraying Fungicides | Spraying Fungicides | Spraying Fungicides | Spraying Fungicides | Spraying Fungicides |
|  | Practices 10 years back | Kept in Clay Pots (Gade) in storage | Applied Fly ash | Applied Fly ash | Used Botanical extracts as fungicide | Used Botanical extracts as fungicide | Used Botanical extracts as fungicide | Used Botanical extracts as fungicide | Used Botanical extracts as fungicide |
|  | Practices 20 years back | Kept in Clay Pots (Gade) in storage | Application of Gomutram | Application of Gomutram | Used Botanical extracts as fungicide | Used Botanical extracts as fungicide | Used Botanical extracts as fungicide | Used Botanical extracts as fungicide | Used Botanical extracts as fungicide |

# What are the Problems trying to solve

| Crop | Issues | Seed Storage | After sowing | Seedling | Vegetative Growth | Flowering | Fruit formation | Maturity | Harvesting |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| All crops | Pest problems | Bugs, Seed borer, sulugulu attack, lack of awareness | Germination and pest control and lack of awareness | lack of awareness on seedling, moisture, germination | Deficiency of Nutrients, water, lack of awareness | Deficiency of micro nutrients, water deficiency lack of awareness | Nutrients deficiency, pest & diseases con lack of awareness | Micro nutrients, water deficiency lack of awareness | Penku purugu |
|  | Disease problem | Vittana kullu | Root trot | Yendu tegulu, Veru kullu | Yendu tegulu (blite) | Flower falling | Pod falling | Kaya kullu | Booju Tegulu |

# What are the objectives to be achieved for this year

- To reduce the cost of cultivation

- To encourage environment friendly practices in the agriculture

# Water are the strategies for ZBNF

- Trainings to the farmers for preparation organic pesticides and fertilizers

- Filed applications of the ZBNF practices

- Exposure visits to the progressive farmers’ fields

# What are the activities planned as per the strategy for ZBNF

| Sl.No | Activity | Practice |
| --- | --- | --- |
| 1 | Farmer Field school | Training-Learning by practicing |
| 2 | Seed Storage | Cow Urine treatment, Beejamrutham |
| 3 | After sowing | Jeevamrutha, Panchagavva, Amruthjalam, Neemastram, Bramhastram, Agnastram, Tulasi kashayam |
| 4 | Seedling | Jeevamrutham, Panchagavva, Amruthjalam |
| 5 | Vegetative Growth | Panchagavva, Botanical extracts |
| 6 | Flowering | Botanical extracts, Bio Fertilizers, micro nutrients |
| 7 | Fruit formation | Jeevamrutham, Panchagavva, Amruthjalam and Botanical extracts, micro nutrients |
| 8 | Maturity | Jeevamrutham, Panchagavva, Amruthjalam and Botanical extracts |
| 9 | harvesting | Safe harvesting method and manual |

# Theme 5: Farm implements/ mechanization for timely sowing

# Situation Analysis of all LMUs

| Sl.No | Operation | Equipment | Number available (own) | Number available (Rent) | Labor friendly (yes/No) |
| --- | --- | --- | --- | --- | --- |
| 1 | Plouging | Madaka | 20 | No | Yes |
| 2 | Preparation of Bode | Guntika | 25 | No | Yes |
| 3 | Land leveling | Papanaguntika | 22 | No | yes |
| 4 | Seed sowing | Seedler (Vittana Gorru) | 18 | No | Yes |
| 5 | Bullock cart | Transportation of crop Produce | 11 | Yes | Yes |
| 6 | Spraying of Pesticides | Sprayers | 51 | 15 | Yes |

# What are the Problems trying to solve

- Availability of  modern technologies

- Labour shortage in agriculture practices

# What are the objectives to be achieved for this year

- To reduce the time of cultivating activity

- To reduce cost of cultivation

- To overcome the agriculture labour shortage

- To encourage mechanisation in agriculture activity

# Water are the strategies for farm implementations/mechanisation

- Providing equipment to the CLiC centre

- Exposure visits to ARS and RARS

- Introducing new farm equipment

# What are the activities planned as per the strategy for critical irrigation

| Sl. No | Operation | Equipment | Number | Importance (high, medium, low) | Urgency (high, medium, low) |
| --- | --- | --- | --- | --- | --- |
| 1 | Seed treatment | Seed treatment Drum | 02 | High | High |
| 2 | Land Development, Tillage and Seedbed preparation Equipment | Tractor and its accessories/power tillers | 03 | High | High |
| 3 | Land Development , Tillage and Seedbed preparation equipment | Rotavator | 03 | High | High |
| 4 | Land Development , Tillage and Seedbed preparation equipment | Land Leveler | 03 | Medium | Medium |
| 6 | Sowing and planting equipment | Seed cum Fertilizer Drill | 03 | High | High |
| 7 | Sowing and planting equipment | Raised bed Planter/ Ridge Furrow Planter | 03 | High | High |
| 8 | Inter Cultivation equipment | Power weeder | 06 | Medium | Medium |
| 9 | Inter Cultivation equipment | Cycle weeder | 12 | High | High |
| 10 | Spraying purpose | Sprayers | 15 | High | High |
| 11 | Pulverizing | Neem Pulveriser | 03 | High | High |
| 12 | Leaf grinding | Grinder | 03 | High | High |
| 13 | Sowing | Seed Sowing equipment(Onion) | 09 | High | High |
| 14 |  | Vegetable Shade nets ( With horticulture department contribution) | 3 | High | High |
| 15 |  | Onion Storage Structure | 2 | High | High |

# What are the budgets for each of the activity? How costs are shared across farmers investment, APDMP and convergence

- 2 Tractor mound pump set @ cost of 40000; total cost is Rs 80,000 will be bear by the project

# Map with LMUs and physical activities planned & other details with description

# Consolidated action plan for all the themes for the learning site (in table)

# Theme wise problems, objectives, strategies and action plan

| LMU | Theme | Problem | Activity Planned | Objectives | Strategy |
| --- | --- | --- | --- | --- | --- |
| Red Soil | Soil health improvement | Deficiency of soil fertility | Tank silt Application | To increasing soil health in terms of soil organic content and soil fertility | Tank silt Application |
|  |  | Soil erosion | Green manure | To control the soil erosion | Green manure |
|  |  | Low soil moisture holding capacity | Bund plantation for bio mass generation | To Increase the soil moisture holding capacity | Bund plantation for bio mass generation |
|  |  | Mono cropping | Sheep penning | To diversify cropping pattern | Sheep penning |
|  |  | Management of crop residues | Composting | To increase soil fertility | Composting |
|  |  | Low organic carbon | Navadhanyalu | To Increasing organic matter in soil |  |
| Saline soils |  | Soil salinity | Tank silt Application | To increasing soil health in terms of soil organic content and soil fertility | Sheep penning |
|  |  | Low organic carbon | Green manure | To control the soil erosion | Tank silt Application |
|  |  | Soil erosion | Bund plantation for bio mass generation | To Increase the soil moisture holding capacity | Green manure |
|  |  | Deficiency of soil fertility | Composting; Sheep penning | To reduced salinity of the soils | Bund plantation for bio mass generation |
|  |  | Mono cropping | Navadhanyalu | To diversify cropping pattern | Composting |
|  |  | Low soil moisture holding capacity |  | To bring into cultivation |  |
| Sandy loam soils |  | Low organic carbon | Tank silt application | To increasing soil health in terms of soil organic content and soil fertility | Tank silt Application |
|  |  | Soil erosion | Compost Pit at field | To control the soil erosion | Farm Yard Manure |
|  |  | Deficiency in soil fertility | Bund Plantation at field | To reduced salinity of the soils | Green manure and composting |
|  |  | Low soil moisture holding capacity | Plantation at cattle shed | To Increase the soil moisture holding capacity | Bund plantation for bio mass generation |
|  |  | Mono cropping | Navadhanyalu | To diversify cropping pattern | Sheep penning |
|  |  | Salinity | Sheep Penning | Compost Pit at cattle shed | Develop convergence with line department |
| All Soils/LMUs | Crop systems diversification and meeting seed requirements | Drought resistant cropping system | Groundnut seed production | To increasing crop yield | Establishment of Mana Vithana Kendram |
|  |  | Local seed availability | Red gram seed production | To control the pest and diseases | Establishment of Community Managed Seed System (CMSS) |
|  |  | Mono cropping | Millet seed production | To Establish Mana Vithana Kendram | Farmer field schools |
|  |  |  | Onion seed production | To make available community management seed system (CMSS) | Develop convergence with line department |
|  |  |  | Vegetable shade nets ( With horticulture department contribution) | To make available local seed system |  |
|  |  |  |  | To enhance quality and productivity of vegetables |  |
| All Soils/LMUs | Protective irrigation for securing crops | Survival of crops during dry period | Sprinklers |  | Construction of lined farm ponds |
|  |  | Address scarcity of the water requirement of the crop | High speed motor for sprinklers | To provide critical irrigation to the crops during drought period | Repairing of existing farm pond |
|  |  | Timely sowing of seeds | Farm pond |  | Providing water use efficiency equipment |
|  |  |  | Rejuvenation of existing open well |  | Providing ittigation through mobile tanker |
|  |  |  | Lining of existing farm pond |  | Groundwater recharge |
|  |  |  | Mobile tanker |  | Develop convergence with line department |
|  |  |  | Dried up Bore well Recharge structure |  |  |
| All Soils/LMUs | Natural farming/ ZBNF practices | Low fertility of soils | Organic farming | To reduce the cost of cultivation | Trainings to the farmers for preparation of organic pesticides and fertilizers |
|  |  | Increasing cost of cultivation | Natural forming | To encourage environment friendly practices in the agriculture | Filed applications of the ZBNF practices |
|  |  |  |  |  | Farmer field schools |
|  |  |  |  |  | Exposure visits to the progressive farmers’ fields |
|  |  |  |  |  | Develop convergence with line department |
| All Soils/LMUs | Farm implements | Lobour shortage | Establishment of CLiC center |  | CLiC center establishment |
|  |  | Lack of knowledge on mechanization of the agriculture | Onion storage structure |  | Develop convergence with line department |

# Consolidated activity plan

| LMU | Theme | Activity | Time Line | Budget | Farmer contribution | Convergence | Project |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Red soil | Soil health | Bunding | July- September | 410338.224 | 0 | 410338 | 0 |
|  |  | Compost Pit at cattle shed(nos) | June -September | 72345 | 0 | 72345 | 0 |
|  |  | Compost Pit at farm (nos) | June - December | 105735 | 0 | 105735 | 0 |
|  |  | Sheep Penning (acres) | May | 49120 | 0 | 0 | 49120 |
|  |  | Bund plantation | July-August | 466938.372 | 0 | 466938 | 0 |
|  |  | Tank silt Application ( acres) | May | 802525.46 | 0 | 802525 | 0 |
| Saline soils |  | Bunding | May | 200996.064 | 0 | 200996 | 0 |
|  |  | Compost Pit at cattle shed(nos) | June-September | 50085 | 0 | 50085 | 0 |
|  |  | Compost Pit at farm (nos) | June - September | 50085 | 0 | 50085 | 0 |
|  |  | Sheep Penning (acres) | May | 35760 | 0 | 0 | 35760 |
|  |  | Bund plantation | July-August | 151747.2 | 0 | 151747 | 0 |
|  |  | Tank silt Application ( acres) | May | 524323.7865 | 0 | 524324 | 0 |
| Sandy loam |  | Bunding | May-June | 766185.408 | 0 | 766185 | 0 |
|  |  | Compost Pit at cattle shed(nos) | June-December | 83475 | 0 | 83475 | 0 |
|  |  | Compost Pit at farm (nos) | June-December | 111300 | 0 | 111300 | 0 |
|  |  | Sheep Penning (acres) | May | 35780 | 0 | 0 | 35780 |
|  |  | Bund plantation | July-August | 281365.64 | 0 | 281366 | 0 |
|  |  | Tank silt Application ( acres) | May | 1311614.138 | 0 | 1311614 | 0 |
| Red soil | Crop and seed | Groundnut seed production | June- December | 32000 | 1600 | 16000 | 14400 |
|  |  | Millet seed production | June - December | 10000 | 500 | 5000 | 4500 |
|  |  | Red gram seed production | June-Jan | 4000 | 200 | 2000 | 1800 |
|  |  | Onion Storage Structure | Sept -Jan | 175000 | 17500 | 87500 | 70000 |
|  |  | Vegetable Shade nets (With horticulture department contribution) | June | 750000 | 75000 | 562500 | 112500 |
| Saline soils |  | Onion seed production | June to Nov | 10000 | 500 | 5000 | 4500 |
|  |  | Groundnut seed production | July- September | 8000 | 400 | 4000 | 3600 |
| Sandy loam |  | Vegetable Shade nets (With horticulture department contribution) | May | 375000 | 37500 | 281250 | 56250 |
|  |  | Onion Storage Structure | July-September | 175000 | 17500 | 87500 | 70000 |
| Red soil | Protective Irrigation | Existing Dug well Rejuvenation (Deepening) | June | 10000 | 1000 | 0 | 9000 |
|  |  | Farm pond | May to June | 550000 | 82500 | 247500 | 220000 |
|  |  | High speed motor for sprinklers | June to Nov | 150000 | 15000 | 0 | 135000 |
|  |  | Sprinklers | August to Jan | 225000 | 11250 | 202500 | 11250 |
| Saline soils |  | Existing Dug well Rejuvenation (Deepening) | June | 30000 | 3000 | 0 | 27000 |
| Sandy loam |  | Existing Dug well Rejuvenation (Deepening) | June | 10000 | 1000 | 0 | 9000 |
|  |  | Dried up Bore well Recharge structure | June | 70000 | 7000 | 35000 | 28000 |
|  |  | Total |  | 8093719.292 | 271450 | 6924809.292 | 897460 |

# Annexure: Detailed- pilot wise and/or farmer wise activity plans, with budget and source (APDMP/Convergence)

- Details send through email

# Expected impact and monitoring indicators

# Describe theme wise and LMU wise

# Targets to be achieved in terms of activities: Targets in terms of farmers and area and numbers provided in the Section 7 in the Plan

# Workout the table:

# Monitoring Indicators

# Monitoring indicators for soil health

- Percentage of increase soil moisture content through measuring the soil moisture: no. of samples, soil health card, MIS

- Tank silt application: records of soil tractors used, record of volumetric measurement of silt excavated, photographs, soil health card, convergence report of FA and department

- Quantity of bio mass, record of MB, soil health report

- Bund plantation along field bunds, convergence report

- For all works: availability of Audio visual aids

    - Monitoring indicators of Crop systems diversification and meeting seed requirements

- Area of crop diversification

- FPO business records

- No. of crops increased in the village

- Variety of local seeds available in the village

# Protective irrigation for securing crops

- Records of area protected through providing critical irrigation

- Records of estimation of water requirement for crops

- FPO records

# Natural farming/ ZBNF practices

- Area of ZBNF practises

- No. of individuals preparing  organic pesticides

# Farm implements

- No. of farmers access implements from CLiC centre

- FPO records

- Amount of service charges collected

- Assets record of at CLiC centre

# Institution Assessment:

- brief report on FPO formation

- Details of the FPO; registration number, date of registration, no. of members, share capital, Bank and bank account details, names and contact info of the key office bearers