## Slide 1: Presentation on
Participatory Planning Module on ‘Climate Resilient Rainfed Agriculture in the “Learning Site”
S.S.Kandagal
LTA -WASSAN

## Slide 2: Participatory Planning Module on ‘Climate Resilient Rainfed Agriculture in the “Learning Site”
Identify the proposed areas through Participatory Rural Appraisal (PRA) exercises-100 ha
A ‘Learning Site’ of around 100 ha area in each cluster of 3 Gram Panchayats
Check list for PRA

## Slide 3: Planning Teams:
From LFA
Water Management Specialist/Engineer and NRM
Agronomist/Crop-Horticulture Specialist
Livestock Production and CPR Specialist
From FA
Water resources development & NRM
Agriculture Facilitator
Livestock Facilitator and CPR

## Slide 4: Pre-Requisites:
The ‘Learning Site’ (of 100 ha area)in the form of a sub-watershed is identified and its borders are delineated on map (cadastral and Google Earth (GE) map). Guidelines for selection of “Learning Site” is at Annexure-1
Physical copies of the maps (cadastral and Google earth) are available; preferably the Google Earth map printed on a larger size flexi sheet.
The names of the farmers in the Learning Site are listed along with their Aadhar numbers.

## Slide 5
Objectives of the Planning Exercise:
The participatory planning exercise results into a comprehensive climate resilient and growth plan for the learning site.
Outputs:
Capturing the baseline situation including analysis of issues
Prepare an action plan that is commonly agreed by the farmers with budgets and detailed activities.

## Slide 6: The Planning Exercise is split into the following Sub-Plans:
Soil health improvement
Protective irrigation plans including soil moisture conservation
Cropping systems diversification and developing seed security
Zero Budget Natural Farming (ZBNF)
Increasing access to Agriculture Implements and Farm Machinery

## Slide 7: Planning Exercise 1 Preparation of a Base Map
  Identify the proposed areas through Participatory Rural Appraisal (PRA) exercises. 100 ha of Learning site should be identified using the criteria. This criteria and process of conducting PRA to identify the learning site is provided at Annexure-1.
  Identify the area on the Google Earth (Pro version). Save the image and take print out in maximum view possible.
    Open Google Earth Pro version
    Spot the location in Google Earth.
    Enlarge the view to the desired size
    Save the area: Go to File >> Save >> save image as >>Select Maximum from Resolution (Next to search) >> Click Save image >> Save as JPEG
    Take the print out on A0 size sheet (For better view, take the color print)
  Start at one known point/landmarks and mark the plots of adjoining farmers. The area should be fixed based on the transact walk made and fields visited.
  Simultaneously, use cadastral maps to check the farmers and survey numbers. The cadastral features can be overlaid later onto GIS platform.
  Facilitate for identification of some land mark and proceed further with each plot. Each plot can be given numbers (1, 2,….)
  Prepare the details of farmers in following table
Columns in the table will be expanded. This table will be used in subsequent exercises too..

## Slide 8: Planning Exercise #2: Improving Soil health
Soil Health Improvement Plan Process Steps:
Start with the Base Map and Table in which LMUs are delineated with details. All the discussions and plans should be done for each LMU.
Explore on Soil Testing:
  Are there any soil test results available for the area? If yes, gather the Soil Test card results and compile them including survey numbers.
  Summarize major observations from soil test results? Discussion & report.
    Status of organic carbon?
    Status of Macro nutrients
    Status of micro nutrients
What are the recommendations?
Present Practices, Strategic plan in the LMU and Farmer wise detailed plan:
(Ask the Key Questions for each of LMU after brief input session)
  Application of Manure
Present Practices
  What are the trends in application of manure? In these 10 years, 10 years before, 20 years before?
  What types of manures are applied? What is the quantity? To which type of soils?
  Any practices in composting? If yes, what are they?
    At household level
    At cattle/ animal sheds
  Did you apply compost to the lands in this LMU?
StrategicPlan
  What activities need to be taken up in the area?
    In situ composting
    Composting at homesteads or cattle/ livestock sheds
    Others? (option – get the numbers and location after consulting the individual farmers?)
Detailed Plan(No of farmers and extent in Acrs)
  Who wants to apply the manure? To which plot? How many acrs?
  Where do you want to produce it? What is the cost, how much can you contribute?
Farm Yard Manure, Compost, Vermi Compost

## Slide 9
  Tank Silt Application
Present Practice
  Was there a practice of Tank Silt application?
  When was it last done? And by how many farmers; how many acres?
  What are the sources for tank silt, if needed;
  Source – Distance – quantity available (sufficient/ moderate / very less)?
  Is the Tank silt quality good?
Strategic Plan (this can be done by a small sub-group or committee)
  Source of tank silt (assure quality)
  Distance
  Modalities of tractors for transport
Detailed Plan
  Name of the farmer
  No of trips
  Contribution and cost sharing per trip

## Slide 10
  Soil Erosion control Works
Present Practices
  Were soil conservation works taken up in the “learning site”?
  If yes, when, under which scheme?
  What is the status of these works?
  Which works are more qualitative? Why?
  Do farmers retain bunds or plough them off?
  Map the active erosion locations in the 100 ha area; where it is very important to have conservation works to prevent larger erosion.
    In Streams and common lands
    In agriculture lands
Strategic Plan
  What are the most preferred and suitable works/interventions for soil conservation
  How many farmers? How many acrs?
Detailed Plan
  Who are the farmers need soil conservation or erosion control works?
  What is the cost? What is the farmers’ contribution?
  What is the source of scheme?

## Slide 11
  Crop Residues Management
Present Practices
  What happens to crop residues? Are they burnt or mixed into soil? If both practices are there, roughly in what % of area crop residues are burnt?
  Are farmers familiar with Rotovators? Should they be used?
  Are rotovators available in the village for hiring?
  What are the rental value and payment practices?
Strategic Action Plan
  Campaign to STOP Burning Crop Residues
  Methods of mixing crop residues into soils
  If not, should it be available at CLiCs- Custom Hiring Center?
  Rental value
Detailed Plan: Farmer wise action plan with budgets and sources

## Slide 12
  Biomass Plantation on Bunds
Present practices
  Was/ is there any practice of biomass plantation on bunds/ commons and adding
  Are there any other practices for adding biomass to the soils?
Strategic Action Plan
  What kind of biomass plants are needed?
  Are there readily available in any nearby nursery? What is the distance? Who is maintaining/running the nursery?
Detailed plan: Farmer wise action plan with budgets and sources

## Slide 13
Possible Action Plans/Points
Soil testing
Activities for development of problematic soils
Activities for improvement of soil fertility
Activities for production of compost
Activities for controlling soil erosion
Tank silt application
Raising nursery for biomass preparation
Seed dibbling on bunds for Biomass
What are the other practices in your experience…….

## Slide 14: Planning Exercise on Component #2: Water and Protective irrigation
Process:
Exploration
Mapping Water Resources in the Learning Site:
  Use the Base Map with drainage lines
  Map water bodies on the map:
    drainage lines, checkdams, tanks, ponds and other water bodies. Note for each water body:
    Map the borewells and open wells
    Number each water body (surface and groundwater)
  For each waterbody (surface and groundwater) ask for the following:
    Ownership (name of owner(s) & private or common)
    Last month of water availability (i.e. when it dries up?).
Mapping Irrigated Areas and Crops irrigated
    Name of the crop and extent of area presently irrigated by each water body, both for kharif and Rabi (also, map the plots irrigated on the map).
    Irrigation practices used in each water body: flood flow, channels, sprinklers, drips
When do drought spells occur? (Types of droughtspells)
    On a calendar (15 days interval from 15th May to 31st Dec) mark the perception of droughtspells (of about 10 days & of about 15 days); i.e. when does drought spell of these two durations occur.
- At sowing time
- during crop growth
    Map/ list the water bodies (surface and groundwater) where water is available during the period.

## Slide 15
Arriving at Strategic Plans:
Planning for Protective Irrigation from Existing Sources
    For each LMU area (numbered) identify sources of protective irrigation on the map.
    Assess if the water bodies will have water during the stage.
Provide Inputs on Protective Irrigation Options: (Use Flip Chart on Protective Irrigation)
    Ensuring Timely Sowing: (show the photographs/ flip chart slides)
      Option 1: Row wetting and seeding. If the forecast is not very negative and when rains are expected within 10 to 15 days; instead of losing the season – farmer can sow row crops like redgram by applying water. Aquaplanter – for groundnut for e.g. enables it.
      Option 2: Tanker providing irrigation attached with a plough (seeding).
    Protective Irrigation with Lined Farm Ponds:(discussion with photographs)
      Each farm pond of size 10 m x 10m x 2.5 m = 250 cu.m volume
      5 acres x 100 mm rainfall
      5 acres x 4046 sq.m/ac x 100/1000 meter rainfall = 2023 cu.m rain water.
      Of this even 20% is runoff = 404 cu.m of runoff water that can be collected into farm ponds. This is more than one filling of the farm pond. Experience suggests that such farm ponds (1 in 5 acres drainage area) can fill 2 to 3 times during a season depending on rainfall.
    Water lifting devises & Diesel / electric Pumps:
    Mobile Protective Irrigation:
      Water can also be transported within limited/ economic distances. Explore if such options exist. There are 2 possibilities:
          Pumping from any water source – tank / borewell / open well and irrigating using sprinklers/ drips.
          Filling in a tanker from a water source and transporting to the field.
      Arrive at number of sprinklers, pipes, pumps etc., required to be placed at the Custom hiring Centers (CLiCs). This also includes aquaplanters.

## Slide 16
Plan for Farm Ponds:
    Mark best locations for farm ponds on the map; along with the names of farmers and plot numbers.
    Since every plot can’t have farm ponds; agreements have to be reached among neighboring farmers on water sharing from farm ponds.
    Site verification and farmers’ consent (including on contribution) to be taken later.
    How do we prioritize the farm ponds as the total budget available for this purpose is limited. (one way is to allocate within LMUs).
    Arrive at the list of prioritized farm ponds

## Slide 17
Explore Possibilities of Groundwater Collectivisation:
    Explain about groundwater collectivization.
    If there is potential, this can be taken up separately.
    Get the farmers and area that they would like to bring under collectivization.
Establishing a Rain-guaze:
    For monitoring rainfall, drought spells etc., it is important to install a rainguage (even a low cost one) at the FFS sites. This along with weather forecasts help in arriving at decisions on protective irrigation for each LMUs.
    Identify location, who takes responsibility of recording etc.
Drinking Water for Livestock:
    Mark the normal livestock tracks passing through the “Learning Site”
    Plan and provide for a water trough (with small height for small ruminants) that can be filled with a borewell (or other source) for livestock drinking water.

## Slide 18
Summary of the Protective Irrigation Plans:
    The LMUs marked on the map (numbered) with their drought vulnerability status.
    Plan (source) of protective irrigation for each numbered LMU.
    How many LMUs are covered and how many not covered? Reasons for non-coverage.
    LMU wise sources for protective irrigation & agreement of the group (and consent for the farmer on sharing water).
    Sharing agreements and consent letters from farmers on water sharing.
    What are the protective irrigation related equipment required? Norms for their use.

## Slide 19: Planning Exercise on Component #3: Crop Systems and Seed
Overall Purpose: Plan for diversifying the crop systems to increase climate resilience and
Specific Purpose:
Mapping existing agronomic practices specific to crop systems, patterns and seed availability
Planning the options to increase climate resilience through reducing diversifying crops
Create necessary support systems (seed and information)
Process:
Exploration
  Mapping Past and present crop systems and management practices
    Ask the farmers to list the crops during this 10 years, 11-20 years and 21-30 years
    What is the reason for adapting this cropping systems? What are the advantages?
    What are the reasons for quitting the previous crop systems
    Is it good for soil health?
    Does this consume less water?
    Is it climate resilient?
    Is it reducing cost of cultivation?
    What is the net income?
  Ask the farmers about options to utilize the rainfall throughout the year
  Ask the farmers options to get most from the land
    Food grains
    Fodder
    Soil Biomass
    Expanding the duration of soil cover, etc

## Slide 20
Arriving at Strategic Plans
  Is the present cropping system drought resilient and most economical?
  What is the spread of rains in a year
  Can we diversify the crops to utilize rainfall available throughout the year to cover soils, to get more crops in a single season?
    What crops can be mixed (straight growing/erect, bushy, creepers, etc)
    Provide information on alternative crops
    Share experiences from other villages (photos, charts and videos)
  If yes, what do we do?
  If not, why?
  What needs to be done to reduce the loss, increase income, food grains, fodder, etc.
  Seed production
    What seeds are available?
    What seeds need to be produced?
Volunteering farmers to take up “seed production” and supply seed locally

## Slide 21: Arriving at Detailed Plans
  List of interested Resource farmers: Identify 2-3 resource farmers and learning plots for FFS
  Identify the farmers who would adapt Climate resilient cropping systems

## Slide 22: Planning Exercise on Component #4: ZBNF
Overall Purpose: Plan for promoting sustainable agriculture practices in ZBNF model through four key practices:
Extension by a practicing resource farmer
Dissemination of knowledge and handholding in practice using community video
Establishing an NPM shop
Organizing farmers
Specific Purpose:
Mapping existing agronomic practices specific to Pest/ Disease management and Soil Fertility Enhancement
Planning the options to increase climate resilience through ZBNF practices
Create necessary support systems
Process:
Exploration
  Mapping crop wise pest problems and management practices
    Ask the farmers to list the major crops on a chart paper
    Map the major pest and diseases related problems at every stage (But the pest and disease information should be captured in separate tables)
    Capture existing practices to manage pests and diseases
  Mapping Crop/Land wise soil fertility related practices
    Mapping application of chemical fertilizers
    Mapping application of compost practices

## Slide 23
Arriving at Strategic Plans
  Is your problem solved by chemical pesticides?
  Can we shift to ZBNF practices, this year onwards?
    Provide alternative/climate resilient ZBNF practices using flip charts and videos
  If yes, what do we do?
  If not, why?
  What needs to be done for improving soil fertility, pest and disease control
Arriving at Detailed Plans
  List of interested Resource farmers: Identify 2-3 resource farmers and learning plots for FFS
  Identify the farmers who would adapt ZBNF practices

## Slide 24: Planning Exercise on Component #5: Implements and Farm machinery
Purpose:
To assess the existing practices in using farm implements for different purposes
To assess the need-demand-availability-gap
To assess the scope for establishing a custom hiring centre
Exploration
What is the equipment not available with you, therefore you are missing the timely operations?
        What are the ways and means to reduce drudgery on labour or women?
What do you do if the material is not available or scarce?
Is equipment available on rent? If Yes, what are they? What is the rent?
      Is it accessible to you? What do you do if the service/hiring cost is higher?
Which type of crop operation, the existing farm equipment is not appropriate?
  Land preparation
  Seed sowing
  Weeding
  Inter cultivation
  Providing irrigation
  harvesting
  Cutting residues
  Postharvest processing
Do you know what is the appropriate equipment?