## Sheet1
Process steps and timeline for setting up of Climate Information Centres
S.No | Process step | Activity | Persons responsible | Requirements | Timeline
1 | Identificaton of CLIC villages | APPI team identify suitable village for the project/CLIC |  | Project objectives
2 | Identificatio n of CLIC centre Building | APPI team identify suitable building for CLIC |  | Room which can accomodate 10-15 members in GP or any community centre. It should have electricity connection, should have proper security locking system. Room should be separte and it should not common hall to avoid damage/theft of electronics
3 | Indenting compute,electronic,furniture for CLIC | APPI team indent electronics/furniture |  | CPU, 32" LCD monitor,Keyboard, Mouse, Inverter, Battery for backup, public addressing system( amplifier, mouth piece, 2 loud speakers, Table with lockable desks, chair, rain guage, rainfall grapg flex, registers(3)
4 | Identification/selection of CLIC operators | APPI team identify and recruit CLIC operators |  | He/she should be from local village with farming background, having atleast intermediate qualification, knowing computer operation is essential.
5 | Meeting with Farmer groups/federations regarding CLIC management and ownership | APPI team organise village level meeting with GP body or farmer group or federation on how-to-manage CLIC centres. |  | APPI team should consult members/stakeholders and educate on CLIC centres, also on essentials of ownership and managment.
6 | Procuring CLIC computer,electronics,furniture | APPI team place an order for CLIC computer,electronics, furniture etc. |  | Purchasing, payments, shipment etc
7 | Setting up CLIC centres | Wassan computer expert install computers and other electronic devices |  | Local electrician, wirings, boards, wassan computer expert
8 | Training for CLIC operators | Three day residential training program on computer basics ,CLIC operation and weather data managment |  | Trainin g facilities, computers and accomodation at Parigi LRC
9 | Inuaguration | APPI team inuagurate CLIC centres . |  | APPI team invite local leaders, CBOs, farmers and press