# Modalities for Establishment of the FPO Office with CLiC facilities

The FPO office with CliC or Foss (Farmer one stop shop) or Rythu Seva Kendra location, should be strategically selected to ensure the centre would have maximum footfall and would cater to the requirements of the people in the cluster. The factors that should be taken into consideration while establishing the centers are stated below

- SELECTION OF VILLAGE

    - The village selected, should be centrally located  to all  the villages in the cluster

    - Proximity to market place should be considered

    - The selected village should have strong community participation with ownership of the FPO and villagers

    - The identified village should have good Transportation facility, along with road connectivity (accessible to various habitations within the cluster and from outside).

    - FPO board members (and representatives from various habitations) should agree upon the selection of Village

    - Gram Panchayat acceptance for the location (so that they are adequately informed)

    - The ideal location is if the Gram Panchayat allocates required space with nominal or no charges  (subject to other conditions fulfilled).

- CLiC CENTER :

- The Center should be facing the road/ market place, as this would increase its visibility.

- The Centre must have 3 functional spaces/ rooms

- A room for conducting meetings amongst FPO members

- A room for CLiC counter shop

- A room for CHC equipments

- Open space at the back of the building, would be ideal, as it would be used for storage of equipments and related material

- Rent for the premises should ideally be around Rs.5000 per month as the  FPO would have to meet rental expenses post two years of establishment of the CLiC centre. If GP or a local donor provides premises free of cost or at lower cost, it would be ideal.

- Location identified for establishment of CliC’s/FPO office should be free from any Political bias or interference – i.e. politically and culturally acceptable to all.

- Lease agreement with the owner has to be signed and the  tenure for the lease should be at least 3 years

- SHOP OUTLET:

- It has to be facing the  market / road in order to ensure higher visibility and scope for increased footfall

- Adequate space for display of material/ information in front of the shop and storage space internally.

- Some parking place on the road/ nearby

- Security is important

- MEETING ROOM:

- In addition to the shop outlet, a room size larger than  (10 x 13) feet is necessary for  the Meeting Room

- The room should be able to accommodate 15-20 people

- A wall visible to all,  wherein a  large TV (about 52 inches) can be mounted

- Space for Almirah and a refrigerator

- STORAGE ROOM (CUSTOM HIRING)/ SHED:

- Storage room should have space for storing equipments/materials: Backyard space to store pipes ,sprinklers, small machines, other equipment’s

- Security of  stored material is important.

- A storage area of (20 x 20) feet (open courtyard/ shed) with proper protection may be tried

- INSTALLATION OF A RAIN-GAUGE :

- Ideally, the rain gauge should be installed in the same or nearby location of  CLiC.

- The requirements  for installation of rain gauge are

- Open space, no obstructions (trees/ buildings)

- Fencing; protected from kids etc.

- No water logging or threat of intrusion from animals.

The above are just pointers, actual location should be decided, based on the local conditions.  It should be ensured that, the FPOs play an active role in proposing and deciding on the location, also negotiate the rental agreement.

# COMMUNITY RESOURCE PERSONS- UTILIZATION FOR PROJECT ACTIVITIES

There are 3 categories of Resources persons in the Project

- FPO staff paid from Project for the project  period

- Thematic Activity wise Resource Persons Planned

- Community Organizer budgeted to FA ( over and above 2 category if required ) – budgeted to the FA.

- CATEGORY 1: FPO STAFF PAID FROM PROJECT FOR THE PROJECT PERIOD: Based on recent discussion with IFAD Mission, there would be 3 staff members working with FPO, supported by the Project for project period. FA will pay the salary of the CliC operator through FPO i.e. on the authorization/ approval of monthly plan and report by the FPO.  The project would pay 100% salary for the  initial year and FPO would have to contribute to the payment of salary in due course.

| Sr No | Name of the FPO Staff | Unit | No of Units | Unit Cost (Rs.) | Total Cost |
| --- | --- | --- | --- | --- | --- |
| 1 | FPO Manager | Month | Approx. 6 for this year | 8000-10000 | 48000-60000 |
| 2 | FPO accountant | Month | Approx. 6 for this year | 8000-10000 | 48000-60000 |
| 3 | Centre Operator (CliC/FOSS) | Month | Approx. 6 for this year | 8000-10000 | 48000-60000 |

This is the maximum limit and may vary in the range provided. FPO should maintain the register and monitor the  time allocated and the output delivered by the staff.

- CATEGORY 2: THEMATIC ACTIVITY WISE RESOURCE PERSON PLANNED: During the various thematic activities being planned in the project, the budget for the CRP is defined, based on the activity planned for the person. Theme wise CRP’s planned are below

2.1.	Farmer’s Learning and Action’s (FLA): There are 2 kinds of resource person’s identified under FLA’s i.e. Master Trainer and Master Farmers. The details of the roles and responsibilities can be found in the FLA note, shared by SPMU

2.1.1 Master Trainers: They are responsible for Training 315 Master farmers + 70 FA’s agri and NRM Facilitators.  A Honorarium and travel allowance of Rs 1700 per day would be provided to the them. The number of persons and the training days planned are based on the FFS plans circulated. The 9 LFA/FA/CB expert staff identified, as part of Master Trainer team are not considered as Resource person's, as they are already paid from the project.

2.1.2 Master Farmers: The Master Farmers are paid Rs 600, as resource fee per day, for conducting one FLA session.

2.2. 	Livestock: There are 2 resource persons planned under Livestock related activities. Poultry health worker  and Para workers for Small and Large Ruminants

| Sr No | CRP name | Unit | No of Units | Unit Cost (Rs.) | Total Cost | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | BYP Para-worker | User fee for vaccination Rs./bird vaccinated | No. of birds vaccinated | To be decided |  | Paid by the household to FPO for vaccination services; FPO pays to the worker |
|  |  | Maintaining the data base (Blue Card); Rs./household/ month | 50 households | 10 Rs./hh | 500 | To be paid from the project |
| 2. | Para worker | User fee @Rs./per animal vaccinated | As the no. of animals vaccinated | To be decided |  | User pays to the FPO & FPO pays to the Para worker |
|  |  | Per Livestock FFS | 100 (FFS planned) per GP per year – assuming 4 rearer groups in a GP. | 300 | 30000 | One Para worker is paid Rs 300 per FFS, with Target of 100 FFS in year per GP. |

2.3 	Ground Water: CRP’s are paid, based on activity/ task basis for the below set of activities

| Sr No | Activity | Unit | No of Units | Unit Cost (Rs.) | Total Cost | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Well Inventory | Well | As per site | 35 |  |  |
| 2 | Household Survey | Household | As per village | 20 |  |  |
| 3 | Thematic Map preparation | Days per GP | 70 | 350 |  | At GP level 7 maps @ 10 days each |
| 4 | Crop water budgeting data collection | Days per GP | 30 | 350 |  | 2 seasons per year 15 person days season= 30 days |
| 5 | Observation Well monitoring | Days per GP | 48 | 350 |  | 4 person days per month x 12 month =48 |
| 6 | Ground Water Sharing Plans Data survey | Acres |  | 300 |  |  |

2.4 	CMSS (Community managed Seed Systems)

| Sr No | Activity | Unit | No of Units | Unit Cost (Rs.) | Total Cost | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Para-seed certifier | Per quintal of seed produced | As per midterm report |  |  | Payment included in the sale price. |

- CATEGORY 3: COMMUNITY ORGANIZER BUDGETED TO FA (OVER AND ABOVE CATEGORY 2 IF REQUIRED): In the FA’s budget, allowance for Rs 8000 per GP per month to community organizers has been provided. Terms for using the allowance are:

1. 	FA can take Community Organizers, as Community Resource Persons(CRP) for mobilization of resources or any other purpose

2. 	The basis of payments can be Task /  Daily/ monthly, with the limit of Rs 8000 per GP per month. However, the tasks and roles should not be replicated, over theme based CRP already planned or FA’s staff roles and responsibilities. Under NO circumstances can they be taken as FA staff on a monthly basis.

CRP Registration:

In web portal, there would be database for CRPs. The CRP  details have to  be uploaded into the portal and CRPs registered. The registered CRPs have to be approved by the LFA. Only the approved CRPs can be paid. The CRP work needs to be uploaded into the web portal through a mobile form developed for the purpose. This system will be in place as soon as the APDMP portal is online.

Qualifications and selection criteria:

| Sr. No | Type of CRP/ FPO Staff | Qualifications / selection criteria | Hired by | Process of selection | Brief description of functions |
| --- | --- | --- | --- | --- | --- |
| 1 | FPO Manager | - At least degree or Inter with good work experience. - Fluent in reading, writing in Telugu and at least working knowledge of English. - Basic mathematics skills - Preferable – basic computer knowledge. - Preferably having experience in institutions (such as SHGs) - Within the Mandal; preferably from the cluster | FPO | - FPO advertises locally and also in the notice board of the GP - Panel constituted for tests & interview (by LFA) along with FPO. - Marks given for tests and results displayed at FPO office. | - FPO meetings - FPO Records - Updates board and executive members and helps in its review. - Provides information to FAs when asked for. - Plan and Review of the CRPs and other staff hired - *Prepares reports on the progress of activities every fortnight/ monthly - Ensure all compliances. |
| 2 | FPO Accountant | - Degree in B.Com or inter with 2 yrs experience in accounting - Preferably working experience with FPOs/ Vos/ MMS - Good knowledge and experience on standard accounting practices. - Functional knowledge of English. - Preference to basic knowledge of computers. - Ability to learn | FPO | - FPO advertises locally and also in the notice board of the GP - Panel constituted for tests & interview (by LFA) along with FPO. - Marks given for tests and results displayed at FPO office. | - Maintain records of all financial transactions - Maintain accounts; in Tally software. |