Andhra Pradesh Drought Mitigation Project

(APDMP)

Background:

The project is in its first year of implementation and is being implemented in 315 Gram Panchayats in 105 mandals based on well defined selection criteria. The project area is located in Anantapur, Chittoor, Kadapa, Kurnool (the Rayalaseema region) and Prakasam, the five driest districts of the state.

Component 1: Climate resilient production systems

Sub-component 1.1: Improved crop production systems

Sub-component 1.2: Improved livestock production systems

Sub-component 1.3: Strengthened farmer organisations.

Component 2: Drought proofing through NRM & governance

Sub-component 2.1: Water governance

Sub-component 2.2: Water monitoring and conservation.

Sub-component 2.3: Regeneration of common property rangeland (CPR)

Impact Assessment Process:

1. Impact Evaluation is the process which will assess the contribution of project in achieving its overall goal, and involves baseline and end-of-project sample surveys (in a five year project a mid-term survey may be omitted).  These surveys will be coordinated by the PMU M&E unit and contracted to an external agency, with specific expertise in such assessments.  Information to be collected will include the impact level indicators of IFAD’s Results and Impact Monitoring System (RIMS). These include mandatory ‘anchor indicators’ relating to household assets, and child malnutrition (anthropometric data of children under five years of age). Other indicators of poverty may also be used, such as quality of housing and sanitation.  Data will also be collected other goal and objective indicators from the log-frame, and on other indicators that help relate changes in all these indicators following participation in project activities and delivery of project outputs, and also to other log-frame indicators.

2. Participatory Monitoring and Evaluation (PME) will be used to gather further information on project outcomes. At project level, one of the strategies could be to organise an annual workshop in which the participating smallholder farmers, women, progressive farmers, representatives from the FPOs, private sector representatives, partner agencies including banks, etc., would be given the opportunity for sharing their views about the project and identify mechanisms for improvement. In PME, the primary stakeholders - the project target communities – are active participants in all stages of the project cycle, not just sources of information. PME will also focus on building the capacity of the local communities to analyse, reflect and take decisions and actions. PME attempts to provide opportunities for joint learning of various stakeholders at various levels of the project cycle.

PME facilitates greater stakeholder commitment and ownership on the project activities, in turn empowering them to take corrective actions to help themselves. In the field implementation and community level, participatory M&E is a kind of social process; it generally involves intense negotiations between different target communities having different needs, expectations and worldviews. In a way PME is also a kind of grassroots political process which addresses issues of equity, power and social transformation. Above all, PME could be a highly flexible process, continuously evolving and adapting to the programme specific circumstances and needs. PME is but the building block for successful M&E system in all IFAD projects and the project staffs will be oriented and sensitized on the need for sharing of project information and knowledge on regular basis with all stakeholders including the project target communities with open mind and transparent attitudes.

Monitoring and Evaluation Matrix:

| Narrative summary | Key performance questions | Key performance indicators | Data to be collected | Means of data collection | Frequency | Responsibility |
| --- | --- | --- | --- | --- | --- | --- |
| Goal: Improve the incomes of 165,000 farm households and strengthen their resilience to drought. | Have project households acquired more assets? | At least 75 percent of households1 report increased assets of 20% | Ownership of a list of assets with standard values - to create an overall asset index | RIMS+ baseline and impact surveys covering project and control households | At baseline and completion | Contracted agency |
|  | Has food security improved for project households? | Reduction in the prevalence of child malnutrition(Boys/Girls) | Age, height and weight of children aged under 5 years. Also data on food shortages and quality of diet |  |  |  |
|  | Have the income of project households improved relative to other households, and is this increase coming from farming? | Average annual income per household1 from and non-farm activities |  | Annual outcome survey (AOS) covering project and control group households | Yearly | Project M&E unit (survey managed by LTA outcome monitoring team) |
| Development objective: Strengthen the adaptive capacity and productivity of agriculture in the rainfed zones of 5 districts in southern AP | Has capacity of project farmers to adapt to drought improved relative to other farmers? | Number of households1 reporting increased adaptive capacity | Index2 based on outcomes and some outputs | Calculated from M&E data | Yearly | LTA M&E team |
|  |  | Number of farmers1 using protective irrigation and the area receiving protective irrigation | Area irrigated in kharif by groundwater, ponds and other sources. | AOS covering project and control group households | Yearly | Project M&E unit (survey managed by LTA outcome monitoring team) |
|  | Has farm production and productivity increased for project farmers relative to other farmers? | Number households reporting1increased crop and livestock production & sales | Direction of change in production, value of sales |  |  |  |
|  |  | Yield of main crops relative to non-project farmers. | Yields of g-nut, green gram and cotton. |  |  |  |
|  |  | Offtake of sheep breeding flocks | Numbers of breeding ewes and numbers of sheep sold |  |  |  |
| Component 1: Climate resilient production systems |  |  |  |  |  |  |
| Outcome 1: Adoption of more productive and resilient crop and livestock production systems | Are project farmers using more sustainable production systems than other farmers? | No of farmers1 who adopt sustainable PoP for rainfed crops, and/or livestock, and/or supplemental irrigation | List of resilient/sustainable practices and numbers of farmers adopting | AOS covering project and control group households | Yearly | Project M&E unit (survey managed by LTA outcome monitoring team) |
| Output 1.1: Improved crop production systems | How many project farmers are being reached by key project outputs? | Numbers of farmers1 accessing CLIC services | Number of farmers using CLIC for at least one service, also data on numbers for each service. | Data reported by DFA and FPO and included in DPMU reports. Confirmed by AOS, which will also gather data on control group farmers. | Annually or seasonally | DFA, FPOs and DPMU Project M&E unit (survey managed by LTA outcome monitoring team) |
|  |  | Numbers of crop producers1 trained via FFS | Number of FFS members by FFS topic, and number in 2nd, 3rd seasons etc. |  |  |  |
|  |  | Number of crop producers1 participating in ISFM | Number of farmers participating in one or more ISFM practices, also data on numbers for each practice. |  |  |  |
| Output 1.2 Improved livestock production systems for small ruminants and poultry | Are Pashu Sakhi reaching most livestock producers | Number of livestock producers1 using Pashu Sakhi services | Number of PS users, also type of services delivered, numbers using each service, services from other providers, and income generated by PS. | AOS covering project and control group households Pashu Sakhi records | Yearly Quarterly | Project M&E unit/ LTA. DFA / DPMU |
|  | How many project livestock producers are participating in other activities? | Number of livestock producers1 trained via FFS | Number of FFS members by FFS topic, and number in 2nd, 3rd seasons etc. | Data reported by DFA and FPO and in DPMU reports. Confirmed by AOS, which will also gather data on control group farmers. | Annually or seasonally | DFA, FPOs and DPMU Project M&E unit (with LTA outcome monitoring team) |
|  |  | Number of livestock producers1 participating in improved grazing, feeding and housing. | Number of producers & number of animals |  |  |  |
| Output 1.3 Farmer Producer Organizations established | How many farmers are members of FPOs? | No of FPOs established and registered | Number of FPO, also FPO membership1 and services provided |  |  |  |
| Component 2: Drought proofing via NRM & governance |  |  |  |  |  |  |
| Outcome 2: Water committees empowered at GP and HUN level to plan investments in water supply and manage water demand | Are GP and HUN Water Management Committees operating as planned and effectvely? | No of functional Water Committees at GP and HUN level in project area | Number of GP and HUN committees with regular meetings, making resource assessments, completing seasonal water budgeting, adoption of these plans by farmers, and feedback from farmers. | Water Management Plan adoption survey Annual assessment of the performance of water committees at GP and HUN levels | Yearly | GP WMC support-ed by DFA/LTA Via DFA and Dept of GW |
| Output1.1: Water Management Committees established in Gram Panchayats and strengthened take lead in water governance | Have GP WMCs been set up? | Number of Water Management Committees (WMC) established | Number of GPs with WMCs, also number of WMC members trained. | Data reported by DFA and FPO and included in DPMU reports | Monthly | DFA |
| Output 1.2: Rainwater harvesting and conservation infrastructure built and maintained | How much rainwater can be stored by project facilities? | Water harvesting capacity (cu.m.) | Number of ponds built by SWC and farm pond sub-components and average pond capacity. Also data on filling of ponds in a season | Data reported by DFA and FPO and included in DPMU reports | Yearly | DFA |
| Output 1.3: Common property rangelands developed | What area of rangeland have been improved? | Area of improved rangeland | Area of rangeland and numbers of GPs where this is located - also areas of different types of improvement, numbers of hh involved, and utilisation by livestock. | Data reported by DFA and FPO and included in DPMU reports | Yearly | DFA |
| Component 3: Management and lesson learning |  |  |  |  |  |  |
| Outcome 3: Lessons from the project identified and utilised to inform future development strategies. | Have lessons from APDMP had an impact on public sector agencies? | Three major lessons from APDMP discussed within the government and public institutions | Documentation of these lessons and dates and forums where these have been discussed. | PMU reports | Yearly | SPMU with LTA KM Advisor |
| Outputs: 3.1 Lesson learning-related documents and events | What lesson learning has taken place? | Number and type of evidence-led documents and events | List of events and documents | PMU reports | Yearly | SPMU with LTA KM Advisor |