QUARTERLY PLANNING AND BUDGETING

Background

APDMP is a project of Govt of AP taken up with loan funding from IFAD to evolve scalable approaches to manage droughts and related farmers’ distress. The program is operational in 5 districts in 315 GPs. The project adopts a multi dimensional approach in mitigating the drought and drought like situation in the selected GPs through various interventions.

Since the scope of project is across multiple districts, various  organisations(Governmental and Non Governmental) have been engaged to carry out the implementation of the activities envisaged in the project to achieve the desired outcome.

Role played by Organisations

The table gives a snapshot of role played by organisation

| Organisation | Role |
| --- | --- |
| State Project Management Unit(SPMU) | - Anchoring the Process at State level - Coordinating with various government department and line departments and facilitating convergence activities under the project - Carrying out Administrative role and facilitating the release of project funds |
| District Project Management Unit (DPMU) | - Anchoring the project at district level - Carrying out Administrative role and facilitating the release of project funds to Facilitating Agencies |
| Lead Facilitating Agencies(LFA) | - Coordinating with various Facilitating agencies for execution of the proposed work - Acting as interface between SPMU, LTA and FA - Monitoring and evaluating the work of FA - Capacity Building of FA |
| Facilitating Agency(FA) | - Executing of the works proposed in the project at ground level - Enhancing Community participation in the institutions |
| Lead Technical Agency(LTA) | - Project process design and related support to SPMU - Capacity building services - Process Monitoring and Evaluation - Planning and Budgeting |

Need for Planning and Budgeting

The project period is for 5 years and has to achieve certain  predefined target as provided in the Logical Framework. In order to achieve the overall target at macro level, it is important to breakdown the targets on Quarterly basis , thus the quarterly Planning and Budgeting would help in

- Assessing the performance of Lead Facilitating Agency

- Bringing about Accountability and Transparency  in the expenditure of budget by Facilitating agencies

- Achieving the targets through systematic approach

- Assessing and developing course correction in implementation process

- Developing a roadmap for the forthcoming quarters based on the target achieved in the previous quarter

- Developing a better understanding of the project at LFA and FA level

Quarterly Planning  and Budgeting Exercise : Quarter 2

The Planning and Budgeting exercise was conducted in Accion Fraterna on  16th and 17th August. The following were the key points of the exercise

- The Milestone targets to be achieved for the quarter, was discussed with LFAs

- LFAs, post consultation with concerned stakeholders proposed their Quarterly plan

- The proposed plan  was reviewed by LTA and SPMU. necessary feedback was provided and subsequently revisions were made, were required.

- SPMU approved the Quarterly plans and budgets proposed by  the LFAs

- Since the budget release is at  multiple levels, the budget being released need to be approved by stakeholders as per standard budget release format (Eg: In case money is  being released to an FPO, the FPO directors need to give an undertaking of the money to be released and this would need  approval  of  FA, LFA and DPMU).

- The flow proposed above, would ensure that every stakeholder is cognisant of the budget being released and would also be accountable for its utilisation