## APDMP Targets-Final
Sr. No | Result | Unit | Target PIM | Project Targets per GP
1 | At least 75 percent of households report increased assets of 20% | HH | 123750 | 393
2 | Number of households reporting cultivation of more than 2 crops in kharif, at least 15% increase in rabi cultivated area, and integration with livestock | HH | 123750 | 393 Farmers per GP 1. 100 Ha : 100*80=8000 2. No of Seed producing farmers under CMSS 3. No of farmers receiving seed under CMSS 4. No of farmer receiving Navdhanya kits
3 | Increased Adaptive capacity | At least 4 Project level indicators access | 165000 | >>>>>>>
4 | No of farmer/area under protective irrigation | Nos/Ha | 52800/52662 | 168
5 | No of farmers accessing CliC's | No | 132000 | 420 farmers using CliC services ( per GP)
6 | No of farmers trained via FFs | No | 115000 | Total : ( First year 30=30) 2nd year : 30 (in other 2 GPs. =60 farmers & each influencing 3rd Year: 120(additional 2 GPs not covered in Project) and each master farmer would train 3 farmers = 180*3*315= 170100 farmers
7 | Number of livestock producers using Pashu Sakhi services | No | 43000 | BYP: Total :32,000 (315 enterprenuers+ 15750units+800 Pashu Sakhi's )
Small Ruminants and large ruminants healthcare services: 31500(315*100)
8 | No of FPO's registered | No | 40 | done; 105
9 | No of functional Water Committees at GP and Hydrological unit level in project area | No | 300 | 315 Committees
10 | Increased Water harvesting capacity | cum | 9.9 million | 126 farm pond equivalent at 250 cum each
11 | Regenrating degraded land | Ha | 42900 | 136.1905
Special Target
1. 100 Poorest of Poor
2. 30% women
Project Level Tracking indicators (HH levels)
1. HH involved in Participation in Groundwater Sharing arrangements
2. Access to weather and other crop/livestock information through CLICs
3. Access to micro-irrigation
4. Participation in crops FFS
5. Participation in Livestock FFS
6. Access to Pashu Sakhi services
7. Access to fodder from regenerated common property resources

## MileStone Sheet-Final
Quarter 2 (Jul- Sept)
Sr No | Theme | MileStone | MileStone Targets in Project | Unit | Means of Verification | Remarks | Q2 assessment parameters
1 | NRM Plans | NRM works planned from Project | 105 sites work completed | Cluster | - |  | No of Clic Centres
2 |  | Covergence works finished | - |  | - |  | No of CHC
3 | FFS | FFS session | 420 FFS units completed | Cluster | Event Report submitted in portal in app and verified by DPMU/SPMU |  | No of FFS
4 | FPO's | Training completed on 5 modules | 525 trainings completed |  | Trainings captured in app and event report uploaded |  | Hydrlogical unit estbalished
5 |  | FPO membership with share capital deposited | 21000 |  | Data to be shared |  | Ground Water Collectivization in Ha
6 |  | FPO women members | 6300 |  |  |  | Entrepreneur BYP Est.
7 | CliC | No of CliC/ Rythu Sewa Kendra/ Foss centre identified and rental agreement signed | 105 | Cluster | Rental agrrement signed |  | BackYard Poultry Units Est
8 |  | CHC situation analysis completed | 35 | Cluster | Report in format to be submitted to DPMU and SPMU. Exercise and format to be shared by LTA
9 |  | Procurement of equipments for CHC to be completed | 35 | Cluster
10 |  | CHC inagurated | 35 | Cluster | Transaction in centre recorded
11 | Ground Water | GP Selection | 53 | GP
12 |  | CRP Selection | 106 | GP
13 |  | Procurement of equipments | 53 | GP
14 |  | Establishment of hydrological monitoring network | 53 | GP | Data set to be shared to SPMU/DPMU in format shared by LTA . Register maintained at CliC's
15 |  | Ground water recharge plans | - | GP | No of plans submitted. Plan format to be shared by LTA
16 |  | Crop water Budeting Plans | - | GP | Workshop Report Report and rules set by committee. Format to be shared by LTA
17 |  | Preparedness and placing support system with equioments PI @ FPO level | 50 acres per cluster | Cluster | Demonstraion & system building planned
18 |  | Ground water pooling- Identifcation of potential WS patches | 53 | GP | Format to be shared by LTA to be shared to DPMU/SPMU by LFA
19 |  | Ground water pooling- Appoved Plans | 30 | GP
20 |  | Preparation of resource analytical book of GP to be developed by resource person with the support of FA |  | GP | Resource book shared to DPMU/SPMU
21 | LiveStock- BYP | Situation analysis of RLU's | 105 | Cluster | Report in format to be submitted to DPMU and SPMU
22 |  | Formation of CIG's | 35 | Cluster | Depositing of CIG money in FPO account
23 |  | HH adapting improved package of practice | 35 | Cluster | Data on number of household able to sell 10-12 birds apart from own consumption
24 |  | No of GP accesssing schedules seasonal vaccination | 35 | GP | Data formats to be shared by LFA to DPMU/SPMU/LTA
25 |  | Establishing of BYP breed farm (entreprenuer level ) | 35 | Cluster | Data to be shared by LFA . Format will be given in training
26 |  | Exposure cum training visit on BYP | 35 | Cluster | Training report should shared in webportal. DPMU and SPMU can verify from Portal
27 | LiveStock- small Ruminants | Trained Paraworkers | 315 | Cluster | Training report to be shared in webportal. DPMU and SPMU can verify from Portal
28 |  | Informal Group of small Ruminant rearers | 35 | Cluster | Depositing of money in FPO account
29 | CMSS | Registration for seed certification to be completed | 105 | Cluster | Payment is made to SCCO for registration
30 |  | Seed farmers trained in seed production and certification protocols | 100% | No. | Upload of events in the portal
31 |  | CMSS Committee established in each FPO | 105 | Cluster | Formal resolution of FPO
32 |  | Seed indent prepared for seed production in Rabi (for 2019 kharif) | 105 | Cluster | Seed Indent Note submitted
33 |  | Mid-term report prepared for the ongoing seed production with estimated yields and procurement requirements | 105 | Cluster | Mid-term report submitted
34 | Vulnerable groups | Participatory Exercises complete in all habitations to identify vulnerable groups | 315 | GPs | Portal database
35 |  | List of 100 most vulnerable households uploaded into the portal | 315 | GPs | Portal database
36 | Commons | Identification of common lands in the cluster and delineation in the maps. | 105 | Cluster
37 |  | Basic profile of the commons uploaded into the website | 105 | Cluster

## MileStone Sheet-for LFA
Quarter 2 (Jul- Sept)
Sr No | Theme | MileStone | MileStone Targets in Project | Unit | Means of Verification | Remarks | Q2 assessment parameters
1 | NRM Plans | NRM works planned from Project |  | Cluster | - |  | No of Clic Centres
2 |  | Covergence works finished |  |  | - |  | No of CHC
3 | FFS | FFS session |  | Cluster | Event Report submitted in portal in app and verified by DPMU/SPMU |  | No of FFS
4 | FPO's | Training completed on 5 modules |  |  | Trainings captured in app and event report uploaded |  | Hydrlogical unit estbalished
5 |  | FPO membership with share capital deposited |  |  | Data to be shared |  | Ground Water Collectivization in Ha
6 |  | FPO women members |  |  |  |  | Entrepreneur BYP Est.
7 | CliC | No of CliC/ Rythu Sewa Kendra/ Foss centre identified and rental agreement signed |  | Cluster | Rental agrrement signed |  | BackYard Poultry Units Est
8 |  | CHC situation analysis completed |  | Cluster | Report in format to be submitted to DPMU and SPMU. Exercise and format to be shared by LTA
9 |  | Procurement of equipments for CHC to be completed |  | Cluster
10 |  | CHC inagurated |  | Cluster | Transaction in centre recorded
11 | Ground Water | GP Selection |  | GP
12 |  | CRP Selection |  | GP
13 |  | Procurement of equipments |  | GP
14 |  | Establishment of hydrological monitoring network |  | GP | Data set to be shared to SPMU/DPMU in format shared by LTA . Register maintained at CliC's
15 |  | Ground water recharge plans |  | GP | No of plans submitted. Plan format to be shared by LTA
16 |  | Crop water Budeting Plans |  | GP | Workshop Report Report and rules set by committee. Format to be shared by LTA
17 |  | Preparedness and placing support system with equioments PI @ FPO level |  | Cluster | Demonstraion & system building planned
18 |  | Ground water pooling- Identifcation of potential WS patches |  | GP | Format to be shared by LTA to be shared to DPMU/SPMU by LFA
19 |  | Ground water pooling- Appoved Plans |  | GP
20 |  | Preparation of resource analytical book of GP to be developed by resource person with the support of FA |  | GP | Resource book shared to DPMU/SPMU
21 | LiveStock- BYP | Situation analysis of RLU's |  | Cluster | Report in format to be submitted to DPMU and SPMU
22 |  | Formation of CIG's |  | Cluster | Depositing of CIG money in FPO account
23 |  | HH adapting improved package of practice |  | Cluster | Data on number of household able to sell 10-12 birds apart from own consumption
24 |  | No of GP accesssing schedules seasonal vaccination |  | GP | Data formats to be shared by LFA to DPMU/SPMU/LTA
25 |  | Establishing of BYP breed farm (entreprenuer level ) |  | Cluster | Data to be shared by LFA . Format will be given in training
26 |  | Exposure cum training visit on BYP |  | Cluster | Training report should shared in webportal. DPMU and SPMU can verify from Portal
27 | LiveStock- small Ruminants | Trained Paraworkers |  | Cluster | Training report to be shared in webportal. DPMU and SPMU can verify from Portal
28 |  | Informal Group of small Ruminant rearers |  | Cluster | Depositing of money in FPO account
29 | CMSS | Registration for seed certification to be completed |  | Cluster | Payment is made to SCCO for registration
30 |  | Seed farmers trained in seed production and certification protocols |  | No. | Upload of events in the portal
31 |  | CMSS Committee established in each FPO |  | Cluster | Formal resolution of FPO
32 |  | Seed indent prepared for seed production in Rabi (for 2019 kharif) |  | Cluster | Seed Indent Note submitted
33 |  | Mid-term report prepared for the ongoing seed production with estimated yields and procurement requirements |  | Cluster | Mid-term report submitted
34 | Vulnerable groups | Participatory Exercises complete in all habitations to identify vulnerable groups |  | GPs | Portal database
35 |  | List of 100 most vulnerable households uploaded into the portal |  | GPs | Portal database
36 | Commons | Identification of common lands in the cluster and delineation in the maps. |  | Cluster
37 |  | Basic profile of the commons uploaded into the website |  | Cluster

## Detailed Plan Sheet
Quarterwise Activity(Physical and Financial) Tracker
S.No. | Year | Quarter | Select District | LFA Name | FA Name | Cluster | Theme | Description of the Planned Items | AWPB Head | Sub Component | Sub Head of Sub Component | Physical works |  | Financial |  |  | Plan Date(Execution of Work) |  | Remarks
[12 empty] | Units | Quantity/ No. | Unit Cost | Amount | Budget to be released to whom | From | To | [9 empty] | Institutions
1 | [24 empty] | Accion Fraternia -1 | LFA |  | CMSS | FY 17-18
[20 empty] | AF | Crop production systems |  |  |  | Accion Fraternia -2 | FA | Q1(Apr-Jun) | Soils | FY 18-19
[20 empty] | HANDS | Livestock Production Systems | Anantapur | Climate resilient production systems | Climate Information Centre | Sahjeevan-1 | FPO | Q2(Jul-Sept) | LiveStock HealthCare Service | FY 19-20
[20 empty] | APMAS | Farmers Organisations | Kurnool | Drought Proofing NRM and Governance | Extension Service provision(FFS) | Sahjeevan-2 | Convergence | Q3(Oct-Dec) | LiveStock-SR | FY 20-21
[20 empty] | CSA | Water Governance | Chittor |  | Support to Adaptive research | APMAS |  | Q4(Jan-Mar) | LiveStock-BYP | FY 21-22
[20 empty] | AAA | Water Monitoring and Conservation | Kadapa |  | Integrated soil fertility management | FES |  |  | GroundWater
[20 empty] | FES | Regenerating common property rangeland | Prakasam |  | Protective irrigation | Jana Jagriti |  |  | Crop Extension Service
[20 empty] | RASS |  |  |  | Capacity Building | Annadata MACS
[20 empty] | RHGBMS |  |  |  | Support to Sheep and Goat Production | HANDS
[20 empty] | EFFORT |  |  |  | Support to Feed and Fodder | IA& BWS
[24 empty] | Support to Backyard Poultry | RIDS
[24 empty] | Capacity Building | Gram Vikas
[24 empty] | Support for FPOs | Aranya Agriculture Alternatives
[24 empty] | Services to Producers | APARD
[24 empty] | Community Managed Seed Systems | AARDIP
[24 empty] | Custom / Machinery Hiring Centers (CHCs) | NYA
[24 empty] | Capacity Building Trainings | CSA
[24 empty] | Water Budgeting Workshop | APARD
[24 empty] | Crop Water Budgeting | SPES
[24 empty] | Studies and Consultancies | RASS
[24 empty] | Soil and Water Conservation | Pragati
[24 empty] | Monitoring Water Resources | PPT
[24 empty] | Civil Works | CORE
[24 empty] | Surveys and Studies | FES
[24 empty] | Office Equipment | GORD
[24 empty] | MIS Development | Chaitanya
[24 empty] | Audits /b | GVS
[24 empty] | Workshops, Trainings, TA | RHGBMSS
[24 empty] | Office Equipment and Facilities | REDS
[24 empty] | Salaries - Staff Seconded from GoAP | PARTNER
[24 empty] | PMU Contracted Staff | EFFORT
[24 empty] | Office Running Costs | SNIRD
[24 empty] | Salaries - Staff Seconded from GoAP | SARDS
[24 empty] | Contracted Staff at DPMUs | SREEKARAM
CRDO

## Working sheet (hidden)
Component / Sub-component / Item | AWPB Head
Component - 1: Climate resilient production systems | Climate resilient production systems
Sub-component - 1.1: Crop production systems | Drought Proofing NRM and Governance
A. Climate Information Centre | Lesson learning and Management
CliC Centre Equipments
CliC Centre Operationzalized ( Rent , Maintenance etc.)
CLIC facilitator (1 persons) | Sub Head | Climate Information Centre
| Crop production systems | Extension Service provision(FFS)
B. Extension Service provision(FFS) | Livestock Production Systems | Support to Adaptive research
1. Farmer Field School | Farmers Organisations | Integrated soil fertility management
| Water Governance | Protective irrigation
| Water Monitoring and Conservation | Capacity Building
C. Support to Adaptive research | Regenerating common property rangeland | Support to Sheep and Goat Production
| Lesson Learning | Support to Feed and Fodder
| State Project Management Unit | Support to Backyard Poultry
D. Integrated soil fertility management | District Project Management Unit /c | Capacity Building
| Support from International / national TA (FAO/Others) | Support for FPOs
Services to Producers
Community Managed Seed Systems
E. Protective irrigation |  | Custom / Machinery Hiring Centers (CHCs)
Capacity Building Trainings
Water Budgeting Workshop
F. Capacity Building |  | Crop Water Budgeting
Studies and Consultancies
Soil and Water Conservation
Component - 1.2: Livestock Production Systems |  | Monitoring Water Resources
1. Support to Sheep and Goat Production |  | Civil Works
Surveys and Studies
2. Support to Feed and Fodder |  | Office Equipment
MIS Development
3. Support to Backyard Poultry |  | Audits /b
BackYard Poultry Units |  | Workshops, Trainings, TA
Entrepreneur Poultry Breeder Units |  | Office Equipment and Facilities
Salaries - Staff Seconded from GoAP
PMU Contracted Staff
4. Capacity Building |  | Office Running Costs
Salaries - Staff Seconded from GoAP
Component -1. 3: Farmers Organisations |  | Contracted Staff at DPMUs
A. Support for FPOs
1. Super Cluster FPOs
2. Village/ GP / cluster Level FPOs
Formation/ institution strengthening of FPOs
B. Services to Producers
C. Community Managed Seed Systems
D: Custom / Machinery Hiring Centers (CHCs)
CHC established
Component - 2: Drought Proofing NRM and Governance
Sub-component - 2.1: Water Governance
1. Capacity Building Trainings
2. Water Budgeting Workshop
Crop Water Budgeting
4. Studies and Consultancies
Sub-component - 2.2: Water Monitoring and Conservation
1. Soil and Water Conservation
2. Monitoring Water Resources
3. Civil Works
4. Surveys and Studies
Sub-component - 2.3: Regenerating common property rangeland
Component - 3: Lesson learning and Management
A. Lesson Learning
B. State Project Management Unit
1. Office Equipment
2. MIS Development
3. Audits /b
4. Workshops, Trainings, TA
C. District Project Management Unit /c
1. Office Equipment and Facilities
D. Lead Technical Agency /d
E. Support from International / national TA (FAO/Others)
Lead Facilitating Agency
Facilitating Agency
II. Recurrent Costs
A. State Project Management Unit
1. Salaries - Staff Seconded from GoAP
2. PMU Contracted Staff
3. Office Running Costs
B. District Project Management Unit
1. Salaries - Staff Seconded from GoAP
2. Contracted Staff at DPMUs