## Andhra Pradesh Drought Mitigation Programme

Process Monitoring: Concept Note

-  Dr. Ananth S Panth, LTA (WASSAN)

1. Process Monitoring: Background

Process Monitoring of Impacts is a method for steering interventions / projects / programs. In other words, it influences the behavior of involved stakeholders to follow a desired course for achieving specified objectives. It is essentially about identifying processes considered relevant for the achievement of results or impacts and then monitoring whether these processes are valid and actually take place. The need for process monitoring can occur either for changing contextual conditions or modifying implementation strategies.

The aim of is to steer the implementation of projects by continuously observing whether they are likely to achieve expected impacts. Thus, process monitoring is oriented on impacts throughout the entire implementation chain and therefore the likeliness of impacts can be observed even at early stages of implementation.

2. Components of Process Monitoring:

The project involves monitoring of processes that leads to outputs and outcomes. In the project cycle, the activities are designed based on planned outputs. These outputs is based on the desired objectives, which are part of the larger goals. Thus the process of achieving an objective which is part of a larger goal is attained by carrying out a set of activities. These activities leads to a set of outputs. Each set of output is associated with a set of activities carried out. The outputs is of two types. One is the desired output as per the desired set of activities. These are according to the plan in the project cycle. However, after the activities are carried out, there would be a set of outputs, which are actual. The process monitoring will analyse the difference between the desired and actual outputs. The actual output would be either the same as desired or better or not to the expected level. The difference in the levels of output, also known as process variance, could be due to differences in the methods of carrying out the activity. At the activity level, certain inputs might not have been given, or of poor  quality or carried out differently, hence leading to different types of outputs.

The process monitoring provides us the "process variance", i.e. the difference between the desired activity and actual activity, as well as the difference between the desired output and actual output. The process variance could be positive or negative, considering the key processes / critical points.  If the process variance is high and positive, the desired activity process needs to change the design. If the process variance is high and negative, the activity process needs corrections.

The process monitoring analysis should finally lead to design corrections (feedback loop) for better implementation. It should also provide feedback to the administration based on performance (administrative feedback).

Larger goal 		Objectives                    Output     		Activities   = Project cycle

(Outcome)

3. How to carry out the process monitoring activity?

The process monitoring is to be carried out for each of the themes separately.

A. At the quarterly plan level - once the action plan is made ready by the theme expert, the activities including the key activities (critical points) will be reviewed by M & E (LTA - Dr.Ananth S Panth) before being approved by Lead Advisor (LTA-Mr. A. Ravindra).

B. After the quarterly action plan is implemented - every ninth and tenth week of the quarter (first two weeks of third month of the quarter) is to be allotted for process monitoring.

Aspects to be followed during the monitoring:

- identify the key activities ( critical points)

- identify the activity happened or not

- review the quality of process followed

- review the quality of output and outcome

| Sl. No. | Theme | Designed Activity | Actual Activity | Designed Output | Actual Output | Designed Outcome | Actual Outcome |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Sl. No. | Theme | Designed Activity | Actual Activity | Designed Output | Actual Output | Critical Milestone Indicator | Consistency with value Indicators | Value 1 | Value 2 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

C. Documentation of Process Monitoring:

Information of all the 105 clusters have to be documented for each of the theme. The documentation can be in pictorial form / map atlas - identifying the differences in activity / output / outcome.  The document will be prepared by end of the quarter and shared with all partners of APDMP for improvements.

D. Process Monitoring Team:

The core team shall consist of 15 members - 1 SPMU, 1 LTA, 4 DPMU, 9 LFA.