## Total CB
LFA Wise
[13 empty] | LTA |  |  |  | AF |  |  |  | HANDS |  |  |  | APMAS |  |  |  | FES |  |  |  | RASS |  |  |  | EFFORT |  |  |  | RHGBMSS |  |  |  | CSA |  |  |  | AAA |  |  |  | end
[13 empty] | FAs |  |  |  | 4 |  |  |  | 4 |  |  |  | 4 |  |  |  | 4 |  |  |  | 4 |  |  |  | 5 |  |  |  | 3 |  |  |  | 3 |  |  |  | 4 | 35 |  |  | end
Sl No | Theme | Sub Theme | Participants | Duration | No of Participants | Level of CB Event | Type of CB Event | Trainers/ Facilitators | Whether ToT Needed | No of Persons/ Batch | No of Batches | Remarks | No of Participants | Participants/ Batch | Frequency | No of Batches/ Round | No of Participants | Participants/ Batch | Frequency | No of Batches/ Round | No of Participants | Persons/ Batch | Frequency | No of Batches/ Round | No of Participants | Persons/ Batch | Frequency | No of Batches/ Round | No of Participants | Persons/ Batch | Frequency | No of Batches/ Round | No of Participants | Persons/ Batch | Frequency | No of Batches/ Round | No of Participants | Persons/ Batch | Frequency | No of Batches/ Round | No of Participants | Persons/ Batch | Frequency | No of Batches/ Round | No of Participants | Persons/ Batch | Frequency | No of Batches/ Round | No of Participants | Persons/ Batch | Frequency | No of Batches/ Round | end
1 | FFS | FFS | Farmers @ 30 per Learning Site | 3-4 Hours | 3150 | Learning Site | FFS | Master Farmers | Yes | 30 | 1260 | One FFS @ Fortnighly, 6 months | NA | NA | NA | NA | 360 | 360 | Fortnightly | 12 | 360 | 360 | Fortnightly | 12 | 360 | 360 | Fortnightly | 12 | 360 | 360 | Fortnightly | 12 | 360 | 360 | Fortnightly | 12 | 450 | 450 | Fortnightly | 15 | 270 | 270 | Fortnightly | 9 | 270 | 270 | Fortnightly | 9 | 360 | 360 | Fortnightly | 12 | end
2 | FFS | FFS | Master Farmers (105*2) and FA Facilitators-Agri, Institutions, NRM ((1+1+3)*105) | 3 days | 385 | LFA | Training | FFS-Master Trainers | Yes | 25 | 15 |  | NA | NA | NA | NA | 44 | 22 | Quarterly | 2 | 44 | 22 | Quarterly | 2 | 44 | 22 | Quarterly | 2 | 44 | 22 | Quarterly | 2 | 44 | 22 | Quarterly | 2 | 55 | 22 | Quarterly | 2 | 33 | 22 | Quarterly | 2 | 33 | 22 | Quarterly | 2 | 44 | 22 | Quarterly | 2 | end
3 | FFS | FFS | Master Trainers (CB, Agl, NRM Experts and one relevant person) of LFAs | 2 days | 36 | LTA | ToT | FFS-Core Team | No | 36 | 1 |  | 36 | 36 | Quarterly | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | end
4 | BYP | BYP | Orientation Trainings to BYP Rearers @ 100/ Cluster in 105 Clusters | 3-4 Hours | 10500 | Village | Orientation | FA Livestock Facilitator and Service Providers | Yes | 25 | 420 |  | NA | NA | NA | NA | 1200 | 33 | Fortnightly | 36 | 1200 | 33 | Fortnightly | 36 | 1200 | 33 | Fortnightly | 36 | 1200 | 33 | Fortnightly | 36 | 1200 | 33 | Fortnightly | 36 | 1500 | 33 | Fortnightly | 45 | 900 | 33 | Fortnightly | 27 | 900 | 33 | Fortnightly | 27 | 1200 | 33 | Fortnightly | 36 | end
5 | BYP | BYP | Service Providers @ 2/Cluster in 105 | 2 days | 210 | LFA | Training | LFA Livestock Experts | Yes | 35 | 6 |  | NA | NA | NA | NA | 24 | 24 | Once | 1 | 24 | 24 | Once | 1 | 24 | 24 | Once | 1 | 24 | 24 | Once | 1 | 24 | 24 | Once | 1 | 30 | 30 | Once | 1 | 18 | 18 | Once | 1 | 18 | 18 | Once | 1 | 24 | 24 | Once | 1 | end
6 | BYP | BYP | Service Providers @ 2/Cluster in 105 | 1 day | 210 | LFA | Refresher Training | LFA Livestock Experts | Yes | 35 | 6 |  | NA | NA | NA | NA | 24 | 24 | Once | 1 | 24 | 24 | Once | 1 | 24 | 24 | Once | 1 | 24 | 24 | Once | 1 | 24 | 24 | Once | 1 | 30 | 30 | Once | 1 | 18 | 18 | Once | 1 | 18 | 18 | Once | 1 | 24 | 24 | Once | 1 | end
7 | BYP | BYP | Breeding Farm Entrepreneurs-1/Cluster | 2 days | 105 | LFA | Exposure | LTA/LFA | No | 35 | 3 |  | 105 | 35 | Once | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | end
8 | Small Ruminants | Small Ruminants | Rearer Field Schools @ 30/GP | 3-5 Hours | 3150 | Learning Site | FFS | Master Farmers | Yes | 30 | 1260 | One FFS @ Fortnighly, 6 months | NA | NA | NA | NA | 360 | 30 | Fortnightly | 12 | 360 | 30 | Fortnightly | 12 | 360 | 30 | Fortnightly | 12 | 360 | 30 | Fortnightly | 12 | 360 | 30 | Fortnightly | 12 | 450 | 30 | Fortnightly | 15 | 270 | 30 | Fortnightly | 9 | 270 | 30 | Fortnightly | 9 | 360 | 30 | Fortnightly | 12 | end
9 | Small Ruminants | Vaccination | Para Workers @ 1/GP | 21 days | 315 | LTA/LFA | Training cum Internship | LTA and Veterinary Doctor | No | 35 | 9 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | end
10 | Small Ruminants | Livestock themes and Training Skills | Livestock Experts and 1 from any FA | 1 day | 18 | LTA | ToT | LTA | NA | 18 | 1 |  | 18 | 18 | Once | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | end
11 | FPO | FPO Concept and Membership | FPO Governing Body Members | 1 day | 1575 | FA | Training | LFA CCB; ID Experts | No | 35 | 45 |  | NA | NA | NA | NA | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 225 | 35 | Once | 6 | 135 | 35 | Once | 4 | 135 | 35 | Once | 4 | 180 | 35 | Once | 5 | end
12 | FPO | FPO as PIA and Services | FPO Governing Body Members | 1 day | 1575 | FA | Training | LFA CCB; ID Experts | No | 35 | 45 |  | NA | NA | NA | NA | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 225 | 35 | Once | 6 | 135 | 35 | Once | 4 | 135 | 35 | Once | 4 | 180 | 35 | Once | 5 | end
13 | FPO | FPO Governance | FPO Governing Body Members | 1 day | 1575 | FA | Training | LFA CCB; ID Experts | No | 35 | 45 |  | NA | NA | NA | NA | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 225 | 35 | Once | 6 | 135 | 35 | Once | 4 | 135 | 35 | Once | 4 | 180 | 35 | Once | 5 | end
14 | FPO | FPO Management and Indicators for Good FPO | FPO Governing Body Members | 1 day | 1575 | FA | Training | LFA CCB; ID Experts | No | 35 | 45 |  | NA | NA | NA | NA | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 225 | 35 | Once | 6 | 135 | 35 | Once | 4 | 135 | 35 | Once | 4 | 180 | 35 | Once | 5 | end
15 | FPO | FPO Legal Compliance | FPO Governing Body Members | 1 day | 1575 | FA | Training | LFA CCB; ID Experts | No | 35 | 45 |  | NA | NA | NA | NA | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 225 | 35 | Once | 6 | 135 | 35 | Once | 4 | 135 | 35 | Once | 4 | 180 | 35 | Once | 5 | end
16 | FPO | FPO as CLICs and Business Service Provider | FPO Governing Body Members | 1 day | 1575 | FA | Training | LFA CCB; ID Experts | No | 35 | 45 |  | NA | NA | NA | NA | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 180 | 35 | Once | 5 | 225 | 35 | Once | 6 | 135 | 35 | Once | 4 | 135 | 35 | Once | 4 | 180 | 35 | Once | 5 | end
17 | FPO | CLIC Operational Manual and Services | CLIC Operator | 3 days | 105 | LTA | Training | LFA CCB; ID Experts | No | 35 | 3 |  | 105 | 35 | Once | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | end
18 | FPO | FPO Opeational Manual, Business and Services | Manager | 5 days | 105 | LTA | Training | LFA CCB; ID Experts | No | 35 | 3 |  | 105 | 35 | Once | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | end
20 | PGWM | Well inventory (for Identification of observation wells) | Cluster CRPs for GW +FA-NRM Facilitators and LFA CB+Agl; DPMU (LTA will place RPs; Max 10 participants in one training batch) | 3 days | 177 | LFA | Hands on Training | PRPs from LTA | LFA | 9 | 20 | Installing Mobile application, Demontration, Collecting data, upload, using water level indicator and Water quality tracer, yield test | NA | NA | NA | NA | 20 | 20 | Once | 1 | 20 | 20 | Once | 1 | 20 | 20 | Once | 1 | 20 | 20 | Once | 1 | 20 | 20 | Once | 1 | 23 | 23 | Once | 1 | 17 | 17 | Once | 1 | 17 | 17 | Once | 1 | 20 | 20 | Once | 1 | end | 0
21 | PGWM | Interpretation of well inventory data and mapping groundwater movement for preparing GW Recharge Plans | NRM Persons and Data analysts @ LFA and DPMU | 3 days | 23 | LTA | Training | LTA | LTA | 23 | 1 | Interpretation of well inventory data and mapping groundwater movement, Installation of GW monitoring network. | 23 | 23 | Once | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | end
22 | PGWM | Experience Sharing on impact and process of Crop Water Budgeting Exercises | LFA (NRM, Agl and Res Persons; DPMU | 4 days | 32 | LTA | Workshop | LTA | LTA | 32 | 1 | Assessment of water balance, resource mapping, listing crop wise irrigation practices; Crop water budgeting; Revised Cropping Plans; Tools and Techniques for participatory exercises | 32 | 32 | Once | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | end
23 | PGWM | Crop Water Budgeting Exercises | CRPs and NRM FA Facilitators | 4 days | 140 | LFA | Training | LFA | LFA | 30 | 5 | Assessment of water balance, resource mapping, listing crop wise irrigation practices; Crop water budgeting; Revised Cropping Plans; Tools and Techniques for participatory exercises | [40 empty] | end
24 | PGWM | Groundwater collectivisation (for preparing Water Sharing plans) | LFA (Agl, NRM, CB), DPMU (NRM/Agl, Inst) | 4 days | 37 | LFA | Training cum Exposure | LTA | LFA | 37 | 1 | Concept; Tools and techniques, Methods, Opportunities and Challenges in APDMP | 37 | 37 | Once | 1 | [36 empty] | end
25 | PGWM | Groundwater collectivisation (for Water Sharing plans) | FA staff (Agl, NRM, I&CB) | 3 days | 175 | LFA | Training | LFA | LFA | 20 | 9 | Concept; Tools and techniques, Methods, Opportunities and Challenges in APDMP | [40 empty] | end
26 | PGWM | Groundwater collectivisation (for Water Sharing plans) | CRPs | 2 days | 315 | LFA | Training | LFA | LFA | 35 | 9 | Mobilising farmers, Formation of Water Sharing Groups and Survey | [40 empty] | end
27 | CMSS | Seed Production: Seed Production Process, techiniques | Seed Producers | 1 day | [48 empty] | end
28 | CMSS | Concept and Process of CMSS | LFA: Team Leader, Agrl, Inst, CCB; | 2 days | 36 | LTA | ToT | LTA | No | 36 | 1 | All CMSS training topics to be covered: Conmcept, process, Book Keeping, | 36 | 36 | Once | 1 | [36 empty] | end
29 | CMSS | CMSS Planning workshops | LFA: Team Leader, Agrl, Inst; JDA, ADA, AOs concerned | 1 day | 112 | LFA | Workshop | DPMU | No | 25 | 5 |  | 112 | 22 | Once | 5 | [36 empty] | end
30 | CMSS | Orientation on Concept and Process of CMSS | FPO Sub Committee on CMSS | 1 day | 525 | LFA | Training | LFA | Yes | 15 | 35 |  | NA | NA | NA | NA | 60 | 30 | Once | 2 | 60 | 30 | Once | 2 | 60 | 30 | Once | 2 | 60 | 30 | Once | 2 | 60 | 30 | Once | 2 | 75 | 30 | Once | 3 | 45 | 30 | Once | 2 | 45 | 30 | Once | 2 | 60 | 30 | Once | 2 | end
31 | CMSS | Seed Certification process | Vittana Mitra | 2 days | 105 | State | Training | APSSCA+LTA | No | 35 | 3 |  | 105 | 35 | Once | 3 | [36 empty] | end
32 | CMSS | Book keeping in CMSS | FPO Accountant cum MVK Book Keeper; FPO Manager; 1 FPO Leader | 1 day | 315 | LFA | Training | LFA | Yes | 35 | 9 |  | NA | NA | NA | NA | 36 | 36 | Once | 1 | 36 | 36 | Once | 1 | 36 | 36 | Once | 1 | 36 | 36 | Once | 1 | 36 | 36 | Once | 1 | 45 | 45 | Once | 1 | 27 | 27 | Once | 1 | 27 | 27 | Once | 1 | 36 | 36 | Once | 1 | end
33 | Gender & Equity | Women in Agriculture | FA: Gender and Equity Enablers, LFA: ID Experts, DPMU: ID Experts | 2 days | 49 | LTA | Workshop | LTA | No | 49 | 1 |  | 49 | 49 | Once | 1 | [36 empty] | end
end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end
Note on F23: VALI: 53 Clusters (FA-GW NRM Facilitator and 2 CRPs/Cluster): 106 LFA Agl+CB: 9*2=18
Note on F24: VALI: LFA NRM and Data analystsl: 9*2=18 DPMU NRM Persons: 5

## LFA
|  | Note: Number of participants/ batch should be 25-35 depending upon the total number of participants | [17 empty] | If it is only one day write same day
Sl No | Theme | Sub Theme | Participants | Event | Duration | LFA | FA | FPO | Frequency of each round | Total No of Participants | [8 empty] | Start Date | End Date | Place | Res Persons | Remarks
[10 empty] | AF | HANDS | APMAS | FES | RASS | EFFORT | RHGBMSS | CSA | AAA
1 | FFS | FFS | Farmers @ 30 per Learning Site | FFS | 3-4 Hours | LFA | FA | Name | Fortnight | 360 | 360 | 360 | 360 | 360 | 450 | 270 | 270 | 360
2 | FFS | Training to Master Farmers | FFS Facilitators/ Master Farmers @ 11 per FA | Training | 3 days | LFA | FA | NA | Quarterly | 44 | 44 | 44 | 44 | 44 | 55 | 33 | 33 | 44
4 | BYP | Orientation | BYP Rearers @ 100 from Cluster | Training | 3-4 Hours | LFA | FA | Name | Fortnight | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 900 | 900 | 1200
5 | BYP | BYP | Service Providers @ 2/Cluster | Training | 2 days | LFA | NA | NA | Once | 24 | 24 | 24 | 24 | 24 | 30 | 18 | 18 | 24
6 | BYP | BYP | Service Providers @ 2/Cluster | Refresher Training | 1 day | LFA | NA | NA | Once | 24 | 24 | 24 | 24 | 24 | 30 | 18 | 18 | 24
11 | FPO | FPO Concept and Membership | FPO Governing Body Members | Training | 1 day | LFA | FA | NA | Once | 180 | 180 | 180 | 180 | 180 | 225 | 135 | 135 | 180
12 | FPO | FPO as PIA and Services | FPO Governing Body Members | Training | 1 day | LFA | FA | NA | Once | 180 | 180 | 180 | 180 | 180 | 225 | 135 | 135 | 180
13 | FPO | FPO Governance | FPO Governing Body Members | Training | 1 day | LFA | FA | NA | Once | 180 | 180 | 180 | 180 | 180 | 225 | 135 | 135 | 180
14 | FPO | FPO Management and Indicators for Good FPO | FPO Governing Body Members | Training | 1 day | LFA | FA | NA | Once | 180 | 180 | 180 | 180 | 180 | 225 | 135 | 135 | 180
15 | FPO | FPO Legal Compliance | FPO Governing Body Members | Training | 1 day | LFA | FA | NA | Once | 180 | 180 | 180 | 180 | 180 | 225 | 135 | 135 | 180
16 | FPO | FPO as CLICs and Business Service Provider | FPO Governing Body Members | Training | 1 day | LFA | FA | NA | Once | 180 | 180 | 180 | 180 | 180 | 225 | 135 | 135 | 180
20 | PGWM | Well inventory (for Identification of observation wells) | Cluster CRPs for GW +FA-NRM Facilitators and LFA CB+Agl; DPMU (LTA will place RPs; Max 10 participants in one training batch) | Hands on Training | 3 days | LFA | NA | NA | Once | 180 | 180 | 180 | 180 | 180 | 225 | 135 | 135 | 180
30 | CMSS | Orientation on Concept and Process of CMSS | FPO Sub Committee on CMSS | Training | 1 day | LFA | NA | NA | Once | 60 | 60 | 60 | 60 | 60 | 75 | 45 | 45 | 60
32 | CMSS | Book keeping in CMSS | FPO Accountant cum MVK Book Keeper; FPO Manager; 1 FPO Leader | Training | 1 day | LFA | NA | NA | Once | 36 | 36 | 36 | 36 | 36 | 45 | 27 | 27 | 36

## LFA CB Plan
Note: Number of participants/ batch should be 25-35 depending upon the total number of participants
Refer Previous sheet for total number of Participants for each LFA
Insert rows for more number of batches
Sl No | Theme | Sub Theme | Participants | Event | Duration | LFA | FA | FPO | Frequency of each round | Start Date | End Date | Place | Res Persons | Remarks
1 | Agriculture | FFS | Farmers @ 30 per Learning Site | FFS | 3-4 Hours | LFA | FA | Name | Fortnight |  | 0
2 | Agriculture | Training to Master Farmers | FFS Facilitators/ Master Farmers @ 11 per FA | Training | 3 days | LFA | FA | NA | Quarterly | 2018-08-28 | 2018-08-31
4 | Livestock | Orientation on BYP | BYP Rearers @ 100 from Cluster | Training | 3-4 Hours | LFA | FA | Name | Fortnight |  | 0
5 | Livestock | Strengthening BYP | Service Providers @ 2/Cluster | Training | 2 days | LFA | NA | NA | Once
6 | Livestock | Strengthening BYP | Service Providers @ 2/Cluster | Refresher Training | 1 day | LFA | NA | NA | Once |  | 0
11 | FPO | FPO Concept and Membership | FPO Governing Body Members | Training | 1 day | LFA | FA | NA | Once |  | 0
12 | FPO | FPO as PIA and Services | FPO Governing Body Members | Training | 1 day | LFA | FA | NA | Once |  | 0
13 | FPO | FPO Governance | FPO Governing Body Members | Training | 1 day | LFA | FA | NA | Once |  | 0
14 | FPO | FPO Management and Indicators for Good FPO | FPO Governing Body Members | Training | 1 day | LFA | FA | NA | Once |  | 0
15 | FPO | FPO Legal Compliance | FPO Governing Body Members | Training | 1 day | LFA | FA | NA | Once |  | 0
16 | FPO | FPO as CLICs and Business Service Provider | FPO Governing Body Members | Training | 1 day | LFA | FA | NA | Once |  | 0
20 | PGWM | Well inventory (for Identification of observation wells) | Cluster CRPs for GW +FA-NRM Facilitators and LFA CB+Agl; DPMU (LTA will place RPs; Max 10 participants in one training batch) | Hands on Training | 3 days | LFA | NA | NA | Once
30 | CMSS | Orientation on Concept and Process of CMSS | FPO Sub Committee on CMSS | Training | 1 day | LFA | NA | NA | Once |  | 0
32 | CMSS | Book keeping in CMSS | FPO Accountant cum MVK Book Keeper; FPO Manager; 1 FPO Leader | Training | 1 day | LFA | NA | NA | Once |  | 0

## Sheet2 (hidden)
Agriculture | FFS | Done
Agriculture | Other
Agriculture | Seed
Agriculture | Soils
Institutions | FPO: BoD
Institutions | FPO: Functionaries
Institutions | CLIC
Livestock | BYP
Livestock | Small Ruminant
Groundwater | PGWM
Other | Gender
Other | Equity, PoP