## Sheet1
Sr Name | Type of Activity | Brief of the Activity | If Any Report /Minutes of Meeting (Please Attach , Give file Name here) | No of Days Spend | Month
1 | Planning | 1. Planning for Preparation of FFS modules and material: Internal discussion about designing the FFS, pooling the material (Available), etc (4 days) 2. Planning for process monitoring design: Internal discussion (2 days) 3. Planning meeting for designing the Capacity Building strategy and interventions in APDMP: Internal meeting (2 days) 4. Preparation for APDMP inaugural workshop: Preparation for presentation on Convergence (1day) |  | 9 | April | 2, 3, 4, 6, 7, 10,12
2 | Training/ Meeting/Workshops | 1. Convergence Meeting with District Collector, Prakasam district (1 day) 2. Induction Training to the newly joined APDMP staff at S/DPMUs (Preparation and coordination: 5 days and actual training: 5 days) 3. Learning Site planning workshop (1 day) 4. SPMU office inaguration (1day) 5. Induction Training-Field Work 6. Presentation by participants about the learnings during induction training | 1. Convergence meeting with Dist Collector, Prakasam 12 Apr 2018.docx | 13 | April | 11, 14, 15, 16, 17, 18, 19-20, 23, 26-29
3 | Documentation/Posters/ Charts | 1. Preparation of Training modules for FFS 2. Module preparation for Induction Training |  | 1 | April | 4
4 | FieldVisit | 1. 100 Ha NRM Plans testing at Anantapur (1 day) | - | 1 | April | 2
5 | Documentation/Posters/ Charts | 1. Preparation of Training Cost Norms (1 day) 2. Preparation of CB Need Assessment Formats and Training Calendar Formats (1 day) 3. Discussion on Gender Strategy in APDMP | Training Calendar | 9 | May | 4, 8, 10, 17-22
6 | Training/ Meeting/Workshops | 1. FPO Module Writing Workshop 2. Coordination and Preparation of Modules on FPOs |  | 5 | June | 25-29
7 | Planning | 1 Discussion on CLIC Module |  | 1 | June | 25,
8 | Documentation/Posters/ Charts | 1. Coordination and Preparation of Modules on FPOs 2. Coordination for FPO Training plans with LFAs 3. FFS Resource Material | FPO Modules | 13 | July | 3-5, 13,14,15,16,17,19,20, 21,24, 30
9 | Training/ Meeting/Workshops | 1. ToT to Master Trainers on FFS 2. Discussion about Training plans on Livestock theme in APDMP |  | 4 | July | 10, 12, 17-18
10 | Planning | 1. Groundwater milestones and CB Plan |  | 2 | August | 4, 16
11 | Training/ Meeting/Workshops | 1. Workshop on FFS at SPMU 2. Women in Agriculture 3. Module on Protective Irrigation 4. ToT to Master Trainers on FFS at AFEC Trg Centre, Anantapur 5. Training to Master Farmers on FFS at FES, Madanapalli | Vali FFS Framework.docx Module on protective irrigaiton.docx | 10 | August | 8, 9, 13, 14; 20-21,25, 27-28, 29
12 | Documentation/Posters/ Charts | 1. Checklist for preparing case studies by training participants 2. Gender and Social Inclusion Strategy |  | 3 | August | 21-22, 27
13 | Training/ Meeting/Workshops | 1. Workshop on Livestock Rearers Field Schools at SPMU 2. Ground Water Collectivisation Meeting at SPMU 3. ToT on GW Collectivisation at AF-EC, Anantapur |  | 5 | September | 6, 7, 14, 18-19
14 | Documentation/Posters/ Charts | 1. FFS ToT Report Preparation 2. FPO Modules and material 3. PoP Identification formats |  | 6 | September | 4, 5, 9, 17, 29, 30
15 | Training/ Meeting/Workshops | 1. FPO Modules 2. Training Cost Norms 3. CWB Module and material development workshop @ SPMU 4. PoP identification field exercises in Kurnool and Kadapa districts 5. Training on Groundwater Collectivisation - 2nd batch |  | 11 | October | 4, 5, 6, 19, 22-24, 30-31; 10-11
16 | Planning | 1. Q3-Q4 Milestones planning meeting at LTA |  | 1 | October | 9,
17 | Training/ Meeting/Workshops | 1. ToT on CWB at AF-EC, Anantapur 2. Workshop on preparations for Rabi FFS at SPMU |  | 4 | November | 1, 2, 3, 14
18 | Documentation/Posters/ Charts | 1. Handouts on CWB 2. FPO office board designing 3. Training to FPO Staff |  | 4 | November | 6, 27, 28, 14
19 | Training/ Meeting/Workshops | 1. Video conference about IFAD mission visit |  | 2 | November | 26,
104

## Sheet2
April | Documentation/Posters/ Charts
May | Training/ Meeting/Workshops
June | FieldVisit
July | Planning
August | Others
September | Review of Staff Works