Note

A workshop on Institution development is held on 12-13 Jun 2018 at AF, Anantapur. Communication and Capacity Building Experts and Institution Development experts of LFAs; Institution Development experts of DPMUs, Gender Equity Enabler of SPMU and LTA representatives are present. During this workshop it was detailed to organise a separate workshop to develop modules on Institution building and prepare a capacity building plan on formation and strengthening the Farmer Producer Organisations (FPOs). In APDMP, 105 FPOs are formed in all clusters. Following are the type and number of stakeholders to be trained on Institutions Development

| Sl No | Type of Stake holder | No of participants | Remarks |
| --- | --- | --- | --- |
| 1 | Governing Body members of FPO | 9 to 15 members in each FPO | Training plan is prepared |
| 2 | FPO Manager | 105 | To be planned |
| 3 | FPO Accountant | 105 | -do- |
| 4 | CLICs Operator | 105 | -do- |
| 5 | FA Facilitator Institution and CB | 105 | -do- |

All the stakeholders need to be oriented on institutions development. As a first step, follow up workshop is organised during 26-29 July 2019 at APMAS to develop modules and material and schedule the capacity building plan on Institution development. 5 themes are identified for Governing body members and the training plan is prepared.

- FPO concept and membership

- FPO services as PIA, CLICs and Business services

- FPO governance

- Good practices and indicators for good FPO

- Legal Compliances

Similar to Governing body members, the training plan will be prepared for other stakeholders.

Following is the budget required for training the FPO Governing body members

- Batching: Each FA has formed 9 to 12 FPOs. Governing body members of 2 FPOs would be organised into one batch.

- Thus, about 53 batches would be required.

- No of training events is 5

- No of training events for 53 batches is 265

- No of days of training: 1 day for all 5 themes

- Cost of training the one batch of FPO Governing body members is: Rs 19000

- Total cost of training 265 batches of FPO Governing body members is: Rs 50.30 lakh