Capacity Building Need Assessment (CBNA) and Capacity Building Action Plan (CBAP) Preparation

Venue: O/o SPMU, APDMP, Guntur						Date:

Participants: Communication and Capacity Building Experts of all LFAs

Facilitation: Capacity Building Expert – WASSAN, LTA

Purpose: The technical experts of LFAs have prepared action plan for 1st year for all clusters. These action plans include plans for 100 ha, livestock, groundwater, establishment of CLICs, formation and strengthening Farmer Cooperative, establishment of Custom Hiring centre, development of common property resources, etc. There are functionaries at FA level, facilitators at Farmer Cooperative and project village level. In addition to them, FFS facilitators, master farmers will also be active performers in the project. Therefore, this CB plan will cover

- Functionaries at FA

- Facilitators at Project village/Farmer cooperative

- Master Farmers for FFS

- Farmer Cooperative Office bearers

- Trainers

Information about project is already communicated in some form to majority of households. Hence, instead conducting formal training to all project households, all project beneficiaries/farmer households will be covered through communication by CLICs and the result achieved from Learning site.

Process:

- All LFA CB coordinators will analyse the plans prepared by FAs for the year 2018-19

- Role and Responsibilities will be delineated for each functionary with regard to the planned interventions

- Existing capacities will be assessed for each person responsible in order to achieve the desired result. This will highlight a ‘particular capacity gap’ by absence of which it is difficult to achieve the desired result within the timeframe. CB Need Assessment document will be ready. (Format-1)

- All capacity building events will be listed out including training and non-training.

- Detailed action Plan will be prepared for all training and non-training CB events with the help of budget norms for training

- A list of available potential resource persons will be prepared. Training of Trainers will be planned.

- A detailed strategic CB plan will be ready

Note: All Participants should bring the copy of all plans prepared in the project villages.

Format 1: CB Need Assessment

| Sl No | Planned Intervention: |  | Key Result Indicator: |  |
| --- | --- | --- | --- | --- |
|  | Person/ Institution responsible to perform | Desired capacities | Present Capacity | Required Capacity |
|  | Person/ Institution responsible to facilitate/ enable |  |  |  |

Format 2: CB Action Plan

| Sl No | Theme | Sub Theme | Type of Participants | No of Participants | Type of CB Event | No of days | Tentative Dates | Venue | Resource Persons | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Format 3: Inventory of Training Centres

| Sl No | Venue | Place | Hall Capacity | Fans/ AC | Night Stay Accommodation capacity | WASH rooms (Separate/ Common/ Nil |
| --- | --- | --- | --- | --- | --- | --- |