Workshop on finalising Rearer Field School (RFS) Operationalisation

Date: 6-7 Sep 2018	Venue: SPMU, Guntur	Participants: Livestock Experts of LFA, LTA, SPMU

Special Guest: Dr Venkataramana: Additional Director, Agriculture, Directorate of AH

Introduction: All the participants introduced themselves.

Background: COO, Kripa Das welcomed all participants and gave the background of the meeting by reminding that the project has completed one year by this day. Dr Kulasekhar joined as Livestock expert in the SPMU team. He reiterated the need to speed up the livestock activities in the project. The major challenge is to follow the project implementation manual and trace the progress as per the Log frame. He also indicated to implement the activities with proper visibility and as per the field requirements in line with APDMP objectives. He also invited the participants to provide inputs to the project implementation plan and strategies as per the field reality. The quarterly plan for 3rd Quarter should be submitted to SPMU by 20th Sep. One day workshop is already conducted with DoAH and today the process is to be finalised to operationalise convergence plan to enhance the service delivery. He also informed that CLIC centres will start functioning in all 105 clusters at FPO offices by 10 October 2018.The target is to cover 115000 farmers (both crop farmers and livestock farmers) through Farmer Field Schools. About 31500 Livestock Rearers have to be covered by Livestock Rearers Field Schools (RFS).

Dr Venkataramana: Prevailing Severe drought condition is the right context to act upon augmenting livestock systems. Since the technology and processes are in advanced stage these days, all the functionaries and facilitators who work on livestock should also think and act using the available technology and improved processes. It is important to appraise the available resources and plan to utilise for mitigating the drought. He assured that the department is highly willing to contribute to the project as it also has objectives related to livestock. The list of FPOs formed in APDMP is available with the department. The more focus in 5 districts is to provide food and nutrition i.e. fodder and feed. The earlier plan was:

- Promoting mechanisation in conserving fodder in APDMP. There are three types of units ranging from Mega: Rs 2.2 cr, Medium: Rs 1 cr and Small: Rs 12 lakh, which medium and small units have 75%. For example, small size baler machine, mini silage units, front end harvesters, etc

- Prepare the plan based on the resources available, requirements, operational capacities, etc.

- Suggested the project teams to assess the requirement for next 4 months, especially to face the summer. He assured that the department will submit all the activities (end to end) related to fodder development.

- Discussed about OoruraPasuGrasaKshetralu (OPGK).

- Feed and fodder Inputs: Concentrated feed, TMR, chaff cutters, etc

- Gokulams: Infrastructure for cattle rearing in convergence with MGNREGS.

- The application process is also well defined. Suggested LFAs to understand eligibility criteria, application process and follow these standard processes to ease the constraints in convergence.

- Shared his experience in exploring the options for fodder production (in tanks, etc) and fodder preservation (instead burning). Timely acting up on is very essential.

- He assured complete cooperation from the department

- LFA-Aranya brought the findings from assessment of RLUs to the notice of Adnl Director

- Prakasam team requested to consider FPOs instead forming new FPOs/Cooperatives. But only Sheep cooperatives will be eligible for NCDS loan.

- Department requested MGNREGS to include patch for BYP, mini gokulams etc.

Agenda for today meeting

| Particulars | Priority | Schedule | Progress |
| --- | --- | --- | --- |
| - Back Yard Poultry |  | Day-1 FN |  |
| - Establishment of Breeder Farm | High |  | Complete |
| - Training the remaining Breeder Farm Entrepreneurs | High |  | Complete |
| - Training the Service Providers | High |  | Complete |
| - Mass Vaccinationin village | High |  | Complete |
| - Orientation to HHs | Medium |  | Complete |
| - Construction of Night Shelters | High |  | Complete |
| - Small Ruminants |  | Day-1 AN |  |
| - Para Worker Training | High |  | Complete |
| - Breed improvement programmes | Low |  |  |
| - Common land development | Low |  |  |
| - Preventive health care | High |  | Complete |
| - Insurance | High |  | Complete |
| - Medicine banks | High |  | Complete |
| - Drinking water in the context of existing drought | Medium |  | Complete |
| - Strengthening Veterinary institutions (RLUs, VDs/ VHs) | High |  | Complete |
| - Fodder development action plan to deal the drought | Medium |  | Complete |
| - Rearer Field School: Concept, design and Plan | High | Day-2 FN | Complete |
| - Others |  |  |  |

# Detailed Discussion

# Back Yard Poultry

## Establishment of Breeder Farm

Exposure is organised for the Entrepreneurs. Norms are prepared for establishment of BF and also the modalities for operationalising by BFE.

| Sl No | LFA | No of Clusters | No of BFEs trained | No of Breed Farms established | No of BFEs to be trained | No of clusters list ready | No of Clusters Rs 200 collected | No of Clusters Rs 200 deposited |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | APMAS | 12 | 4 |  | 8 | 6 | 6 | 0 |
| 2 | AFEC | 12 | 4 |  | 8 | 12 | 12 | 0 |
| 3 | HANDS | 12 | 4 |  | 8 | 6 | 6 | 0 |
| 4 | CSA | 9 | 2 |  | 7 | 7 | 7 | 5 |
| 5 | Aranya | 12 | 4 |  | 8 | 12 | 12 | 12 |
| 6 | RASS | 12 | 4 |  | 8 | 10 | 10 | 10 |
| 7 | FES | 12 | 4 |  | 8 | 12 | 12 | 6 |
| 8 | RHGBMSS | 9 | 3 |  | 6 | 9 | 9 | 0 |
| 9 | EFFORTS | 15 | 5 |  | 10 | 15 | 15 | 3 |
|  |  | 105 | 34 |  | 71 | 89 | 89 | 36 |

Points discussed

- Next batch Exposure date: Two persons (One Entrepreneur and LS facilitator) from each FA has already undergone exposure to Srikakulam/Paderu. It is expected that these participants started constructing the breeder farm infrastructure. Exposure would be conducted to remaining two entrepreneurs and LFA livestock Experts in the month of Oct 2018

- Local Desi breed shall be selected keeping the local requirements in view.

- Establishment of Breeder farms: Complete establishment of atleast one Breed Farm per FA by 30 Sep in all 35 FAs. Remaining 2 per FA will be proposed to complete in 3rd quarter.The budget for first breed/FA farm will be released to FPO.

- The design needs to be modified to be able to withheld to wind. The lateral support bars/pipe may be required in addition to the iron made poles. The cost of the unit needs to be revisited keeping the increased cost, modifications and the cost of labour. Rs 1.00 lakh support from the project is suggested by the participants.

- Procurement procedure: Any single item not exceeding Rs 1.50 lakh can be procured at FPO level.

  - The fund will be released to FPO.

  - A sub committee for BYP should be formed for procurement of material duly avoiding potential conflict of interests (such as BOD members, FA decision makers, etc) to secure the role of members. The composition of sub committee shall be as follow

    - Two representatives from FPO other than the cheque signatories

    - Breed Farm Entrepreneur

    - FA Coordinator

    - NRM expert of LFA

  - Specifications are provided to maintain quality and quantity.

  - Minimum of three quotations should be procured by the sub-committee and the lowest quote with specified quality shall be finalised.

  - The material supplier supplies to the entrepreneur which (quantity and quality as specified)

  - BFE should acknowledge the receipt of the material

  - LFA certify receipt of material as specified (quantity and quality)

  - LFA to ensure installation of the unit as per the specifications.

  - Payment will be paid by FPO through RTGS/Cheque to the material supplier

- It is observed that some of the LFAs are conditioning BYP rearers to become members of FPO for any further interaction/involvement in the project. Hence, it is suggested that while it is important to encourage all members to be part of FPO, BYP rearers shall be initially encourage to get involved in the project and subsequently in the FPO.

- Coverage: 300 HHs/Cluster @ 100 HHs/GP. BFE will be only one per cluster. The BFE should supply minimum 50% to the project beneficiaries exceeding which can be sold in the market by the BFE. In first year, the project js began with 100 rearer HHs and 1 BFE. Number of BFEs required will be decided based on the review of BYP theme at the end of the first year.

## Training the Service Providers

Service Providers modules will be provided to LFAs by 15th Sep 2018 by LTA. Flip calendar is to be provided to every Service Provider. There are 2 service providers for every cluster. It is suggested to take up the printing at central level. The cost norms for conducting trainings will be as per the norms approved and communicate by SPMU.

## Mass Vaccination in the village

It is decided to take up mass vaccination in the project villages to prevent RD and Fowl pox disease. The vaccine is available at Vaccine production centre, Samarlakota. DPMU in coordination with SPMU will arrange the vaccine available at LFA level. The vaccine should be administered in Nov 2018.

## Orientation to HHs on BYP

The BYP rearing HHs should be oriented on the potential of BYP and the basic precautions to be taken up. Livestock facilitator of FA will organise these village level orientations with the support from local VAS. The budget is provided in the BYP unit. However, it is desirable to conduct this training as part of Rearer Field School.

## Construction of Night shelters

The design should be uniform for all HHs. FPO will supply the material and give marking with the help of mason (engaged by FPO). The total cost of the unit is Rs 4590 and the project support is limited to Rs 3000/- only. Hence, the beneficiary should construct on her own or meet the balance of expenditure. Construction of night shelters in all clusters should be completed by 31st Dec 2018. All clusters should have plan for one full BYP unit within the 2nd quarter. The sub committee formed for Breeder Farm will be the same for constructing night shelter with adding two beneficiaries of night shelter.

# Small Ruminants

## Para worker Training (21 days)

There will be one para worker per every GP, who is identified from rearers’ households. His/her role is to conduct Rearers’ Field School (RFS).  First 7 days training should be conducted at LFA followed by next 7 days training at Veterinary Hospital. Considering the requirements in the project, the training is redesigned as mentioned.

| Sl No | Content | Duration | Remarks |
| --- | --- | --- | --- |
| 1 | Basic orientation on APDMP with specific focus on livestock interventions: | 3 days | LFAs with support from LTA |
| 2 | Technical Training (Theory): Basic orientation on Small Ruminants - Small Ruminant Management practices, basic anatomy, etc: - Diseases, preventive health care, first aid - Lamb and pregnant ewe management - Clinical Sample collection - Feed and Fodder management - Development of Commons - Breed Improvement - Reporting and Responding to outbreaks | 5 days | District/Regional Animal Husbandry Training Centre Responsibility: DPMU Cost norms to be developed by SPMU with support from LTA Material for para worker kit: (Approx Rs 3000/ Kit/ GP) - Vaccination kit - Vaccine carrier - Syringes, Needles and First Aid kit including thermometer, etc - Gloves, Protective Jackets and shoes |
| 3 | Practical Training: Internship with Local VAS - Deworming techniques - Storage and carrying vaccine - Vaccination skills - First Aid - Cold chain maintenance | 6 days | - SPMU is coordinating with Director AH. At district level, JDAH will give a letter to VAS for providing practical training to the para workers. - Cost of practical training: Honorarium to VAS (Rs 500/day), Working lunch and travel for para worker (Rs 150/day) |
| 3 | Service Delivery, Communication skills, customer management, Action plan, Coordination with FPO, Role and responsibilities, etc | 2 days | LTA |

- ‘GorrelaAarogyaParirakshana’and other relevant booksare available with publishing wing of directorate. 350 book sets are required including FA facilitators and Para workers.

- The protocol to purchase the para worker kit shall be finalised by SPMU.

- All CB related activities will be in the LFA CB plan

- LFA will conduct the CB activities including payment to training outside LFA (VAS, etc).

## Breed Improvement programme

Discussed above

## Common Land Development

Not discussed

## Preventive Health care

Disease surveillance protocol: FPOs and other interventions in APDMP have IT and database support to track the disease trends in all the 105 project mandals. This is supported by trained para workers and availability of timely and paid services at FPO level. All the rearers are potentially become the members of FPOs. This will help the project to understand and set a protocol to establish disease surveillance mechanism and thereby reduce the mortality rate.  This will certainly be helpful to Government to establish more appropriate service delivery mechanism that secures animals and the livelihood of the rearers.

Task for tomorrow: End results for Livestock stream in APDMP with a vision statement by keeping the following in view..

- Disease surveillance system: Contagious and parasitic disease (maps)

- Trained Para worker - based doorstep paid service delivery

- Institutionalising availability of all infrastructure, medicines and services

## Insurance

We have experience with insurance products offered by different insurance companies. Considering the difficulties in processing and honouring claims, it is decided to jointly design an insurance product alongwith insurance companies. It is also discussed whether to utilise the subsidy scheme available with the DoAH. The changes required:

- Product Development

  - Negotiate with national level insurance companies without the mediating agency.

  - Fixing sum assured per animal/flock

  - Negotiating the % of premium in the context of APDMP project for 5 years of period.

- Protecting the animal

  - with evidence based preventive health care and assured service delivery

  - Mobile based data base management

- Simplifying claim process

  - Decentralising/ Localising certifying the claims

  - Claim assessment process to be eased to reduce moral hazard

  - Waiving off the post-mortem requirements

## Medicine bank

It is decided that all CLICs will have small medicine shop with all basic drugs. LTA to work on modalities to operationalise this medicine bank. To overcome the license related protocols, LFAs with the support from DPMU will find a legally acceptable way. Dr Kulasekhar, SPMU will explore the options to facilitate FPO to get the required permissions. Meanwhile livestock experts of LFA and ADAH of DPMUs will explore options with Drug Inspectors in the respective districts.

## Drinking water in the context of existing drought

Construction of troughs for drinking water is an old experience. Most of these structures remained unused, empty and damaged due to variety of reasons. It is evident that filling the troughs is the major challenge. On other hand, water is not available where there is actual need for livestock. LFAs are requested to identify the locations where water is to be provided for livestock with appropriate type of storage/facility. Ravindra explained the Pune model of water tanker with ball valve (as arrangement in toilet flush tank). This infrastructure has to be created in grazing tracks as decided by the rearers. The water should be donated by a farmer and conveyance arrangement shall be from project funds. All LFAs agreed to pilot in anyone cluster/LFA and to be included in the plan for next quarter. LFAs will communicate the details of location by 20th September

# Strengthening Veterinary institutions (RLUs, VDs/ VHs)

Joint analysis of veterinary institutions is taken up by LFAs alongwith DPMUs.

| Sl No | Capital related | Capital O&M related | Suggested actions |
| --- | --- | --- | --- |
| 1 | - Storage facilitators, - Castrators, sterilizers, - Vaccine carriers, - Drenching guns, - Automatic vaccinators, - Store the vaccines | - Electricity Bills | - Explore alternatives (electricity) to maintain cold chains, bulk coolers, castrators for small ruminants, sterilizers, vaccine carriers, drenching guns, etc. |

Format for strengthening RLU/VH/VDs and Capturing the needs of CLICs(to be submitted by LFAs by 10 Sep 2018 to SPMU with a copy to LTA and DPMU)

LFA:			FA: 		Mandal:		Cluster:

| Sl No | Particulars | Answer/Quantity |
| --- | --- | --- |
| 1 | Type of Inst | RLU/VD/VH |
| 2 | Location (Address) |  |
| 3 | Contact Person |  |
| 4 | Designation |  |
| 5 | Phone |  |
| 6 | E-Mail |  |
|  | Requirements |  |
| 1 | Electricity Connection (Rs) |  |
| 2 | Refrigerator 250 L (No) |  |
| 3 | Bulk Cooler with stabiliser |  |
| 4 | Steriliser |  |
| 5 | Mouth Gag (Set) |  |
| 6 | Baby Microscope |  |
| 7 | Castrators Small |  |
| 8 | Castrators Large |  |
| 9 | Toothraspier |  |
| 10 | Vaccine carrier |  |
| 11 | Spring balance |  |
| 12 | Automatic vaccinator |  |
| 13 | Auto Drenching gun |  |
| 14 | Thawing machine |  |

Format for requirements in CLICs

| Sl No | Particulars | Answer/Quantity |
| --- | --- | --- |
| 1 | CLIC Location |  |
| 2 | Contact Person |  |
| 3 | Designation |  |
| 4 | Phone |  |
| 5 | E-Mail |  |
|  | Requirements |  |
| 1 | Refrigerator | 1 |
| 2 | Vaccine carrier | 3 |
| 3 | First Aid kit | 3 |
| 4 | Protecting Clothes | 3 |
| 5 | Baby microscope | 1 |
| 6 | Drenching gun | 3 |
| 7 | Spring balance (for growth monitoring) | 1 |
| 8 | Castrator for small ruminants | 3 |
| 9 | Slide Boxes | 6 |
| 10 | Any other (Specify)….. |  |

# Common Land Development and Fodder development action plan to deal the drought

It is certain that this year severe drought conditions are prevailing leading for acute shortage of fodder now and in coming months (summer). This will result in mortality of small ruminants, loss of weight, etc. APDMP should take this opportunity to demonstrate mitigating options even in fodder availability. The plan should include growing fodder in variety of locations including common lands, private lands and leased lands with protective irrigation facility; improved ways for production and preservation of feed and fodder. The plan should include fodder production and residue management. Seed can be sourced from the DoAH. The project is willing to invest on this which should become a long-lasting model finding permanent solution. If required, protective irrigation can also be planned to protect the fodder crop.

# Rearer Field Schools

- Objectives of RFS

- To improve reduction of mortality and morbidity rate

- Improving lambing rate

- Increasing birth weight

- Improvement of Body weight

- Reducing number of migration days through Fodder development

- Increasing In breeding

- Ways to achieve the objectives

- Organising shepherds into group of 10-12 rearers

| Sl No | Activity | Time (Min) |
| --- | --- | --- |
| 1 | Flock examination by the para worker and a report on - Physical appearance of flock: examination of eyes, ears, nose and mouth - Identification of sick animals - Enquiry on mortality - Observation of faeces (different faecal matter), ectoparasites - Specific symptoms of any disease | 60 |
| 2 | Data Entry on elite ewes, pregnant ewes, Body weight, Birth weight, Number of Lambs, size of the flock, mortality, Number of rams in flock, number of ewes, type of breeds in the flock, Breed of rams being used, true to type/pure breed in the flock. |  |
| 3 | Productivity - Identification of elite animals for continuous monitoring - Pregnant ewes - Checking the body weight of lambs and adults - Breed: True to Type, Ram breed, type of breed using for - Traditional knowledge (Indigenous Technology Know-how) - Disease surveillance |  |

- Agriculture FFS Model: Ms Praveena explained about the agriculture FFS model. The total number of farmers to be covered through FFSs is 115500. However, the actual possibility is estimated as 103950, of which 72450 will be through Agriculture FFS and 24150 through Livestock Rearer Field Schools. About 100 rearers will be covered from each of 105 clusters each year, summing to 31500 in 3 years.

| Sl No | RFS Topic | No of RFSs | Remarks |
| --- | --- | --- | --- |
| 1 | Departmental activities - Deworming - Vaccination | 6 | - Indent preparation and submission to VAS by LFA - Availability of dewormers and vaccines by DPMU - Delivery of vaccines and dewormers to paraworkers by FAs - Preparation of vaccination and deworming report by LFA |
| 2 | Disease surveillance,contagious and non-contagious diseases | 6 | Theory and practical sessions |
| 3 | Shelter | 3 | Theory and practical sessions |
| 4 | Feeding and water management | 6 | Theory and practical sessions |
| 5 | Pregnant animal care including lambcare | 6 | Theory and practical sessions |
| 6 | Breeding | 6 | Theory and practical sessions |

- Responsibility of activities: FA Livestock facilitator and Livestock para worker

- Support and Monitoring responsibility: LFA Livestock Expert

- Regular Activities in every RFS:

  - Review of previous session and action plan: 15 Min

  - Data Entry: 30 Min

  - Disease surveillance: 90 Min

  - Productivity: Body/Birth weight, practices, etc: 60 Min

  - Group Dynamics: 20 Min

  - Special topic (As per the need): 30 Min

  - Question and Answers: 30 Min

  - Action plan till next RFS: 15 Min

  - Conclusion: 10 Min

- Repository of Special topics:

  - Nutrition: Feed and fodder

  - Shelter Management

  - Management of pregnant ewes and lambs

  - Breeding

  - Drinking water

  - Insurance

  - Preventive health care wsrt Deworming and Vaccination in sheep

  - Government Schemes on Disease surveillance

- Number of Rearers to be covered through RFS

  - 30 per Gram Panchayat; 9450 rearers in 315 GPs

  - 10-12 rearers will form an informal group; i.e. 3 groups in every GP

- Coverage of women:

  - All the BYP rearers will be women: 100/ unit/Cluster >> 10500 women in the year 1 and 21000 women in the next 2 years

  - All (210) the service providers will be women in year 1 and 630 in 3 years

  - All (105) Breeding farm entrepreneurs will be women

- Design of conducting RFS:

  - Who will participate: It is estimated that there will be 30-35 rearers in a GP. These rearers will be organised into 3 groups of 8-10 each and the RFS will be conducted for 8-10Rearers (preferably from one habitation). RFS will be conducted in subsequent days covering the three groups.

  - Who will conduct: Para Worker

  - Who will organise Rearers: Community Organiser

  - Where will this happen: Flock

  - Who will provide technical support: FA livestock Facilitator

  - Who will monitor: LFA Livestock Expert

  - Frequency: Once in a month, preferably on 5th, 10th and 15th of every month (in case holiday, next working day)from December 2018 to March 2019 and continuation of this frequency will be based on the review to be conducted in March 2019

  - Total number of RFSs in a year for a group of 10-12 members rearers group

  - GP wise number of rearers to be mentioned by the LFA

  - Formation of group = 8-10 rearers per 1 group, 18-22 rearers per 2 groups,28-35 groups per 3 groups

  - Target: 1 RFS/Group/ month from Dec- March

- Pre RFS:

- Place of RFS to be decided: Field flock

- Mobilisation of rearers by Community Organizer (In case of non availability of community organiser, Para worker should organise rearers)

- Members should be willing to pay for services

- Shepherds should be registered for RFS

- Post RFS:

- Para worker will collect basic data (to be decided the data type, format and form)

- Para worker will submit the specified data/photo/information to Livestock Facilitator of FA.

- Livestock Facilitator of FA will certify and forward the same to FPO for payment to para workers for the services provided with a copy to LFA for information.

- Livestock specialist of LFA will compile the data and prepare a report for the project.

- Livestock Specialist of LFA should take up the issues identified through RFS to address either by him/herself or with the support of local VAS/ADAH

- Livestock expert of DPMU i.e. APD,DPMU will take the responsibility to address the issues with JDAH.

- List of rearers: It is decided that the list of rearers in each GP will be submitted by LFAs by 15 Sep 2018 in the format below:

| Sl No | FA | Mandal | GP | Habitation | No of shepherds | No of sheep | No of RFS groups |
| --- | --- | --- | --- | --- | --- | --- | --- |

The FAs, in later stages should also have the data-shepherd wise sheep/goats.

- List of the training programmes

- Para workers: a) 3 days on the project (by LFA CB expert and livestock experts), 5 days on livestock theme (in RAHTC/DAHTC), 6 days internship (At VAS/VD), 2 days action plan(by LFA CB expert and livestock experts)

- FA Livestock Facilitator and CB anchor: RFS concept and design (by LTA): 2 days

- LFA livestock Experts, Livestock experts of DPMU: Participatory Training Methodologies (PTMs by LTA): 2 days on 18-19 Sep 2018 at AFEC, Anantapur

# Other topics discussed in the presence of COO, APDMP

## Formation of Procurement committee

- Dr Kulasekhar from SPMU

- Representative from LTA

- Dr Prakash from DPMU, Anantapur

- Dr Janardhan from DPMU, Prakasam

- Dr Gopal Reddy from LFA-APMAS

## Convergence activities with MGNREGS:

Proposed list is shared with the participants for discussion and suggestions for inclusion.

## Innovative activities:

If there is any innovative intervention which will strengthen the efforts to mitigate drought impact, can be proposed with details of economics, costing, beneficiary share, convergence opportunities, etc shall be proposed to SPMU.

Advance fee for vaccination services

Livestock Expert from all LFAs