Action Plan of Livestock Programme

| SL NO | ACTIVITIES | JULY - SEPTEMBER |  |  | OCTOBER - DECEMBER |  |  | JAN - MARCH |  |  | REMARKS | SUPPORT REQUIRED FROM SPMU / LTA / DPMU |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | NO OF CLUSTER / UNIT | DEAD LINE | BUDGET | NO OF CLUSTER / UNIT | DEAD LINE | BUDGET | NO OF CLUSTER / UNIT | DEAD LINE | BUDGET |  |  |
| 0 | MAPPING THE LIVE STOCK CENSUS LARGE AND SMALL RUMINANTS |  |  |  |  |  |  |  |  |  |  |  |
| 1 | HEALTH CARE |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Situation analysis |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 | Gap identification |  |  |  |  |  |  |  |  |  |  |  |
|  | Infrastructure requirement at VD/RLU/cliks |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 | Selection of paraworkers |  |  |  |  |  |  |  |  |  |  |  |
| 1.4 | Training of paraworkers |  |  |  |  |  |  |  |  |  |  |  |
| 1.5 | 1st vaccination done by paraworkers |  |  |  |  |  |  |  |  |  |  |  |
| 1.6 | Record of vaccination submitted to clics and AHD on regular basis |  |  |  |  |  |  |  |  |  |  |  |
| 1.7 | Payment based system established |  |  |  |  |  |  |  |  |  |  |  |
| 1.8 | Site selection |  |  |  |  |  |  |  |  |  |  |  |
| 1.9 | GP resolution |  |  |  |  |  |  |  |  |  |  |  |
| 1.10 | Shelf of works |  |  |  |  |  |  |  |  |  |  |  |
| 1.11 | Sanction of shelters from NREGS |  |  |  |  |  |  |  |  |  |  |  |
| 2 | SMALL RUMINANT |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Orientation workshop on Tools and methodology of Situational Analysis |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 | Conducting baseline/ situation analysis |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 | Vaccination & health services delivered (regularized) |  |  |  |  |  |  |  |  |  |  |  |
| 2.4 | Identification & selection of paraworkers |  |  |  |  |  |  |  |  |  |  |  |
| 2.5 | Formation of SR informal groups |  |  |  |  |  |  |  |  |  |  |  |
| 2.6 | Integration of SR informal groups with FPO |  |  |  |  |  |  |  |  |  |  |  |
| 2.7 | Identification of Sites and beneficiaries, Preparation of Design and estimate, Approval |  |  |  |  |  |  |  |  |  |  |  |
| 2.8 | Preparation of Plan for the Panchayat and cluster |  |  |  |  |  |  |  |  |  |  |  |
| 2.9 | Habitation/ GP level meetings |  |  |  |  |  |  |  |  |  |  |  |
| 2.10 | Grazing lands identified |  |  |  |  |  |  |  |  |  |  |  |
| 2.11 | Fodder development on grazing lands |  |  |  |  |  |  |  |  |  |  |  |
| 2.12 | Social norms for grazing |  |  |  |  |  |  |  |  |  |  |  |
| 2.13 | Homestead lands |  |  |  |  |  |  |  |  |  |  |  |
| 2.14 | Cropping pattern change/ crop residue management |  |  |  |  |  |  |  |  |  |  |  |
| 2.15 | Identification and establishing Nursery Enterprise |  |  |  |  |  |  |  |  |  |  |  |
| 2.15.1 | Number of shepherds cultivating fodder |  |  |  |  |  |  |  |  |  |  |  |
| 2.15.2 | Fodder production by FPO |  |  |  |  |  |  |  |  |  |  |  |
| 2.15.3 | Tank bed cultivation |  |  |  |  |  |  |  |  |  |  |  |
| 2.15.4 | Experiment on crop residue management by LFA |  |  |  |  |  |  |  |  |  |  |  |
| 2.15.5 | Number of farmers having dense plantation of border rows with jowar/ bajra |  |  |  |  |  |  |  |  |  |  |  |
| 2.15.6 | Number of farmers having fodder trees in homestead lands |  |  |  |  |  |  |  |  |  |  |  |
| 2.16 | Formation of village level institutions |  |  |  |  |  |  |  |  |  |  |  |
| 2.17 | Identification of 1000 ewes & breeders |  |  |  |  |  |  |  |  |  |  |  |
| 2.18 | Demonstration of supplementary feeding in clusters |  |  |  |  |  |  |  |  |  |  |  |
| 2.19 | Training of Rearers through RFS (Rearers Field School) |  |  |  |  |  |  |  |  |  |  |  |
| 3 | BYP |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | Situational Analysis |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 | Identification of BYP Unit having poorest of poor |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 | Sensitization and mobilization of hhs into BYP |  |  |  |  |  |  |  |  |  |  |  |
| 3.4 | Monthly meeting of CIG & Book Keeping |  |  |  |  |  |  |  |  |  |  |  |
| 3.5 | Identification |  |  |  |  |  |  |  |  |  |  |  |
| 3.6 | Tor for FA |  |  |  |  |  |  |  |  |  |  |  |
| 3.7 | Conducting trg in coordination with AHD |  |  |  |  |  |  |  |  |  |  |  |
| 3.8 | Indent for vaccination |  |  |  |  |  |  |  |  |  |  |  |
| 3.9 | Plan of vaccination |  |  |  |  |  |  |  |  |  |  |  |
| 3.10 | Identification breed farm enterprise |  |  |  |  |  |  |  |  |  |  |  |
| 3.11 | Tor with FA |  |  |  |  |  |  |  |  |  |  |  |
| 3.12 | Training of entrepreneur |  |  |  |  |  |  |  |  |  |  |  |
| 3.13 | Initiate Construction of Breeding Farm |  |  |  |  |  |  |  |  |  |  |  |
| 3.14 | Monitoring of pop |  |  |  |  |  |  |  |  |  |  |  |
| 3.15 | Production & Selling |  |  |  |  |  |  |  |  |  |  |  |
| 3.16 | Training of HH |  |  |  |  |  |  |  |  |  |  |  |