## Slide 1
Implementation Guidelines
For Improved Livestock Production System –
BACKYARD POULTRY

## Slide 2
Process Steps for Implementation
Identification of Gram Panchayat for BYP units in a cluster
Formation of CIG
Formation of CIG
Membership Fees and Poultry Fund at FPO
Management and Transparency of Poultry Fund
Process of Setting Up of Desi Poultry Farm Enterprise
Technical Verification of Breeding Farm Enterprise by livestock specialist of LFA
ToR with Enterprise
Training of Entrepreneur
Business Plan of Breeding Farm Enterprise
Entrepreneur Contribution to Poultry Fund
Technical Specification
Development of Physical Infrastructure at Breeding Farm
Package of Practices at Breeding Farm
Monitoring and Record Keeping

## Slide 3
Process Steps for Implementation
Poultry Rearing at Household Level
Healthcare Service
Equipment for Service Providers
Modalities of Cost Recovery for Services
Training on PoP ( package of practices)by Livestock Facilitator
Adopting PoP
Pay to CIG’s Poultry Fund at FPO
Access to Night Shelter, Installments through FPO, Purchase Materials in Bulk and Supply to each household
Supplementary Feed by households to the Poultry
Identification of service providers
ToR with Service Providers, CIG and FAs
Training of Service Provider
Vaccination Database
Review and Monitoring
Vaccine Carrier
First Aid Medicine Kits
Mobile / Tab for Data collection
Pre-paid
CIG submits vaccination records to FPO
FPO pay to service provider

## Slide 4
Major Milestones of the Projects
Sl No | Milestone | Means of Verification | Time line
1 | Selection of Cluster | List of 100 households, Resolution of GP | 
2 | Selection of Entrepreneur | Resolution of FPO, Technical verification report, ToR with Entrepreneur | 
3 | Selection of Service Provider | Resolution of CIG, ToR with Vaccinator | 
4 | Formation of CIG | Resolution of CIG | 
5 | Opening of Leger of Poultry Fund in FPO account | Copy of Ledger account | 
6 | Construction of night shelter and Package of Practices at Breeding farm completed | Photographs, Data sheet | 
7 | Training of Service Provider | Training report, Training kits and materials | 
8 | Vaccination at Households and Breeding Farm | Vaccination records | 
9 | Start selling of chicks from Breeding farm | Data sheet | 
10 | Night Shelter at household constructed | Data Sheet of Households along with photographs | 
11 | Distribution of chicks to 100 HHs | Records | 
12 | 100 HHs rearing 4- Hens | Sample Data | 

## Slide 5
Household Night Shelter
Design and Estimates of Night Shelter at Household level

## Slide 6
Estimation of Household Night Shelter
House Hold Night Shelter |  |  |  |  | 
Estimate |  |  |  |  | 
Size 4'-0"x5'-0" |  |  |  |  | 
S.No | Description | Size | Area | Rate (Rs) | Amount (Rs)
1 | 2 | 3 | 4 | 5 | 6
1 | Cement Roofing Sheet | 6'-0"x6'-0" | 36 Sft | 20.00 | 720.00
2 | Cement Bag (no) | 1 |  |  | 310.00
3 | Mesh | 20'-0"x4'-0" | 80 Sft | 12.00 | 960.00
4 | Bricks (no) | 100 |  | 5.00 | 500.00
5 | Waterers and Feeders | 2 |  | 250 | 500.00
6 | Wood for Verticals | 8 nos | 6'-0" ht | 100.00 | 600.00
7 | Wood for Horizontals | 6 nos | 6'-0" ht | 100.00 | 600.00
8 | Door |  |  |  | 400.00
 |  |  |  | Total | 4590.00
Project will Support Cement Sheet, Cement Bag, Mesh, Bricks, waterers and Feeders

## Slide 7
Detail Project Investment
Sl No | Budget details | Units | Amount (Rs.) per cluster
1 | Infrastructure at household (Night shelter, waterer and feeders) | @ Rs.3000 per household; 100 HHs in a cluster | 300,000
2 | Training of household | Rs.200 per hh x 100 hh | 20,000
3 | Support for one Desi-Breed farms (fencing, shelter, developing foraging areas and initial birds costs) of about ½ acre. (with 25% contribution from the Breed farm owner in terms of labour, material, feed) – In pilot demonstration | Per Farm: Rs. 20000 for fencing, Rs. 45000 for shelter Rs. 15000 for feed supplementation Rs.15000 for birds Rs. 5000 for infrastructure (feederers, hatching baskets etc) | 100000
4 | Medicines and service charge of service provider | Rs. 6000 per year x 2 persons | 12000
5 | Collection of monitoring data including disease surveillance | @Rs.10 per hh per month x 100 hh x 24 months | 24000
6 | Technical support services of resource persons to breed farms and households | Rs.1000 per visit x 12 visit per year | 12000
7 | Training breed farmer | @5000 Rs. Per farmer | 5000
8 | Service providers training including vaccine kit | @ Rs.5000 per person x 2 persons | 10000
 | Total | Per cluster (1 Units) | 483000
1 Cluster – 1 BYP Unit
For 3 clusters = 3* 483000 =1449000
Scale up will be done through Bank linkages, in which subsidy for Breeding Farm will be 25 %

## Slide 8: Roles
FA-FPO prepare Proposal for 3 Units
LFA verify the proposal and certify that all pre-requisites are met
LFA submits FPO wise & Consolidated proposal to DPMU with a copy to SPMU
DPMU assess and recommend proposals to SPMU for sanction and budget release
SPMU sanctions proposals
DPMU releases budget to FPO against the sanctioned proposals
Training budget will be released to LFA against action plan