LIVESTOCK PROJECT CYCLE PLAN

(A)	LIVESTOCK HEALTHCARE SYSTEM

OBJECTIVES:

- Establishing Community Managed Animal Healthcare System integrated with Animal Husbandry Department

SPECIFIC OBJECTIVES:

- Providing Vaccination and preventive healthcare at the door step

- Building local capacities for providing preventive healthcare services

- Reduce mortality of large ruminant by 5% from present state

| OUTPUT | MILESTONE | INDICATOR | ACTIVITIES | REPONSIBILITY | TIMELINE | CAPACITY BUILDING | SUPPORT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DECENTRALIZED HEALTHCARE SYSTEM | Report of Situation analysis |  | Situation analysis | FA & LFA | 30th june | FA and LFA's Livestock Staff | LTA for Tools of Situational Analysis |
|  | CLICS/ RLUs equipped with facilities, medicines, vaccine storage etc | Stock record of RLU/ CLICs | Gap identification |  | 30th August | CLICs staffs on record keeping , storage and cold chain maintenance | AHD for supply of vaccines & medicines |
|  | Require HR/ paraworkers are trained and placed | Training report | Selection of paraworkers | FA & LFA supported by AHD and LTA |  | Para workers |  |
|  |  |  | Training of paraworkers | LFA, FA |  |  | AHD, DPMU, RAHTC |
|  |  |  | 1st vaccination done by paraworkers | Para worker & FA |  |  |  |
|  |  |  | Record of vaccination submitted to CLICs and AHD on regular basis | Para worker & FA |  |  |  |
| REDUCTION OF MORTALITY BY 5% FROM BASELINE | Data based established for capturing data on services and mortality | Web based Data base | Payment based system established | Para worker & FA |  | Para workers on Data Management | DPMU, LTA |
| DEVELOP SHELTER PLAN AND INTEGRATE WITH NRM PLAN | Plan submitted | Designs and estimates worked out | Site selection | FA with LFA, LTA |  |  | SPMU, NREGS |
|  |  |  | GP resolution | FA |  |  |  |
|  |  |  | Shelf of works | LFA |  |  |  |
|  |  |  | Sanction of shelters from NREGS | SPMU/DPMU |  |  |  |

(B)	SMALL RUMINANT

OBJECTIVES:

- Strengthening small ruminant production system

SPECIFIC OBJECTIVES:

- Productivity enhancement in SR production system by ensuring preventive healthcare and fodder and drinking water security

- Mortality reduction by 10% of the baseline

| OUTPUT | MILESTONE | INDICATOR | ACTIVITIES | REPONSIBILITY | TIMELINE | CAPACITY BUILDING | SUPPORT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SITUATION ANALYSIS AND BASELINE REPORT | Availability of cluster profile | Situation analysis completed | Orientation workshop on Tools and methodology of Situational Analysis | LFA and LTA | 30th june | Staff of FA and LFA | Tools for situation analysis - LFA/LTA |
|  |  |  | Conducting baseline/ situation analysis | FA | 30th june | Orientation | Tools for situation analysis - LFA/LTA |
| REDUCTION OF MORTALITY BY 10 % FROM CURRENT STATE | para workers are trained | Para workers submitted report of vaccination to CLICs and VD/RLU | Vaccination& health services delivered (regularized) | FA | 31st August | CB for para workers | AHD, RAHTC, LTA |
|  | Fully equipped RLUs/CLICs in all clusters | Availability of trained Paraworkers in all clusters | Identification& selection of paravets | FA | 30th September |  |  |
| REVIVE SR INTITUTIONS | Informal groups of reares formed | Payment system established | Formation of SR informal groups | FA | 30th September |  |  |
|  |  |  | Integration of SR informal groups with FPO | LFA | 31st October |  |  |
| MODEL NIGHT SHELTER (1 PER GP) | Construction of Model Night Shelter completed |  | Identification of Sites and beneficiaries, Preparation of Design and estimate, Approval | FA | 31st December |  | LTA for Design support |
| SCALE UP NIGHT SHELETER BY INTEGRATING IN MGNREGS | Submission of proposals to NREGS | Gramsabha resolutions and listed under self work | Preparation of Plan for the Panchayat and cluster | FA |  |  | NREGS |
| AVAILABILITY OF FODDER& WATER IN ALL SEASONS | Submission of proposals to MRO for PoB entry | GP resolution | Habitation/ GP level meetings | FA |  | Trainings on fodder/ CPR development | from FES |
|  | Integrating MGNREGS/ watershed programme |  | Grazing lands identified | FA |  | Exposure visits to CPR blocks, fodder development | MGNREGS/IWMP/ Drinking water |
|  | Proposed water bodies for renovation under MNEGS approved by GP |  | Fodder development on grazing lands | FA |  |  |  |
|  |  |  | Social norms for grazing | FA |  |  |  |
|  |  |  | Homestead lands | FA |  |  |  |
|  |  |  | Cropping pattern change/ crop residue management | FA |  |  |  |
|  |  |  | Identification and establishing Nursery Enterprise | FA |  |  |  |
|  | Growing of fodder by Small Ruminant rearers | Number of shepherds growing fodder | 1gp / cluster | FA | 18th October |  |  |
|  | Community fodder production | 10-20 acres of land having fodder | FPO growing fodder in leased land | FA | 31st October |  |  |
|  |  |  | Tank bed cultivation | FA | 31st March |  |  |
|  | Experiment on crop residue management through FPO | 1 experiment |  | LFA | 31st December |  |  |
|  | Dense plantation of jowar and bajra in Navadhanya | Number of farmers having dense plantation in border rows |  | FA | 30th October |  |  |
|  | Cultivation of fodder trees in homestead lands of shepherds | 75% shepherds having plants in homestead lands | Plantation of 5-20 plants in homestesd lands | FA | 31st August |  |  |
| ADOPTION OF SUPPLEMENTARY FEEDING FOR EWES/ DOES |  | List of breeder and numbers of does/ewes submitted to CLiCS | Formation of village level institutions | FA |  |  |  |
|  |  |  | Identification of 1000 ewes& breeders | FA |  |  |  |
|  |  |  | Demonstration of supplementary feeding in clusters | FA |  |  |  |
| IMPROVING PRODUCCTIVITY | Farmers Adapted PoP for improving productivity | No of PoP adopted by the farmers | Training of Rearers through FFS | FA | 31st March | SR Rearers | AHD, LTA |

(C)	DESI BACKYARD POULTRY (BYP)

OBJECTIVES:

- To improve the income and Family Nutrition in the poorest of the poor families in APDMP

SPECIFIC OBJECTIVES:

- Strengthening local health care systems / services

- Developing decentralized chick production and distribution system

| OUTPUT | MILESTONE | INDICATOR | ACTIVITIES | REPONSIBILITY | TIMELINE | CAPACITY BUILDING | SUPPORT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- | --- |
| HELPING EACH HH HAVING 4-5 HENS IN THE CLUSTER (BYP UNIT) | Formation of CIG Depositing CIG money in FPO account | Collection of contribution to | Situational Analysis | Respective FA | 30th July | Orientation and exposure visit | LTA, LFA, APDMP/AHD |
| INCREASE INCOME - DOUBLE FROM BASELINE. RS. 4-5000/ANNUM | HHs adopt improved management practices - Night shelter, supplementary feed, regular deworming & vaccination | Able to sell 10-12 birds apart from own contribution in a year per HH | Identification of BYP Unit having poorest of poor |  | 30th October | Communication (IEC) material | Tools for situational analysis |
|  |  |  | Sensitization and mobilization of HHs into BYP |  |  |  |  |
|  |  |  | Monthly meeting of CIG & Book Keeping |  |  |  |  |
| AVALABILITY OF ATELASET TWO TRAINED PERSON AT BYP UNIT LEVEL | Training of identified persons | Providing health care services in the BYP unit | Identification | FA supported by LFA | 30th September | Baseline training | Module on BYP vaccinator from LTA /AHD |
|  |  |  | ToR for FA |  |  | Database on BYP health care |  |
|  |  |  | Conducting trg in coordination with AHD |  |  |  |  |
| ABLE TO DECREASE MORATALITY RATE BY 50% OF PRESENT STATUS | Vaccination on every fortnight | Vaccination report | Indent for vaccination | CIG supported by FA | 30th July | Data formats | 1. AHD for vaccine 2.CLIC/FPO |
|  |  |  | Plan of vaccination |  |  |  |  |
| ESTABLISHMENT OF BREEDING FORM | Construction of Package of Practices | Selling of Chicks | Identification | FA /LFA | 30th July | Training for Entrepreneur /FA | 1. AHD 2.LTA 3. External Resource Person |
|  |  |  | ToR with FA |  |  |  |  |
|  |  |  | Training of entrepreneur |  |  | Entrepreneur |  |
|  |  |  | Initiate Construction of Breeding Farm | FA |  |  | External Res Person |
|  |  |  | Monitoring of PoP |  |  |  |  |
| DISTRIBUTION OF CHICKS TO THE CIG HHS | 25% of target group by 2 months | Rearing of Chicks of CIG member | Production & Selling | Entrepreneur/ CIG with the support of FA, HH in BYP | 31st December | Training to HH | FA & FPO for marketing support |
|  | 50% by 5 months |  | Training of HH through FFS process |  |  | IEC |  |
|  | 100% by 12 months |  |  |  |  | Regular inputs to breeding farm module |  |

Note : Monthly vaccine report from august is to be submitted.