## Health services
LIVESTOCK PROJECT PLAN - LIVESTOCK HEALTHCARE SYSTEMS
OBJECTIVE | Establishing Community Managed Animal Healthcare System integrated with Animal Husbandry Department
Specific Objectives | Providing Vaccination and preventive healthcare at the door step
Building local capacities for providing preventive healthcare services
Reduce mortality of large ruminant by 5% from present state
OUTPUT | MILESTONE | INDICATOR | ACTIVITIES | REPONSIBILITY | TIMELINE | CAPACITY BUILDING | SUPPORT REQUIRED
Decentralized healthcare system | Report of Situation analysis |  | Situation analysis | FA & LFA | Feb& Mar'18 | FA and LFA's Livestcok Staff | LTA for Tools of Situational Analysis
| CLICS/ RLUs equipped with facilities, medicines, vaccine storage etc | Stock record of RLU/ CLICs | Gap identification |  | Feb& Mar'18 | CLICs staffs on record keeping , storage and cold chain maiantenance | AHD for supply of vaccines & medicines
| Require HR/ paraworkers are trained and placed | Training report | Selection of paraworkers | FA & LFA supported by AHD and LTA | Feb& Mar'18 | Para workers/Para vet/gopal mitra
|  |  | Training of paraworkers | LFA, FA | May'18 |  | AHD, DPMU, RAHTC
|  |  | 1st vaccination done by paraworkers | Para worker & FA | June'18
|  |  | Record of vaccination submitted to CLICs and AHD on regular basis | Para worker & FA | July'18 onward
Reduction of mortality by 5% from baseline | Data based established for capaturing data on services and mortality | Web based Data base | Payment based system established | Para worker & FA | July'18 onward | Para workers/Para vet/gopal mitra on Data Managemet | DPMU, LTA
Develop shelter plan and integrate with NRM plan | Plan submitted | Designs and estimates worked out | Site selection | FA with LFA, LTA |  |  | SPDMU, NREGS
|  |  | GP resolution | FA
|  |  | Shelf of works | LFA
|  |  | Sanction of shelters from NREGS | SPMU/DPMU
** Group discussed about need of work on conservation of native breeds whicha are more adapted in local conditions and have more resilient capacities in climate change. The same may be integrated with clusters overlapped with ZBNF as a Pilot basis. Detail Project Cycle can be developed once principally approved by APDMP.

## SR
SMALL RUMINANT PROJECT PLAN
OBJECTIVE | Strengthening small ruminant production system
Specific Objectives | Productivity enhancement in SR production system by ensuring preventive healthcare and fodder and drinking water security
Mortality reduction by 10% of the baseline
OUTPUT | MILESTONE | INDICATOR | ACTIVITIES | REPONSIBILITY | TIMELINE | CAPACITY BUILDING | SUPPORT REQUIRED
Situation Analysis and Baseline report | Availability of cluster profile | Situation analysis completed | Orienetation workshop on Tools and methodology of Situational Analysis | LFA and LTA | Feb'18 | Staff of FA and LFA | Tools for situation analysis - LFA/LTA
|  |  | Conducting baseline/ stituation analysis | FA | March/April'18 | Orientation | Tools for situation analysis - LFA/LTA
Reduction of mortality by 10 % from current state | Para vet / para workers are trained | Para workers submitted report of vaccination to CLICs and VD/RLU | Vaccination& health services delivered (regularized) | FA | Paravet training programme May'18 | CB for paravets/para workers | AHD, RAHTC, LTA
| Fully equipped RLUs/CLICs in all clusters | Availability of trained PW/GM/P.vet in all clusters | Identification& selection of paravets | FA | March/April'18
Revive SR intitutions | CIG of reares formed | payment system established | Formation of SR CIG | FA | April'18
|  |  | Integration of SR CIG with FPO | LFA | June'18
Model night shelter (1 per GP) | Construction of Model Night Shelter completed |  | Identification of Sites and beneficiaries, Preparation of Design and estimate, Approval | FA | October'18 (some may start early) |  | LTA for Design support
Scale up Night Sheleter by integrating in MGNREGS | Submission of proposals to NREGS | Gramsabha resolutions and listed under self work | Preparation of Plan for the Panchayat and cluster | FA | October'18 |  | NREGS
Availability of fodder& water in all seasons | Submission of proposals to MRO for PoB entry | GP resolution | Habitation/ GP level meetings | FA | March'18 | Trainings on fodder/ CPR development | from FES
| Integrating MGNREGS/ watershed programme |  | Grazing lands identified | FA | March'18 | Exposure visits to CPR blocks, fodder development | MGNREGS/IWMP/ Drinking water
| Proposed water bodies for renovation under MNEGS approved by GP |  | Fodder development on grazing lands | FA | Nov/Dec'18
|  |  | Social norms for grazing | FA | Nov/Dec'18
|  |  | Homestead lands | FA | Nov/Dec'18
|  |  | Cropping pattern change/ crop residue management | FA | Nov/Dec'18
|  |  | Identificationa and establishing Nursery Entreprise | FA | Dec'18
Adoption of supplementary feeding for Ewes/ Does |  | List of breeder and numbers of does/ewes submitted to CLiCS | Formation of village level institutions | FA | Aug'18
|  |  | Identification of 1000 ewes& breeders | FA
|  |  | Demonstration of supplementary feeding in clusters | FA
Improving Producctivity | Farmers Adapted PoP for improving productivity | No of PoP adopted by the farmers | Training of Rearers through FFS | FA | July'18 onwards | SR Rearers | AHD, LTA
** Breed Improvement Programe to be taken up from 2nd year of the project

## Desi BYP
Theme: Back Yard Poultry in Livestock Component
| Objective: | To improve the income and Family Nutrition in the poorest of the poor families in APDMP
| Specific Objectives | · Increase in productivity & backyard poultry at HH Level
· Strengthening local health care systesm/services
Developing decentralized chick production and distribution system
No | Out Puts | Mile Stone | Indicator | Activities | Responsibilities | Time Lines | Capacity Building | Support Required
( Agency & Type)
1 | Helping each HH having 4-5 hens in the cluster (BYP Unit) | Formation of CIG | Collection of contribution to | Situtational Analysis | Respecitive FA | Feb end | orientation and exposure visit | LTA, LFA, APDMP/AHD
2 | Increase income - Double from baseline.Rs. 4-5000/annum | HHs adopt improved management practices - Night shelter, supplementary feed, regular deworming & vacination | Able to sell 10-12 birds apart from own contribution in a year per HH | Identification of BYP Unit having poorest of poor |  | Feb end | Communication (IEC) material | Tools for situational analysis
|  |  |  | Sensitization and mobilization of HHs into BYP |  | March
|  |  |  | Monthly meeting of CIG & Book Keeping |  | April onwards
3 | Avalability of atelaset one trained person at BYP unit level | Training of identified person | Providing health care services in the BYP unit | Identification | FA supported by LFA | Feb end | Baseline training | Module on BYP vaccinator from LTA /AHD
|  |  |  | ToR for FA |  | Feb end | Database on BYP health care
|  |  |  | conducting trg in coordination with AHD |  | Mid april
4 | Able to Decrease moratality rate by 50% of present status | Vaccination on every fortnight | Vaccination report | Indent for vaccination | CIG supported by FA | From April (monthly twice) | Data formats | 1. AHD for vaccine 2.CLIC/FPO
Plan of vaccination
5 | Establishment of Breeding form | Construction of Package of Practices | Selling of Chicks | Identification | FA /LFA | Feb end | Training for Enterprenuer /FA | 1. AHD 2.LTA 3. External Resource Person
|  |  |  | ToR with FA |  | Feb end
|  |  |  | Training of enterprenuer |  | Mar End | Entreprenuer
|  |  |  | Initiate Construction of Breeding Farm | FA | April onwards |  | External Res Person
|  |  |  | Monitoring of PoP |  | June End
6 | Distribution of Chicks to the CIG HHs | 25% of target group by 2 months | Rearing of Chicks of CIG member | Production & Selling | Enterprenuer/ CIG with the support of FA, HH in BYP | Aug | Training to HH | FA & FPO for marketing support
|  | 50% by 5 months |  | Training of HH through FFS process |  | Nov | IEC
|  | 100% by 12 months |  |  |  | 2019-07-01 | Regular inputs to breeding farm module