Andhra Pradesh Drought Mitigation Project (APDMP)

Farmer Learning and Action (FLA)

(This document details on mechanism of organising Farmer Learning and Action, finalizing team, core teams and finalizing approximate budget for the FLA.)

Introduction: Farmer Learning and Action is an approach where farmers are trained on climate resilient agriculture production systems by discovery and experiential learning and use of Non-Formal Education methods.

FLA will be held every fifteen days once in a selected learning site where group of 20-25 farmers will attend regularly on fixed day. At the end of 24 sessions, interested and communicative farmers will become master farmers for the coming year to run FLA in learning sites with minimal support of staff facilitators.

FLA Curriculum would be based on the present climatic situation, season and interventions proposed in the project and at the end farmers and facilitators will arrive with some action points in the field to carry out for the coming fortnight and review it in the next FLA session. By doing so farmers would gain the skills and knowledge of the proposed activities in the project on climate resilient agriculture.

Objectives of FLA:

- To develop master farmers to conduct FLA in the learning site with minimal support of external facilitators.

- To encourage “farmer to farmer learning approach” by integration of various sectors including natural resources such as soil, water, crop and sustainability through institutions such as CLiCs, CHC and FPO.

- To identify the action points in each FLA and encourage to implement in the respective individual’ fields.

- To develop Participatory adaptive research on identified key issues in the project area.

Design of FLA:

Climate Resilient Agriculture will be taken up in 250 acres of a sub-watershed area in a cluster – denominated as “Learning Site”. This site will be geographically divided in two parts, in which FLA sessions will be organized separately.

- FLA will be conducted in 100 ha site. For operational purpose, this site is divided into 50 ha each. In each site separate FLA will be organised once in every 15 days throughout the year. One master farmer is needed to conduct FLA in 50 ha. Therefore, from every learning site 2 farmers should be trained as master trainers to conduct FLA. In case of absence of any master trainer on any FLA, there should be one more master farmer who could conduct FLA as per the schedule. Hence, total 3 farmers from each learning site should be trained. One of them must be a woman farmer.

- Their key responsibility is to facilitate one FLA on a fortnightly basis and support 20 -25 farmers in implementation of the plans arrived at FLA. Master Farmers will implement all the plans first in their own fields.

- Farmers will be registered into the FLA. They will be encouraged to join FPO by paying share capital of not less than Rs.1000 per member. In case of poor households, the same can be collected in instalments.

- Key activities in the FLA are:

  - Weather monitoring (Rain gauge installed at CLICs)

  - Agro Eco System Analysis

  - Review of the previous plans

  - FLA-Inputs-Session – on the topic of the season; farmer-resource persons may also be invited for these session

  - Planning tasks for the next fortnight.

- At field level, Agriculture Facilitator of Facilitating Agency (FA) is responsible for conducting FLA. Each Agriculture Specialist is responsible for conducting FLAs in all the three learning sites. (Total 3 Learning sites * 2 groups * 2 FLAs/month = 12 FLAs in every month)

- Beyond the Learning-Site, if any farmer intends to take up the practices – the services/ linkages will be provided through CLiCs

Process of FLA:

There are two steps in the FLA- implementation process:

- Pre-FLA Planning: Baseline survey and Situation analysis (NRM, Crop System, Inputs, farm implements/machinery and Irrigation)

- Fortnightly FLA on field and at CLIC.

- Preparations for FLA (Planning):

Following activities are to be completed before the start of FLAs

- Demarcation of 100 ha area

- Registration of farmers and mobilising farmers into FPO; it is mandatory for the Master Farmers

- Learning Site Plans are ready:

  - NRM Planning: A detailed plot mapping of the area with all the baseline data needs to be completed. This exercise results in

    - Baseline data with a detailed map where plots are linked to farmers.

    - NRM Plans that can be integrated into MGNREGS

    - Critical interventions to be supported by APDMP (critical but MGNREGS do not have adequate provision.

  - Soil fertility plans

  - Crop systems & Seed plan and

    - Pest and disease surveillance & input plans

    - Farm mechanization/ implements for timely operations

    - Protective irrigation plans

    - Establishing weather monitoring and visualization and groundwater monitoring systems

- Selection of Lead Farmers (one female and two male in each sub-FLA site):

- Plans with Budgets: The above plans will be developed for the entire FLA area along with budgets, and approvals will be taken from DPMU. This will be a yearlong plan. In the budget a provision of Rs.?? For each FLA will also be included.

- During FLA conducting at learning site:

- Schedule: The frequency of FLA is once in a fortnight. FLA should happen with 15 days of interval. The time can be fixed by the farmers according to their convenience. But, morning time is very conducive for both farmers to spend time in the field as well as for identification of pests and diseases in the field. Therefore, 7:00 AM to 12:00 noon is the ideal time.

- Meeting Place: Most of the FLAs will be held in the learning site. If required, the projector, board, chart papers, posters, etc. should be carried to the learning site during FLA. Some of the FLAs (on theory) can be organised at CLICs using Audio-visual equipment. If it is important to show some videos after FLA, FLA can be extended to CLICS. with facilities for 20 persons to sit, project videos through Pico Projector.

- Communication Tools to be used: LTA will develop all communication tools for FLAs. However, LFAs and FAs are also encouraged to collect, prepare and use the tools wherever appropriate and necessary

  - Flip charts – for the relevant themes

  - Demonstrations

  - Specimens: herbarium / insect library to be prepared during FFS

  - Videos

  - Mobile (brought from CLiCs).

  - Pico Projector with screen

  - FLA- Tool kit (magnifying glass, vials etc.) @Rs.1500 max.

  - Stand (foldable board) with charts and clips; marker pens / brown sheets.

  - FLA- Register

- Production of Relevant Videos:

  - Each LFA – Identify persons with aptitude to be developed as Video Resource Persons or tie up with CRZBNF video resource persons trained by Digital Green.

  - A centralized video editing support be created at LTA level to provide backend support. Along with training the computer persons in FA / LFA on simple video editing tools.

Indicators of successful FLA

- List of good practices followed in each learning site

- Cadre of experts/resource farmers trained/available

Team Structure

- There are 105 learning sites in APDMP.  Each site contains 100 ha. It is expected that “Farmer Learning and Action (FLA)” would be facilitated to bring out the expected achievements and spread these learnings to other sites in the village, eventually. These FLA activities will be held once in every fortnight dividing the Learning Site farmers into 2 batches. Thus, the total number of FLAs in each Learning site is 48. Total number of FLAs in all Learning sites across APDMP is 5040 (48*105). Budget for 5040 FLAs is provided at Annexure 1.

- It is expected that one of the results of the FLA would be list of action points. Therefore, it is desirable that all facilitators shall be present during the FLA. All functionaries of FA would be present to facilitate interventions related to their core function.

- The services of community resource persons can be utilised for the tasks related to organising farmers, etc

- For facilitation of each FLA on regular basis, 2 master farmers are required. These farmers will be identified from learning sites who have relatively better orientation to APDMP practices. One of them must be women farmer. Keeping the possibility of absence by one of them on any event, it is important to train atleast 3 farmers as Master Trainers. Thus, the total master farmers required is 105*3 = 315. In addition to these master farmers, agriculture facilitators from FAs will join in the respective batches. About 14 batches is required to train these 385 Master Farmers (315 master + 35 FA Agriculture Facilitators and 35 FA NRM Facilitators). These master farmers would be trained in rounds. Each round will cover content of 3 FLAs. Thus, to cover 24 FLAs, 8 rounds are required.  Budget for training 385 Master Farmers in 15 batches * 8 rounds (Total training events is 120) is provided at Annexure 2.

- Total number of Master trainers required is 36 (@ 3/batch). LFA would nominate 3 persons (atleast one woman) for training. Pool of Master Trainers will be formed with these 36 master trainers and 9 CB experts from LFAs. Thus, the total number of master trainers in the pool would be 45 (Atleast 12-15 women). The training would be conducted in 2 batches. These master farmers would be trained in rounds. Each round will cover content of 3 FLAs. Thus, to cover 24 FLAs, 8 rounds are required.  Budget for training 45 Master Farmers in 2 batchers * 8 rounds is provided at Annexure 3.

- A core APDMP team is formed to design FLA. The role of this team is to design curriculum, organize training of Master Trainers, Scheduling FLA, etc. This core team will manage FLA at project level. Eventually more persons could be part of this core team. Their main objective would be to standardize FLA and train 45 Master Trainers. This team will include

  - Mr Nunna Venkateswarlu, SPMU

  - Mr Subramanyeswara Rao, DPMU-Chittoor

  - Mr I Murali, DyPD, DPMU, Kadapa

  - Mr Rajasekhar, LFA-CSA

  - Mr Chandra Sekhar, LFA-CSA

  - Ms Padma, LFA-AAA, Kurnool

  - Mr SS Kandagal, LTA-WASSAN

  - K Jayaram, LFA-APMAS

  - Dr Yalamanda Reddy, LFA-AF

  - M Bhakthar Vali, LTA

  - A Ravindra, LTA

- This core team will organize the training of 45 Master trainers in 2 batches running simultaneously.

- There would be 20-25 members in each batch.

- Each training would be for 3 days.

| Table: Number of participants in each level of training |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl No | District | No of FAs | No of Learning Sites | No of master farmers to be trained | No of FA Agriculture Facilitators + NRM Facilitators | Total master Trainers for FLA | No of batches Required | No of Master Trainers to be trained by Core Team | No of CB Experts of LFAs | No of Master Trainers to be trained |
|  |  | (1) | (2) | (3) | (4) | (3)+(4) = (5) | (6) | (7) | (8) | (7)+(8) = (9) |
| 1 | Anantapur | 12 | 36 | 108 | 24 | 132 | 5 | 12 | 3 | 15 |
| 2 | Kurnool | 7 | 21 | 63 | 14 | 77 | 3 | 6 | 2 | 8 |
| 3 | Chittoor | 8 | 24 | 72 | 16 | 88 | 3 | 9 | 2 | 11 |
| 4 | Kadapa | 3 | 9 | 27 | 6 | 33 | 1 | 3 | 1 | 4 |
| 5 | Prakasam | 5 | 15 | 45 | 10 | 55 | 2 | 6 | 1 | 7 |
|  | Total | 35 | 105 | 315 | 70 | 385 | 14 | 36 | 9 | 45 |

Training Methodology

- The core team will develop fortnightly FLA modules and materials with support of LTA.

- Training the Master Trainers:

  - This core team will organize the training of 45 Master trainers in 2 batches running simultaneously. For every 3 FLAs, one round of training will be conducted. Thus, the total 8 rounds and 16 batches of Master Trainers would be trained.

  - In each round of training, content for the next 3 FLA events would be covered

  - There will be 24 FLA events in a year. Covering content of 3 FLA events in each round of training, these master farmers would undergo 8 rounds of Trainings. Each training would be for 3 days.

- Training the Master Farmers: 45 Master Trainers will organize training of 385 Master Farmers (FAs identify 315 Farmers of which atleast 105 would be women and 35 Agriculture Facilitators and 35 NRM Facilitators from FAs) Total number of batches is 14

- Organising FLA Events: These 385 Master Farmers will then organize fortnightly FLA events.

- List of Training Venues: Since capacity building is the responsibility of LFA, all CB coordinators will identify suitable training venues at district.

Monitoring Indictors for FLA

- Each FLA will be captured by a mobile application (photo, geo-coordinates, attendance, and few other fields).

- It is important that each farmer/ participant in FLA register by paying a nominal fee. This fee has to be decided.

- A web tool will be developed for registration of the farmers for FLA. This tool will be helpful in tracking the continuity of the participants to the FLA. The same can facilitate tracking the FLA events and related updates.

- This web tool will generate a dashboard will be prepared at the central level where FPO, FA, LFA, District and state level summary of FLA will be automatically compiled. This will be used as monitoring tool at such levels

- FA should prepare and upload the following documents for each FLA session, in addition to the register maintained at each Learning Site, FLA wise

- Indicators:

- Date, place and sl number of FLA

- Attendance (online or a sheet?)

- Capture the following

  - AESA

  - Participatory Research Activities (PaR)

  - Special Topics covered

  - Action Points/Decisions Taken

- Photograph showing the participants

- Important Photos supporting the FLA 2-3

Budget:

Note:

- It is expected that for 1st year, FLAs would be organised for the cropping period.

- Starting from July, the cropping period would remain till December

- Total number of FLAs to be organised is 12 during this 6 months of period

- On average 30 participants would participate in each FLA.

- Training to master farmers would be organised once in 2 months covering content for next 4 FLA sessions. Thus, there will be 3 rounds of training to Master Farmers

- Training to master trainers to train master farmers also will be organised in 3 rounds

- There will be resource kit at each FLA. During the first year, Resource kit for farmers/ participants is not planned.

- Annexure-3: Budget for Training 45 Master Trainers

- Number of bathes 2

- Number of participants/ batch: 22-23

- No of days/batch: 3

- No of rounds of trainings in a year: 8 (one per every 3 FLAs)

- Place of Training: District (All residential trainings should be conducted where accommodation is available)

| Sl No | Particulars | 3 days Residential @ Dist |  | Amount |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Unit | Unit Cost |  |
| 1 | Food and Refreshment Cost (Participants + RP + Support staff | Participant | 950 | 20900 |
| 2 | Hall Rent and Logistics | 3 Days | 15000 | 15000 |
| 3 | Resource Persons Hon and travel | Res Person | 5100 | 5100 |
| 4 | Travel Allowance (S/DPMU, LTA, L/FA, FPO staff should claim travel from their project budgets) | Participant | 200 | 4400 |
| 5 | Stationary, Material, etc | Training Day | 1000 | 3000 |
| 6 | Night Stay | Participant | 700 | 15400 |
|  | Total |  |  | 63800 |

- Total Training cost of 1st batch (22 participants)	: 	Rs 63,800

- Total Training cost of 2nd batch (23 participants)	: 	Rs 65,650

- Total cost of 2 batches per round			: 	Rs 129,450

- Total cost for 3 rounds (6 trainings)			: 	Rs 3,88,350

- Annexure-2: Budget for Training the Master Farmers 385 (approximately 25 in each batch)

- Number of participants/ batch: 25

- Number of bathes 15 (it would cover 375 participants)

- No of days/batch: 3

- Place of Training: District

| Sl No | Particulars | 3 days Residential @ Dist |  |  | Amount |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Unit | Unit Cost |  |  |
| 1 | Food and Refreshment Cost (Participants + RP + Support staff | Participant | 950 | 23750 |  |
| 2 | Hall Rent and Logistics | 3 Days | 15000 | 15000 |  |
| 3 | Resource Persons Hon and travel | Res Person | 5100 | 5100 |  |
| 4 | Travel Allowance (S/DPMU, LTA, L/FA, FPO staff should claim travel from their project budgets) | Participant | 200 | 5000 |  |
| 5 | Stationary, Material, etc | Training Day | 1000 | 3000 |  |
| 6 | Night Stay | Participant | 700 | 17500 |  |
|  | Total |  |  | 69350 |  |

- Total Training cost of 1 batch (25 participants)			: Rs 69,350

- No of batches to cover 385 participants:	Approximately 15

- Total cost of 15 batches per round (to cover content of 4 FLAs)	: Rs 10,40,250

- Total cost of 15 batches training for 3 rounds (45 Trainings)		: Rs 31,20,750

- Annexure-1: Budget for Conducting FLA events (approximately 30 farmers in each event)

- Number of participants/ event/batch: 30

- Number of batches/Learning Site:2

- Number of FLA events/batch in a year: 24

- Total number of events in each learning site per year: 48

- Number of Learning sites across APDMP: 105

- Number of events in all APDMP learning sites in a year: 5200 (48*105)

- Place of Event: Learning Site

| Sl No | Particulars | Unit | No of units | Unit Cost | Amount |
| --- | --- | --- | --- | --- | --- |
| 1 | Refreshment | Participant | 30 | 30 | 900 |
| 2 | Resource Fee | FLA | 1 | 600 | 600 |
|  | Total |  |  |  | 1500 |

- Total cost of 1 FLA (30 participants)				: Rs 1500

- Total cost of 2 FLAs in Learning Site per fortnight		: Rs 3000

- Total cost of 24*2= 48 FLAs in each Learning site/ annum	: Rs 36,000

- Total cost of FLAs in 105 sites					: Rs 37,80,000

Annexure-4a: Budget for Resource Material farmer wise (to be developed centrally and supplied to FAs)

| No of participants in each FLA: | 30 |
| --- | --- |
| Total number of participants (30 farmers per FLA * 2 FLAs in each Learning site * 2 FLAs/month * 6 months* 105 Learning sites (=30*2*2*6*105) | 75600 |
| Cost of Resource Material per farmer per FLA (handouts/ brochures, etc | 3 |
| Total cost of material | 2,26,800 |

Annexure-4b: Resource Material for each learning site (to be developed centrally and supplied to FAs). This material can be used in both batches in a learning site

| Sl No | Particulars | Unit | No of units | Unit Cost | Amount |
| --- | --- | --- | --- | --- | --- |
| 1 | Posters (5*8): 10 Poster set (Flexies)/ Learning Site | Posters | 10 | 300 | 3000 |
| 2 | Total budget for 105 learning sites |  | 105 | 3000 | 315000 |

Annexure-5: Resource Kit/FLA Learning Site

| Sl No | Particulars | Unit | No of units | Unit Cost | Amount |
| --- | --- | --- | --- | --- | --- |
| 1 | Bag | No | 1 | 300 | 300 |
| 2 | Register | No | 1 | 100 | 100 |
| 3 | Participatory Action Research related exp | LS |  |  | 1000 |
| 4 | Stationary (Cello tape, Brown sheets, sketches, scales, tapes, etc) | LS |  |  | 600 |
|  | Total |  |  |  | 2000 |
|  | No of FLA Kits Required |  | 210 |  |  |
|  | Cost of all Kits |  |  |  | 420000 |

Annexure-6: Material for participant farmers: While each farmer requires a set of material to use during FLA such as cap, polythene covers, soil testing equipment, lense, etc, this year only book and pen to each participant will be provided.

| Sl No | Particulars | Unit | No of units | Unit Cost | Amount |
| --- | --- | --- | --- | --- | --- |
| 1 | Bag and Hat | No | 0 | 200 | 0 |
| 2 | Note Book+Pen | No | 1 | 30 | 30 |
| 3 | Lens, Polythene covers, voils, brush, etc | LS |  | 770 | 0 |
|  | Total |  |  |  | 30 |
|  | No of FLA Kits Required: 105 learning sites * 2 groups * 30 farmers |  | 6300 |  |  |
|  | Cost of all Kits |  |  |  | 189000 |

Summary of Budgets

| # | Item | Unit Cost | Quantity | Amount |
| --- | --- | --- | --- | --- |
| Budget 1 | Training of Master Trainers/Month batch | 129450 | 3 | 388350 |
| Budget 2 | Training of Master Farmers/15 Batches @ 1 for 4 FLAs | 1040250 | 3 | 3120750 |
| Budget 3 | Conducting FLAs/Month | 630000 | 6 | 3780000 |
| Budget 4a | Resource Material/Farmer wise | 3 | 75600 | 226800 |
| Budget 4b | Resource Material/Learning Site | 3000 | 105 | 315000 |
| Budget 5 | Resource Kit/FLA | 2000 | 210 | 420000 |
| Budget 6 | Resource Kit/Participant Farmer | 30 | 6300 | 189000 |
|  | Total |  |  | 84,39,900 |
|  | Provisioned in AWPB |  |  | 77,00,000 |