## RFS Process
Rearers field school
S.NO | STEP NUMBER | Description of step | Responsibility | Participants | Total no. Of participants | NO.OF DAYS | PLACE OF TRAINING | Budget | Remarks
1 | 1 | orientation and training on RFS along with training modules | LTA | SPMU (2) DPMU(5) LFA(9) LTA(2) | 18 | 2 |  |  | 1.Date and venue to be fixed 2.Modules to be prepared
2 | 2 | orientation and training on RFS along with training modules and collection of data , reporting system , payment system | LFA | livestock facilitators, paraworkers |  | 3 | LFA office | To be mentioned by LFA | 1.Date to be fixed 2.participant number to be mentioned | Days to be taken into account for training of paraworker
3 | 3 | Trainining on disease surveillance including contagious and non contagious diseases | LFA | paraworkers |  | 3 | LFA office | To be mentioned by LFA
4 | 4 | internship of paraworker | DPMU ,LFA ,FA | paraworkers |  | 4 | veterinary dispensary |  | participant number to be mentioned
5 | 5 | Training on shelter | LFA ,FA | paraworkers |  | 2 | FA office |  | participant number to be mentioned
6 | 6 | Training on feeding and drinking water management | LFA ,FA | paraworkers |  | 3 | FA office |  | participant number to be mentioned
7 | 7 | Training on pregnant animal care including Lambcare | LFA ,FA | paraworkers |  | 2 | FA office |  | participant number to be mentioned
8 | 8 | Training on breeding | LFA ,FA | paraworkers |  | 2 | FA office |  | participant number to be mentioned
9 | 9 | Refresher training on all activities and post evaluation on activities | DPMU ,LFA | Livestock facilitators ,paraworkers |  | 2 | LFA office |  | participant number to be mentioned

## RFS Sessions
RFS Sessions
s.no | RFS topic | Number of RFS to be conducted | Responsibility | Monitoring | support | Remarks
1 | Departmental activities 1.Deworming 2.vaccination | 6 | Livestock Facilitator and paraworker | Livestock specialist | DPMU LFA FA | 1.Indent preparation and submission to VAS by LFA 2.Availability of dewormers and vaccines by DPMU 3.Delivery of vaccines and dewormers to paraworkers by FAs 4. preparation of vaccination and deworming report by LFA
2 | Disease surveillance ,contagious and non contagious diseases | 6 | Livestock Facilitator and paraworker | Livestock specialist | LFA | Includes both theory and practical sessions
3 | shelter | 3 | Livestock Facilitator and paraworker | Livestock specialist | LFA | Includes both theory and practical sessions
4 | Feeding and water management | 6 | Livestock Facilitator and paraworker | Livestock specialist | LFA | Includes both theory and practical sessions
5 | pregnant animal care including lambcare | 6 | Livestock Facilitator and paraworker | Livestock specialist | LFA | Includes both theory and practical sessions
6 | Breeding | 6 | Livestock Facilitator and paraworker | Livestock specialist | LFA | Includes both theory and practical sessions
| Total | 33
7 | Breed improvement |  | Livestock Facilitator and paraworker | Livestock specialist | LFA | This should be done with the selected breeder for breed improvement program