# ATP – APMAS – FES – Amadaguru – Maremma FPO

# Fund Release and Expenditure Status

| Details | Timeline | Amount (Lakhs) | % in the released amount | Cumulative % of expenditure |
| --- | --- | --- | --- | --- |
| Fund Received by FPO | February, 2019 | 22.84 |  |  |
| Fund Utilized | November, 2019 | 8.50 | 37.22 | 37.22 |
| Work Completed in Dec 1- 26th payment done | 26th Dec, 2019 | 0.67 | 2.93 | 40.15 |
| Works completed and payment to be done by end of Dec, 2019 | By end of Dec, 2019 | 6.03 | 26.40 | 66.55 |
| New works to be initiated and payment by end of January | End of Jan, 2020 | 4.52 | 19.79 | 86.34 |
| New works to be initiated and payment by end of February | End of Feb, 2020 | 5.66 | 24.78 | 111.12 |
| New Works to be initiated and payment by end of March | End of March | 7.40 | 32.40 | 143.52 |

# Activities Grounded so far

- Water Tanker

- Water Troughs

- BYP-BFE

- RFS

- BRC

- Protective Irrigation

# Details of the works completed – Payment done (inception to 30th November, 2019

| Sl. No | Activities | Amount Paid |
| --- | --- | --- |
| 1 | CLIC Maintenance, Bank Charges, Clic Accountant Salary, CO Salary, Clic Anchor Salary, Office Rent, FPO Office Furniture | 530234 |
| 2 | BFE | 50000 |
| 3 | BRC | 41430 |
| 4 | RFS Events | 4720 |
| 5 | Water Tanker | 125000 |
| 6 | Water Troughs | 92000 |
| 7 | Capacity Building – Travel to Paravet | 3000 |
| 8 | Black Boards | 4200 |
|  | Total | 850584 |

# Plan for utilizing available balance fund

| Sl. No | Activities | Work Completed during 1-26th Dec, 2019 and Payment to be done | Works completed and payment to be done by end of Dec, 2019 | New works to be initiated and payment by end of January | New works to be initiated and payment by end of February | New works to be initiated and payment by end of March |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Office Maintenance, Salaries, Bank Charges | 164 | 50000 | 50000 | 50000 | 50000 |
| 2 | Livings Soils | 0 | 150000 | 249200 | 233550 | 207900 |
| 3 | Farm Ponds | 0 | 0 | 120000 | 280000 | 480000 |
| 4 | BFE | 40000 | 0 | 0 | 0 | 0 |
| 5 | BRC | 0 | 0 | 30000 | 0 | 0 |
| 6 | Feed to Pregnant ewes | 0 | 0 | 0 | 0 | 0 |
| 7 | RFS Events | 0 | 0 | 3000 | 3000 | 3000 |
| 8 | Water Tanker | 0 | 0 | 0 | 0 | 0 |
| 9 | Water Troughs | 0 | 0 | 0 | 0 | 0 |
| 10 | Well Inventory – CRP Honorarium | 0 | 0 | 0 | 0 | 0 |
| 11 | Climate Information Centre | 0 | 0 | 0 | 0 | 0 |
| 12 | Travel Allowance for PWs | 0 | 0 | 0 | 0 | 0 |
| 13 | CMSS | 21750 | 0 | 0 | 0 | 0 |
| 14 | Night Shelters | 5525 | 403325 | 0 | 0 | 0 |
| Total |  | 67439 | 603325 | 452200 | 566550 | 740900 |
| Cumulative Total |  | 67439 | 670764 | 1122964 | 1689514 | 2430414 |

# FA Staff (From Feb, 18 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | CC | 2 | 23 | 23 | 0 |
| 2 | NRM – 1 (Key) | 1 | 23 | 23 | 0 |
| 3 | NRM – 2 | 2 | 23 | 20 | 3 |
| 4 | NRM – 3 | 2 | 23 | 17 | 6 |
| 5 | Institutional Building | 2 | 23 | 23 | 0 |
| 6 | Gender | 1 | 23 | 23 | 0 |
| 7 | Agriculture Coordinator | 1 | 23 | 23 | 0 |
| 8 | Livestock | 2 | 23 | 14 | 9 |
| 9 | Accounts | 1 | 23 | 14 | 9 |
| 10 | Database Assistant | 1 | 23 | 23 | 0 |

# FPO Staff (From Dec, 18 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | Clic Anchor | 1 | 13 | 13 | 0 |
| 2 | Accountant | 1 | 13 | 13 | 0 |
| 3 | CO – 1 (From Jan, 2019) | 3 | 12 | 10 | 2 |
| 4 | CO – 2 (From Jan, 2019) | 2 | 12 | 11 | 1 |
| 5 | CO – 3 (From Jan, 2019) | 2 | 12 | 12 | 0 |

# Reasons at different levels for slow progress (Scoring out of 100)

- SPMU

Scoring as a reason for slow progress (100)

SPMU – 5.00

DPMU –14.38

LFA – 38.13

FA – 33.13

FPO – 9.38

No scope for the works proposed by farmers

  - Not giving proper guidelines

  - Not giving enough time for planning process and identification of beneficiaries

  - Ensuring uniformity across all locations in activities, thus, problem is arising in the field

  - No scope for amendments in guidelines

  - Formulating guidelines without field visits, survey.

  - Monitoring Problem

- DPMU

  - Giving delayed approvals

  - No timely approvals

  - Not able to give clarity on those works

  - Due to some differences between DPMU and LFA, admin sanctioned is getting delayed

  - Sending guidelines, estimates to LFA received from SPMU and not giving any flexibility

  - Less Monitoring and Less Support

  - Delayed issues of guidelines and frequent change of guidelines, plans, activities

- LFA

  - Delay in getting approvals

  - Changing plans and estimates several times

  - Coordination Gaps

  - Communication gaps

  - No timely monitoring

  - There is no common understanding among team

  - Not able to provide support and clarity to FA

  - No effort to get timely approvals

  - Not visiting field to provide necessary guidance

  - Not visiting FPOs every months

  - No capacity building to FPO and FA staff

  - LFA is not giving training to new staff at lower level

  - Unable to provide necessary guidance in grounding work

  - Visit to FA is limited to Field days and AGMs

  - Not giving technical support timely

  - Not having awareness on works, estimates and websites

  - Unable to convince higher ups for changes

  - Passing guidelines to FA and not visiting field regularly, due to which unable to support FA in arriving intervention plan based on field

  - Most of the review meetings held at LFA office

  - Less monitoring visits to field

  - Giving less time to FA for preparation of plans

  - Delayed response in clarifying doubts and problems

  - No training on Accounts, Tally

  - Untimely sanctions

- FA

  - Lack of Communication among team members

  - Poor in institution Building

  - No follow up for getting approvals

  - FA staff is not visiting FPO office regularly

  - FA staff is not attending BOD meetings

  - FA staff visiting FPO office, but not visiting field

  - Not initiating works immediately after getting approvals

  - FA staff is not recognizing the work/ efforts of FPO staff

  - Not enough manpower at FA level

  - Staff who are from the inception have resigned, new staff are taking time to understand the program

  - No coordination among staff and unable to necessary clarifications at needed time

  - No weekly plans and review of the work

  - This FPO cluster is located far away from FA office, except NRM facilitator, other thematic experts are visiting all three clusters. Therefore, they do not have rapport with FPO BODs.

  - Accountant position is vacant, therefore, no support and verification of book of records

  - No Team work among staff

- FPO

  - BODs and FPO Staff are not having enough orientation about program and activities

  - FPO staff has no experience on NRM works to improve progress

  - No training to FPO staff

  - No training to BODs

  - BODs are not having enough orientation/ awareness on business promotion, due to which decision taking is getting delayed

  - COs are not spending enough time in the field

  - Cluster in charges are not mingling with FPO staff

  - No BODs meeting on regular basis

  - BODs are not giving time for meetings

  - BoDs are not attending for trainings and meetings.

  - Unable to convince famers to take up activities after sanction

  - COs are changing very frequently

  - No ownership among BoDs on program

  - COs do not proper training/ awareness on any theme, therefore, they are doing same work twice/ thrice

  - BoDs involvement is not well in work execution

  - BoDs are not taking the CHCs to farmers properly

  - Some of BoDs elected are not responsible

Scoring as a reason for slow progress (100)

| Level | Rangaswamy | Prabhavati | Dhananjaya | Sreeramulu | Sahadevan | Mahaboonb | Aparna | Savitha | Average |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FPO/ BOD | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 9.38 |
| FA | 20 | 35 | 30 | 30 | 50 | 30 | 40 | 30 | 33.13 |
| LFA | 45 | 30 | 40 | 40 | 30 | 40 | 40 | 40 | 38.13 |
| DPMU | 20 | 20 | 15 | 15 | 5 | 15 | 10 | 15 | 14.38 |
| SPMU | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5.00 |

# Required support to expedite the progress

- Change of beneficiaries should be allowed in various works

- FFS

  - FFS events to be organized fortnightly only as before, instead of weekly sessions

  - Department staff to be responsible for conduction of FFS

  - Budget allocation for each FFS session is to be increased

- Estimation cost of various activities should be depend upon the feasibility of local cost

- Bottom pitching is to be allowed for farm ponds

- Frequent changes of Models, estimations and various works should not be there

- Training to FPOs staff is required

- Activities proposed by farmers should be given more priority

- BODs to be given TA and DA for their time in attending meetings

- FA should have authority for giving technical sanctions up to Rs.50000

- Work sanction according to the season

- Should follow the SSR of PR and RD

- Monthly salaries in time

- Vacant positions at FA level to be recruited

Process Followed

|  | Steps till getting sanction | Living Soils (5 patches/ 375 Acres/ 225 farmers) | Farm Ponds (4) | Steps till final payment (Night Shelter – 1) | (Night Shelter – 1) | Water Troughs (4) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Identification of Living soil patches | 40 Days Orientation by LFA 1st April, 2019 Field work – 4th April, 2019 Submission Date – 30th May, 2018 | 6 Days (May, 2019) | BoD meeting | 15 Days | 30 Days |
| 2 | Meeting with Living soil farmers |  |  | Quotation procurement |  |  |
| 3 | Farmer wise survey and document collection |  |  | Purchase material by committee |  |  |
| 4 | BoD meeting and Resolution |  |  | Farmer contribution collection |  |  |
| 5 | Preparation of Estimation |  |  | Work Monitoring by CO. FA - NRM |  |  |
| 6 | Submission of proposals to LFA |  |  | M Book Recording |  |  |
|  |  |  |  | BoD meeting for resolution for payment |  |  |
|  | Correcting the proposals | 15 Days – (June, 2019) |  | Final Payment |  |  |
|  | Discussion on budget availability and based on budget reducing target and final submission | 3rd Week of June, 2019 |  | Check Measurement by CC |  |  |
|  |  |  |  | Check Measurement by LFA |  |  |
| 7 | Approval from LFA – August, 2019 | 1st week of August, 2019 45 Days | 40 Days - July, 2019 | Check Measurement by DPMU |  |  |

# Annex – 2: FA Staff positioned, resigned and gap

| Position | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| CC | Narasimha Rao S |  |  |  |  |  |  |  | Ranga Swamy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key NRM | Sri Ramulu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM |  | Bhargav |  |  |  |  | Dhananjaya |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM |  | Sudarsan |  |  |  |  | Uday Kumar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agriculture | Sahadevan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Gender | Prabhavati |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IB | Narasimharao |  |  |  |  |  |  |  | Rangaswamy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Livestock |  |  | Lavanya |  |  |  |  |  |  |  |  |  |  | Nagendra |  |  |  |  |  |  |  |  |  |
| Accounts |  |  |  |  |  | Jakriya |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Database Assistant | Mahaboob |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |

# Annex – 3: FPO Staff positioned, resigned and gap

| Position | 2018 | 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| Clic Anchor | T Aparna |  |  |  |  |  |  |  |  |  |  |  |  |
| Accountant | K Savitha |  |  |  |  |  |  |  |  |  |  |  |  |
| CO (Jan, 19) |  | Babjan |  |  |  |  |  |  |  |  | Sudhakar | Ramakrishna Reddy |  |
| CO (Jan, 19) |  | Paresh Naik |  |  |  |  |  |  |  |  | Vijay Kumar |  |  |
| CO (Jan, 19) |  | Ramajineyulu |  |  |  |  |  |  |  |  |  |  | Sudarsan Reddy |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |