# ATP - AF-AF2 – Valasa - Sri Annapoorneswari MACS

# Fund Release and Expenditure Status

| Details | Timeline | Amount (Lakhs) | % in the released amount | Cumulative % of expenditure |
| --- | --- | --- | --- | --- |
| Fund Received by FPO | February, 2019 | 3.18 |  |  |
| Fund Received by FPO | July, 2019 | 21.53 | 100 |  |
| Fund Utilized | November, 2019 | 8.37 | 33.87 | 33.87 |
| Work Completed in Dec 1- 15th payment done | I5th Dec, 2019 | 2.02 | 8.17 | 42.05 |
| Works completed and payment to be done by end of Dec, 2019 | By end of Dec, 2019 | 4.17 | 16.88 | 58.92 |
| New works to be initiated and payment by end of January | End of Jan, 2020 | 5.72 | 23.15 | 82.07 |
| New works to be initiated and payment by end of February | End of Feb, 2020 | 2.70 | 10.93 | 93.00 |
| New Works to be initiated and payment by end of March | End of March | 1.58 | 6.39 | 99.39 |

# Activities Grounded so far

- Farm Ponds

- BRC

- CHC – Local Implements

- Horse Gram Seed distribution

- CRPs honorarium – Well Inventory

- CMSS Program

# Plan for utilizing available balance fund

| Sl. No | Activities | Work Completed by End of Nov, 2019 and Payment to be done | Work Completed during 1-17th Dec, 2019 and Payment to be done | Works completed and payment to be done by end of Dec, 2019 | New works to be initiated and payment by end of January | New works to be initiated and payment by end of February | New works to be initiated and payment by end of March |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Office Maintenance and Salaries, Bank Charges | 313109 | 52739 | 0 | 60800 | 60800 | 60800 |
| 2 | CHC local | 186200 | 32770 | 67000 | 0 | 0 | 0 |
| 3 | CMSS Program (Bags) | 7524 | 10500 | 0 | 0 | 0 | 0 |
| 4 | Water Troughs | 0 | 29575 | 42000 | 0 | 0 | 0 |
| 5 | RFS | 0 | 36000 | 0 | 18000 | 18000 | 18000 |
| 6 | Jowar Fodder seed | 0 | 28500 | 0 | 0 | 0 | 0 |
| 7 | Living Soils (Seed) | 0 | 8080 | 28000 | 0 | 0 | 0 |
| 8 | Notice Boards | 0 | 4000 | 0 | 0 | 0 | 0 |
| 9 | Farm Ponds | 165230 | 0 | 0 | 288000 | 192000 | 0 |
| 10 | BRC | 40000 | 0 | 0 | 0 | 0 | 0 |
| 11 | Horse Gram Seed | 120000 | 0 | 0 | 0 | 0 | 0 |
| 12 | CRP Honorarium (Well Inventory) | 5850 | 0 | 0 | 18000 | 0 | 0 |
| 13 | BFE | 0 | 0 | 130000 | 0 | 0 | 0 |
| 14 | Night Shelters | 0 | 0 | 100000 | 0 | 0 | 0 |
| 15 | Critical Irrigation | 0 | 0 | 50000 | 108000 | 0 | 0 |
| 16 | Feed to Pregnant Eves | 0 | 0 | 0 | 80000 | 0 | 80000 |
| Total |  | 837913 | 202164 | 417000 | 572800 | 270800 | 158800 |
| Cumulative Total |  | 837913 | 1040077 | 1457077 | 2029877 | 2300677 | 2459477 |

# FA Staff (From Dec, 17 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | CC | 2 | 25 | 25 | 0 |
| 2 | NRM – 1 (Key) | 2 | 25 | 25 | 0 |
| 3 | NRM – 2 | 1 | 25 | 25 | 0 |
| 4 | NRM – 3 | 2 | 25 | 25 | 0 |
| 5 | Institutional Building | 2 | 25 | 20 | 5 |
| 6 | Gender | 1 | 25 | 25 | 0 |
| 7 | Agriculture Coordinator | 1 | 25 | 25 | 0 |
| 8 | Livestock | 2 | 25 | 9 | 14 |
| 9 | Accounts | 1 | 25 | 25 | 0 |
| 10 | Database Assistant | 1 | 25 | 19 | 6 |

# FPO Staff (From Dec, 18 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | Clic Anchor | 2 | 13 | 13 | 0 |
| 2 | Accountant | 2 | 13 | 11 | 2 |
| 3 | CO – 1 (Aug – Dec, 19) | 1 | 5 | 5 | 0 |
| 4 | CO – 2 (Oct – Dec, 19) | 1 | 3 | 3 | 0 |
| 5 | CO – 3 (Oct – Dec, 19) | 1 | 3 | 3 | 0 |

# Reasons at different levels for slow progress (Scoring out of 100)

- SPMU

FPO Progress (30th Nov, 2019)

- As per Raghavendra Record – Rs. 2.33 Lakhs

- As per Anuradha Record – Rs, 8.38 Lakhs

- As per FPO records – Rs. 8.37 Lakhs

Cost of the estimations is less for night shelters, water toughs

  - Interventions are uniform to all 105 FPOs, however, there should be flexibility to take up works required suitable to local conditions

- DPMU

Scoring as a reason for slow progress (100)

SPMU – 30

DPMU – 10

LFA - 10

FA – 20

FPO - 30

Need to give suggestions on work execution before grounding. Giving suggestions after grounding is not beneficial much

- LFA

  - LFA staff are meeting less frequently with FA staff and FPO staff

- FA

  - Due to distance from GP to GP and Cluster to Cluster, it is taking much time in travel for subject specialists like agriculture, livestock. They have to travel almost 60-70 kms every day

  - Livestock coordinator position is vacant for the last nine months

- FPO

  - Night Shelters

    - As the estimation cost for night shelter is much low, beneficiaries are not coming forward. The estimation also not covered name board and white wash

    - Due to sand policy, procuring sand is very costly as sand reaches are very far away

  - Water Troughs

    - Sand become so cost

    - Estimation cost is very less

    - 20mm, 40mm stones need to be transported from distant location

    - Brick also so costly (each costing Rs. 6.00 to Rs. 6.50)

    - Skilled labour charging Rs,800 – Rs.900/ Day

  - Living Soils

    - Standing crop is reason for slow progress

    - Due to water in the tank, silt application is not possible

    - Farmers are asking for FYM application, instead of tank silt. However, it is very cost

  - Others

    - Due to political interference, support form BoDs are not as expected

    - BoDs attendance is less in meetings

# Required support to expedite the progress

- LFA staff need to visit more frequently and interact with FA staff and FPO to speed up the progress

- Living soils allocated Rs.10.00 lakhs, however, due to some reasons the execution is not happening as expected. Therefore, instead of silt application, FYM application need to be approved. Beneficiaries are ready to meet 50% of the FYM cost

- NRM Vacant position at DPMU to be fulfilled with suitable candidate

- Livestock vacant position at FA level to be fulfilled

# Annex – 1: Details of the works completed – Payment done (inception to 30th November, 2019

| Sl. No | Activities | Amount Paid |
| --- | --- | --- |
| 1 | CLIC Maintenance, Bank Charges, Clic Accountant Salary, CO Salary, Clic Anchor Salary, Office Rent, FPO Office Furniture | 313109 |
| 2 | Farm Ponds | 165230 |
| 3 | BRC | 40000 |
| 4 | CHC – Local Implements | 186200 |
| 5 | Horse Gram | 120000 |
| 6 | CRP honorarium | 5850 |
| 7 | CMSS Program | 7524 |
|  | Total | 837913 |

# Annex – 2: FA Staff positioned, resigned and gap

| Position | 2017 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| CC | A Rudariah |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K Anand |  |  |  |  |  |  |  |  |
| Key NRM | A Rudraiah |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K Anand |  |  |  |  |  |  |  |  |
| NRM | Gowri Sankara |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM | Timmaraju |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D Mohammed Haneef |  |  |  |  |  |  |  |  |
| Agriculture | Obulapati |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Gender | M Peddakka |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IB | T Babu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Surendra |  |  |  |
| Livestock |  |  |  | Murali |  |  |  |  | V Balaji |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Accounts | Dhananjaya |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Database Assistant |  |  |  |  |  |  | S Shameer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |

# Annex – 3: FPO Staff positioned, resigned and gap

| Position | 2018 | 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| CLIC Anchor | B Eeranna |  |  |  |  |  |  | Putta Veerappa |  |  |  |  |  |
| Accountant |  |  | Putta Veerappa |  |  |  |  | B EEranna |  |  |  |  |  |
| CO - 1 |  |  |  |  |  |  |  |  | Mahentesh |  |  |  |  |
| CO - 2 |  |  |  |  |  |  |  |  |  |  | R Jyothi |  |  |
| CO – 3 |  |  |  |  |  |  |  |  |  |  | K Mahalakshmi |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |