# ATP - HANDS-RIDS - Sri Dona Rameswara VUPSSS

# Fund Release and Expenditure Status

| Details | Timeline | Amount (Lakhs) | % in the released amount | Cumulative % of expenditure |
| --- | --- | --- | --- | --- |
| Fund Received by FPO | February, 2019 | 21.39 |  |  |
| Fund Utilized | November, 2019 | 10.96 | 51.26 | 51.26 |
| Work Completed in Dec 1- 15th payment done | I5th Dec, 2019 | 1.73 | 8.09 | 59.35 |
| Works completed and payment to be done by end of Dec, 2019 | By end of Dec, 2019 | 0.41 | 1.93 | 61.28 |
| Works in progress and payment to be done by end of Dec, 2019 | By end of Dec, 2019 | 1.97 | 9.24 | 70.52 |
| New works to be initiated and payment by end of January | End of Jan, 2020 | 4.99 | 23.33 | 93.85 |
| New works to be initiated and payment by end of February | End of Feb, 2020 | 1.50 | 7.01 | 100.87 |

# Activities Grounded so far

- Living Soils (Silt Application, Compost Pit, Plantation)

- Night Shelters

- BYP_BFE

- Farm Ponds

- RFS

- BRC

- Water Troughs

- Water Tanker

- CHC Local Implement

# Plan for utilizing available balance fund

| Sl. No | Activities | Work Completed in Dec 1- 15th payment done | Works completed and payment to be done by end of Dec, 2019 | Works in progress and payment to be done by end of Dec, 2019 | New works to be initiated and payment by end of January | New works to be initiated and payment by end of February |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Office Maintenance and Salaries, Bank Charges | 45336 | 0 | 50000 | 50000 | 50000 |
| 2 | Breeder Farm Enterprise | 55772 | 0 | 54750 | 0 | 0 |
| 3 | Farm Ponds | 48225 | 29000 | 70000 | 120000 | 0 |
| 4 | Water Troughs for Animals | 23000 | 0 | 23000 | 0 | 0 |
| 5 | Living Soils | 675 | 1300 | 0 | 177000 | 0 |
| 6 | Bore well Recharge Structures | 0 | 11050 | 0 | 124400 | 0 |
| 7 | Observation Bore wells – Bore well Installation | 0 | 0 | 0 | 0 | 100000 |
| 8 | BYP – Night Shelters | 0 | 0 | 0 | 27625 | 0 |
| Total |  | 173008 | 41350 | 197750 | 499025 | 150000 |
| Cumulative Total |  | 173008 | 214358 | 412108 | 911133 | 1061133 |

# FA Staff (From Feb, 18 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | CC | 2 | 23 | 22 | 1 |
| 2 | NRM – 1 (Key) | 1 | 23 | 23 | 0 |
| 3 | NRM – 2 | 1 | 23 | 23 | 0 |
| 4 | NRM – 3 | 2 | 23 | 19 | 4 |
| 5 | Institutional Building | 2 | 23 | 22 | 1 |
| 6 | Gender | 1 | 23 | 23 | 0 |
| 7 | Agriculture Coordinator | 2 | 23 | 20 | 3 |
| 8 | Livestock | 2 | 23 | 17 | 6 |
| 9 | Accounts | 1 | 23 | 23 | 0 |
| 10 | Database Assistant | 1 | 23 | 23 | 0 |

# FPO Staff (From Nov, 18 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | Clic Anchor | 1 | 14 | 14 | 0 |
| 2 | Accountant | 2 | 14 | 14 | 0 |
| 3 | CO – 1 (May – Dec, 19) | 2 | 8 | 8 | 0 |
| 4 | CO – 2 (May – Dec, 19) | 1 | 8 | 8 | 0 |
| 5 | CO – 3 (May – Dec, 19) | 1 | 8 | 8 | 0 |

# Reasons at different levels for slow progress (Scoring out of 100)

- SPMU

  - Funds released in Feb, 2019 against the plan submitted in May, 2018

  - Immediately guidelines for execution is not given after funds released

  - DPR is cancelled and not approved till now even after revising it for four times

  - Works identified by the FPO are not sanctioned

  - Estimations, designs are technically not sound (Night shelters)

Scoring as a reason for slow progress (100)

SPMU – 30

DPMU – 25

LFA -20

FA – 15

FPO - 10

Management cost is not released timely.

- DPMU

FPO Progress (30th Nov, 2019)

- As per Raghavendra Record – Rs. 7.68 Lakhs

- As per Anuradha Record – Rs, 19.45 Lakhs

- As per FPO records – Rs. 10.96 Lakhs

DPMU is not giving sanctions timely (ex: Farm Ponds, Living Soils)

    - Proposal submitted in April, 2019 and sanctions given in 23rd July, 2019 (Predated as April, 2019)

    - Minimum time taking for sanctions – 20 Days

    - Maximum time taking for sanctions – 90 days

  - NRM expert position is vacant in DPMU

- LFA

  - NRM Specialist vacant from August, 2019

  - Livestock specialist position is vacant from 15th October, 2019

  - Agriculture specialist position is vacant at present

    - Therefore, FA is unable to get subject related clarifications

- FA

  - Staff rotation is one reason for slow progress

  - Orientation to new members is time taking

  - Livestock and Agriculture positions are vacant now

  - Experienced staff are resigning due to no admin cost and no/ less experienced people are joining. Therefore, execution is affecting

- FPO

  - Subsequent to fund release, there was election code during which execution was not possible

  - Further, standing crop is another reason for work execution was slow

  - After getting sanctions, identified beneficiaries are not coming forward for taking up activities.

  - BoDs percentage of attendance is low most of the case to take a decisions.

# Required support to expedite the progress

- NRM Vacant position at DPMU to be fulfilled with suitable candidate

- NRM, Agriculture and Livestock vacant positions at LFA level to be fulfilled

- Agriculture and Livestock vacant positions at FA level to be fulfilled

- Timely Sanctions from DPMU

- Management cost for 3 months in advance

- Activities proposed by FPO need to be sanctioned (Land levelling, Fodder development, Horticulture)

# Annex – 1: Details of the works completed – Payment done (inception to 30th November, 2019

| Sl. No | Activities | Amount Paid |
| --- | --- | --- |
| 1 | CLIC Maintenance, Bank Charges, Clic Accountant Salary, CO Salary, Clic Anchor Salary, Office Rent, FPO Office Furniture | 474645 |
| 2 | Farm Ponds | 111612 |
| 3 | Living Soils | 102725 |
| 4 | Night Shelters | 11050 |
| 5 | Water Troughs | 92000 |
| 6 | BRC | 55130 |
| 7 | Water Tanker | 125000 |
| 8 | RFS | 13000 |
| 9 | CHC – Local Implements | 108750 |
| 10 | Rainguage | 1000 |
| 11 | Well Inventory Survey | 1500 |
|  | Total | 1096412 |

# Annex – 2: Plan for available balance fund

| Sl. No | Activities | Work Completed in Dec 1- 15th payment done |  |  | Works completed and payment to be done by end of Dec, 2019 |  |  | Works in progress and payment to be done by end of Dec, 2019 |  |  | New works to be initiated and payment by end of January |  |  | By the end of February |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | No. of Units | Unit Cost (Lakhs) | Total Amount (Lakhs) | No. of Units | Unit Cost (Lakhs) | Total Amount (Lakhs) | No. of Units | Unit Cost (Lakhs) | Total Amount (Lakhs) | No. of Units | Unit Cost (Lakhs) | Total Amount (Lakhs) | No. of Units | Unit Cost (Lakhs) | Total Amount (Lakhs) |
| 1 | Office Maintenance |  |  | 45336 |  |  | 0 |  |  | 50000 |  |  | 50000 |  |  | 50000 |
| 2 | Feed to pregnant eves |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |
| 3 | BFE |  |  | 55772 |  |  | 0 | 1 |  | 54750 |  |  | 0 |  |  | 0 |
| 4 | Water Tanker |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |
| 5 | Farm Ponds |  |  | 48225 | 1 |  | 29000 | 2 |  | 70000 | 3 | 40000 | 120000 |  |  | 0 |
| 6 | BYP Night Shelter |  |  | 0 | 2 | 5525 | 11050 |  |  | 0 | 5 | 5525 | 27625 |  |  | 0 |
| 7 | Water Troughs |  |  | 23000 |  |  | 0 | 1 | 23000 | 23000 |  |  | 0 |  |  | 0 |
| 8 | CHC Local Implements |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |
| 9 | RFS |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |
| 10 | Living Soils |  |  | 675 | 1 | 1300 | 1300 |  |  | 0 | 2 |  | 177000 |  |  | 0 |
| 11 | Borewell Recharge |  |  | 0 |  |  | 0 | 0 |  | 0 | 4 | 31100 | 124400 |  |  | 0 |
| 12 | Borewells installation – Observaiton borewell |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 10 | 10000 | 100000 |
| Grand Total |  |  |  | 173008 |  |  | 41350 |  |  | 197750 |  |  | 499025 |  |  | 150000 |

# Annex – 3: FA Staff positioned, resigned and gap

| Position | 2018 |  |  |  |  |  |  |  |  |  |  | 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| CC | D Siva Sankar Reddy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Uma Maheswara Rao |  |  |  |
| Key NRM | H Obulapathi |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM | Mahaboob Basha |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM |  | Venkatesh |  |  |  |  |  |  |  |  |  |  |  |  | Anil Kumar |  |  |  |  |  |  |  |  |
| Agriculture | J Adinarayana |  |  |  |  |  |  |  |  |  |  |  |  | Bramha Reddy |  |  |  |  |  |  |  |  |  |
| Gender | G Adinarayana |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IB | D Siva Sankar Reddy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Uma Maheswara Rao |  |  |  |
| Livestock | A Ramesh Kumar |  |  |  | Shyam Kumar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Accounts | B VIjaya Bhaskar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Database Assistant | B Manjunatha |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |

# Annex – 3: FPO Staff positioned, resigned and gap

| Position | 2018 |  | 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| CLIC Anchor | M Bhaskara |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Accountant | Aruna |  |  |  |  |  |  |  |  | Lakshmi Devi |  |  |  |  |
| CO - 1 |  |  |  |  |  |  | Ramanjineyulu | Diwakar |  |  |  |  |  |  |
| CO - 2 |  |  |  |  |  |  | K Aziz |  |  |  |  |  |  |  |
| CO - 3 |  |  |  |  |  |  | P Rajendra Prasad |  |  |  |  |  |  |  |

| Colour Index |  |
| --- | --- |
| Resigned from Job | Staff in service |