# CTR - FES-GVS – Baireddi Palle – Koundinya Balaji FPO

# Fund Release and Expenditure Status

| Details | Timeline | Amount (Lakhs) | % in the released amount | Cumulative % of expenditure |
| --- | --- | --- | --- | --- |
| Fund Received by FPO | February, 2019 | 20.76 |  |  |
| Fund Utilized | November, 2019 | 7.51 | 36.18 | 36.18 |
| Work Completed in Dec 1- 25th payment done | 25th Dec, 2019 | 2.31 | 11.13 | 47.30 |
| Works completed and payment to be done by end of Dec, 2019 | By end of Dec, 2019 | 2.48 | 11.95 | 59.25 |
| New works to be initiated and payment by end of January | End of Jan, 2020 | 5.93 | 28.56 | 87.81 |
| New works to be initiated and payment by end of February | End of Feb, 2020 | 3.14 | 15.13 | 102.94 |
| New Works to be initiated and payment by end of March | End of March | 0.74 | 3.56 | 106.50 |

# Activities Grounded so far

- Living soils

  - Silts application

  - Compost Pit

  - Plantation

- Farm Pond

- BRC

- Feed to pregnant ewes

- RFS Events

- Water Tanker

- Water Troughs

# Details of the works completed – Payment done (inception to 30th November, 2019

| Sl. No | Activities | Amount Paid |
| --- | --- | --- |
| 1 | CLIC Maintenance, Bank Charges, Clic Accountant Salary, CO Salary, Clic Anchor Salary, Office Rent, FPO Office Furniture | 355084 |
| 2 | Livings Soils (Silt Application, Compost Pits, Plantation) | 95215 |
| 3 | Farm Ponds | 34500 |
| 4 | BRC | 22940 |
| 5 | Feed to Pregnant ewes | 37485 |
| 6 | RFS Events | 36025 |
| 7 | Water Tanker | 124900 |
| 8 | Water Troughs | 44967 |
|  | Total | 751116 |

# Plan for utilizing available balance fund

| Sl. No | Activities | Work Completed during 1-25th Dec, 2019 and Payment to be done | Works completed and payment to be done by end of Dec, 2019 | New works to be initiated and payment by end of January | New works to be initiated and payment by end of February | New works to be initiated and payment by end of March |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Office Maintenance, Salaries, Bank Charges | 69500 | 0 | 54500 | 54500 | 54416 |
| 2 | Livings Soils | 0 | 0 | 98000 | 94000 | 0 |
| 3 | Farm Ponds | 50000 | 68375 | 84000 | 96000 | 0 |
| 4 | BFE | 0 | 0 | 130000 | 0 | 0 |
| 5 | BRC | 0 | 74500 | 0 | 0 | 0 |
| 6 | Feed to Pregnant ewes | 0 | 0 | 0 | 0 | 0 |
| 7 | RFS Events | 10500 | 0 | 10500 | 10500 | 10500 |
| 8 | Procurement of BYP Chicks | 0 | 0 | 0 | 50000 | 0 |
| 9 | Water Troughs | 25000 | 0 | 0 | 0 | 0 |
| 10 | Well Inventory – CRP Honorarium | 24000 | 0 | 0 | 0 | 0 |
| 11 | BYP Service Providers – data collection | 0 | 0 | 9000 | 9000 | 9000 |
| 12 | On farm trials and demonstration | 0 | 0 | 18000 | 0 | 0 |
| 13 | CMSS | 35000 | 0 | 59000 | 0 | 0 |
| 14 | Night Shelters | 0 | 104975 | 130000 | 0 | 0 |
| 15 | Data Display Boards | 7000 | 0 | 0 | 0 | 0 |
| 16 | CHC Local Implements | 10000 | 0 | 0 | 0 | 0 |
| Total |  | 231000 | 247850 | 593000 | 314000 | 73916 |
| Cumulative Total |  | 231000 | 478850 | 1071850 | 1385850 | 1459766 |

# FA Staff (From Dec, 17 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | CC | 1 | 25 | 25 | 0 |
| 2 | NRM – 1 (Key) | 1 | 25 | 25 | 0 |
| 3 | NRM – 2 | 2 | 25 | 25 | 0 |
| 4 | NRM – 3 | 1 | 25 | 25 | 0 |
| 5 | Institutional Building | 1 | 25 | 25 | 0 |
| 6 | Gender | 2 | 25 | 25 | 0 |
| 7 | Agriculture Coordinator | 1 | 25 | 25 | 0 |
| 8 | Livestock | 2 | 25 | 24 | 1 |
| 9 | Accounts | 2 | 25 | 25 | 0 |
| 10 | Database Assistant | 1 | 25 | 25 | 0 |

# FPO Staff (From Nov, 18 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | Clic Anchor | 1 | 14 | 14 | 0 |
| 2 | Accountant | 3 | 14 | 14 | 0 |
| 3 | CO – 1 | 2 | 14 | 12 | 2 |
| 4 | CO – 2 | 3 | 14 | 14 | 0 |
| 5 | CO – 3 | 1 | 14 | 14 | 0 |

# Reasons at different levels for slow progress (Scoring out of 100)

Scoring as a reason for slow progress (100)

SPMU – 20

DPMU –10

LFA - 25

FA – 20

FPO - 25

SPMU

  - Giving scope for accommodating farmers felt activities

  - Not giving salaries to FA staff regularly

  - Delayed fund release

  - Delay in sending guidelines to ground works along with funds

- DPMU

FPO Progress (30th Nov, 2019)

- As per Raghavendra Record – Rs. 4.43 Lakhs

- As per Anuradha Record – Rs, 9.65 Lakhs

- As per FPO records – Rs. 7.51 Lakhs

Not providing support in getting sanctions of activities proposed under convergence (NREGA, Agriculture and Animal Husbandry)

- LFA

  - Delayed in getting sanctions for the proposals sent

  - Not visiting in time after completion of the works

  - Not giving proper orientation before initiating any activity

  - Unable to provide technical support

  - Not giving necessary guidance by visiting field before preparing proposals

- FA

  - Staff of FA is having confusion and lack of clarity about program

  - Staff rotation

  - Some of the activities planned in the program are already being done in the field under MGNREGS

- FPO

  - BoDs are not motivating farmers enough to take up sanctioned activities

  - Enthusiasm is high in meetings and decreasing at the time of execution

  - Activities most needed by farmers are not in the plan (Deep Ploughing, Land reclamation)

  - No advance payment system for works, due to which farmers are not coming forward to undertake works

  - In Living soils, 10 loads quantity and Rs.250-00/ load is not sufficient

# Required support to expedite the progress

- BODs

  - Total Survey took almost 1 year, to take the concept to farmers it took almost one year

  - When everything is ready and team is gear up for execution, sudden rains in odd time affected work execution.

  - Now it is set everything

  - Sanctions are very lately receiving now

  - Everyone is looking for subsidy/ monetary benefit in each and every work

  - Dairy is livelihood activity in the are…. More than night shelters, any other activity for supporting dairy is having lot of demand

- FA team

  - DPMU and LFA need to provide necessary orientation about program/ activities to FA staff and FPO staff

  - SPMU to organize meetings with FA coordinators twice in a year to know their perspective

Process Followed (From Beginning to Sanction, Sanction to Final Payment)

|  | Steps till getting sanction | Farm Ponds (5) (Days) | Night Shelters (40) (Days) | Living Soils (2) | Steps till final payment | Farm Ponds (5) (Days) | Night Shelters (40) (Days) | Living Soils (2) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Village Level meeting | 15 | 10 | 15 | Discussion with Farmer |  |  |  |
| 2 | Farmer Identification |  |  |  | Discussion with BoD meeting |  |  |  |
| 3 | Collecting documents from farmers |  |  |  | Marking by FA |  |  |  |
| 4 | Location Identification |  |  |  | Execution (Earth Work, Stone Pitching, Lining) |  |  |  |
| 5 | Site visit by FA |  |  |  | Measurement |  |  |  |
| 6 | Discussion with BODs meeting for passing resolution |  |  |  | M.Book Recording |  |  |  |
| 7 | Proposal Preparation |  |  |  | Payment |  |  |  |
| 8 | Proposal Submission to LFA | 30 | 10-15 | 15 | Monitoring (CO, FA NRM, BODs, FA – CC, LFA NRM) |  |  |  |
| 9 | LFA NRM Visit |  |  |  |  |  |  |  |
| 10 | Submission to DPMU through LFA |  |  |  |  |  |  |  |
| 11 | Getting approval from DPMU through LFA |  |  |  |  |  |  |  |

# Annex – 2: FA Staff positioned, resigned and gap

| Position | 2017 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| CC | Shankar Naik |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key NRM | Chakrapani |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM | Surendra |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Sandeep Chandu |  |  |
| NRM | Nagiereddy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agriculture | SHanker Naik |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Gender | Madhukumar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Hari Krishna |  |  |
| IB | AV Ramana |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Livestock | Poorna Sankar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | T Ashok Kumar |  |
| Accounts | Kalavathi |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Madhukumar |  |
| Database Assistant | Dayavathi |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |

# Annex – 3: FPO Staff positioned, resigned and gap

| Position | 2018 |  | 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| Clic Anchor | Bhaskara |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Accountant | Kalavathi |  |  |  |  |  |  |  |  |  | Sumathi |  | Radhika |  |
| CO | Suresh Babu |  |  |  |  | Nagendra |  |  |  |  |  |  |  |  |
| CO | Manjunatha |  |  |  |  |  |  |  |  | Anil Kumar |  | M Parvathi |  |  |
| CO | G Rama Chandra |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |