# CTR - RASS-CRE – Kalikiri– Maa Bhumi MACS

# Fund Release and Expenditure Status

| Details | Timeline | Amount (Lakhs) | % in the released amount | Cumulative % of expenditure |
| --- | --- | --- | --- | --- |
| Fund Received by FPO | February, 2019 | 22.40 |  |  |
| Fund Utilized | November, 2019 | 13.90 | 62.05 | 62.05 |
| Work Completed in Dec 1- 19th payment done | I9th Dec, 2019 | 4.29 | 19.15 | 81.21 |
| Works completed and payment to be done by end of Dec, 2019 | By end of Dec, 2019 | 0.00 | 0.00 | 81.21 |
| New works to be initiated and payment by end of January | End of Jan, 2020 | 4.08 | 18.21 | 99.42 |
| New works to be initiated and payment by end of February | End of Feb, 2020 | 3.45 | 15.40 | 114.82 |
| New Works to be initiated and payment by end of March | End of March | 8.80 | 39.29 | 154.11 |

# Activities Grounded so far

- Living Soils

  - Silt Application

  - Compost pit

- Farm Ponds

- Water Troughs

- BFE

- CMSS – Bags, Weighing machine, Moisture Sensor

- Millet

- Feed to Pregnant Ewes

- RFS

- CHC –Local Implements

- Water Tanker

- BRC

# Details of the works completed – Payment done (inception to 30th November, 2019

| Sl. No | Activities | Amount Paid |
| --- | --- | --- |
| 1 | CLIC Maintenance, Bank Charges, Clic Accountant Salary, CO Salary, Clic Anchor Salary, Office Rent, FPO Office Furniture | 609493 |
| 2 | Livings Soils (Silt Application, Compost Pits, Plantation) | 127963 |
| 3 | Farm Ponds | 203906 |
| 4 | BFE | 90000 |
| 5 | BRC | 54500 |
| 6 | Feed to Pregnant ewes | 37485 |
| 7 | RFS Events | 4000 |
| 8 | Water Tanker | 60000 |
| 9 | Water Troughs | 48000 |
| 10 | Well Inventory – CRP Honorarium | 6900 |
| 11 | Climate Information Centre | 130330 |
| 12 | Travel Allowance for PWs | 2000 |
| 13 | CMSS | 16400 |
|  | Total | 1390977 |

# Plan for utilizing available balance fund

| Sl. No | Activities | Work Completed by End of Nov, 2019 and Payment to be done | Work Completed during 1-19th Dec, 2019 and Payment to be done | Works completed and payment to be done by end of Dec, 2019 | New works to be initiated and payment by end of January | New works to be initiated and payment by end of February | New works to be initiated and payment by end of March |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Office Maintenance, Salaries, Bank Charges | 609493 | 0 | 0 | 0 | 0 | 0 |
| 2 | Livings Soils | 127963 | 0 | 0 | 0 | 0 | 600000 |
| 3 | Farm Ponds | 203906 | 250000 | 0 | 230000 | 200000 | 230000 |
| 4 | BFE | 90000 | 0 | 0 | 0 | 0 | 0 |
| 5 | BRC | 54500 | 15500 | 0 | 0 | 0 | 0 |
| 6 | Feed to Pregnant ewes | 37485 | 0 | 0 | 0 | 0 | 0 |
| 7 | RFS Events | 4000 | 0 | 0 | 0 | 0 | 0 |
| 8 | Water Tanker | 60000 | 63500 | 0 | 0 | 0 | 0 |
| 9 | Water Troughs | 48000 | 0 | 0 | 0 | 0 | 0 |
| 10 | Well Inventory – CRP Honorarium | 6900 | 0 | 0 | 0 | 0 | 0 |
| 11 | Climate Information Centre | 130330 | 0 | 0 | 0 | 0 | 0 |
| 12 | Travel Allowance for PWs | 2000 | 0 | 0 | 0 | 0 | 0 |
| 13 | CMSS | 16400 | 0 | 0 | 0 | 0 | 0 |
| 14 | Night Shelters | 0 | 100000 | 0 | 90000 | 50000 | 50000 |
| 15 | CHC Local Implements | 0 | 0 | 0 | 43000 | 80000 | 0 |
| 16 | Fodder Mixer | 0 | 0 | 0 | 25000 | 5000 | 0 |
| 17 | Fodder Seed | 0 | 0 | 0 | 20000 | 10000 | 0 |
| Total |  | 1390977 | 429000 | 0 | 408000 | 345000 | 880000 |
| Cumulative Total |  | 1390977 | 1819977 | 1819977 | 2227977 | 2572977 | 3452977 |

# FA Staff (From Dec, 17 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | CC | 2 | 25 | 19 | 6 |
| 2 | NRM – 1 (Key) | 2 | 25 | 19 | 6 |
| 3 | NRM – 2 | 2 | 25 | 25 | 0 |
| 4 | NRM – 3 | 2 | 25 | 22 | 3 |
| 5 | Institutional Building | 1 | 25 | 25 | 0 |
| 6 | Gender | 1 | 25 | 25 | 0 |
| 7 | Agriculture Coordinator | 2 | 25 | 24 | 1 |
| 8 | Livestock | 1 | 25 | 22 | 3 |
| 9 | Accounts | 2 | 25 | 25 | 0 |
| 10 | Database Assistant | 3 | 25 | 25 | 0 |

# FPO Staff (From Nov, 18 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | Clic Anchor | 2 | 14 | 14 | 0 |
| 2 | Accountant | 2 | 14 | 13 | 1 |
| 3 | CO – 1 (Aug – Dec, 19) | 1 | 14 | 14 | 0 |
| 4 | CO – 2 (Oct – Dec, 19) | 1 | 14 | 14 | 0 |
| 5 | CO – 3 (Oct – Dec, 19) | 1 | 14 | 14 | 0 |

# Perceptions of Contribution/ Role of Different Agencies on Delays in Field Level Activities/ Progress (Score out of 100)

| Sl No | Agency | Scores Given by |  |  |
| --- | --- | --- | --- | --- |
|  |  | FPO and FA | LFA | DPMU |
| 1 | FPO | 20 | 30 | 30 |
| 2 | FA | 10 | 20 | 50 |
| 3 | LFA | 20 | 20 | 10 |
| 4 | DPMU | 25 | 20 | 10 |
| 5 | SPMU | 25 | 10 | 0 |

Reasons Explained by FPO/FA:

On SPMU’s Role

- Giving less time to understand the new Concepts and Guidelines

- Delay fund flow

- Delay in sending operational guidelines after release of funds.

- Frequent changes in Guidelines

- Estimation cost of Silt Application is very low

On DPMU’s Role

- No flexibility in grounding works

- Delay in Sanctions

On LFA’s Role

- LFA staff are meeting less frequently with FA staff and FPO staff

On FA’s Role

- Coordinator and NRM positions are vacant for a period of six months which is crucial

- Staff Rotation and experience staff are leaving and new ones with no experience are joining

On FPO’s Role

- Farmer are going back to take up activities after getting approval from LFA/ DPMU.

- Community is comparing everything with NREGA when it comes with community contribution – why should we

Reasons Explained by LFA:

On the FPO’s Role:

- Farmers keep on changing their decisions/ preferences

- FPO staff does not have adequate rapport with villagers

- There are huge information gaps in demonstration plots; farmers information; etc

On the FA role:

- Does not have adequate rapport with the villagers

- Information sharing/ educating efforts are not adequate in the villages

- Data gaps in program related progress/ information (accuracy/ dependability)

- Poor coordination between FA staff and Mandal Level Government officers (Inconsistency in information between government data and Project data)

- About 15% to 20% of plans/ estimates/ project proposals/ site selection are erroneous

- FA does not act on his/ her own. Field visits to FA/ Villages by LFA are compulsory to push the agenda forward

- Gaps in Staff deployment

On the Role of LFA:

- Unable to provide adequate time for field work at FA level for innovation/ experimentation

- LFA is unable to represent the cases/ issues that require flexibility (designs/ estimates/ plans/ specifications) at DMPU/ SPMU level and win the cases in favour of communities. There is no flexibility. There is no result on this process (of negotiating for flexibility)

On the Role of DPMU:

- Delay in sanctions

- No flexibility

On the role of SPMP

- Common targets are fixed uniformly across all districts/ FPOs, without any relation to field level realities

- No timely action on issuing guidelines/ circulars/ GOs to give clarity to the field level functionaries

- Delays in fund releases

Reasons as explained by DPMU:

FPO:

- No seriousness in monthly BOD meetings at FPO level.

- FPO are rigid about their position/ choice because of certain local politics

- FPO members are not physically present during supervision/ work execution/ quality control of activities

- FPO members are escaping from their roles/ responsibilities

FA:

- Team activity planning work is not happening

- Low rapport with communities

- Low or less level explanation about the project details with communities

- Superficial discussions at FPO level. Issues are not properly discussed. FA proper staff is not participating in FPO BoD meetings

- Thematic experts are not contributing effectively to their respective domains

- There is no activity planning at FA level (Monthly)

- Insecurity at FA level, They are not nurturing FPOs to self-reliance

- They are allocating time to other projects. They are not devoting full time to this project

- FA is unable to win the hearts of FPO members and change the mind sets.

- There is communication gap and disagreements between FPO and FA on several issues. Peoples

LFA:

- LFA does not have necessary skills to support and nurture FA

- There is an information gap between FA and LFA. GO/ Guidelines are not properly explained to FA/ FPOs

- There is no creativity or innovation at LFA level

- LFA team is not able to communicate any content of the project in key events. Salaries are not paid regularly (so this could the reason behind their low commitment / passive roles in the project (50% of the reason could be attributed to delayed salaries).

- Lack of seriousness/ commitment among LFA. Deployment of teams to right task/ assignment is absent.

DPMU:

- Project approvals are delayed in 10% of cases

- DPMU is not adequately staffed.

SPMU:

- No reasons

# Required support to expedite the progress

- In every budget there should be untied money, to plan and accommodate activities preferred by the community

- All Approvals can be from LFA instead of DPMI

- In time fund flow for salaries

# Annex – 2: FA Staff positioned, resigned and gap

| Position | 2017 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| CC | S Srinivasulu Naidu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Lathamma |  |  |  |  |  |  |  |  |
| Key NRM | S Srinivasulu Naidu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Obulesu |  |  |  |  |  |  |  |  |
| NRM | Gajendra |  |  |  |  |  |  |  | Rajesh |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM | Damodar |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Jagadish |  |  |  |  |  |  |  |  |  |
| Agriculture | Majula |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Manasa |  |  |  |  |  |  |
| Gender | Lathamma |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IB | Sudhakar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Livestock | Manoj |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Accounts | Hema Sekhar |  |  |  | Murali |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Database Assistant | M Swetha |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | M Bharath |  | S Rizwan |  |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |

# Annex – 3: FPO Staff positioned, resigned and gap

| Position | 2018 |  | 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| Clic Anchor | B Suresh |  |  |  |  |  |  | M Venkata Ramana |  |  |  |  |  |  |
| Accountant | S Nandini |  |  |  |  | K Yamini |  |  |  |  |  |  |  |  |
| CO | P Bhaskar |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CO | G Sreenivasulu |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CO | S Junaid Ahmed |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |