# KDP - RHGBMS-PARTNER – Chageleru – Bhiravesara MACS

# Fund Release and Expenditure Status

| Details | Timeline | Amount (Lakhs) | % in the released amount | Cumulative % of expenditure |
| --- | --- | --- | --- | --- |
| Fund Received by FPO | February, 2019 | 22.15 |  |  |
| Fund Utilized | November, 2019 | 14.79 | 66.77 | 66.77 |
| Work Completed in Dec 1- 15th payment done | I5th Dec, 2019 | 3.86 | 17.43 | 84.20 |
| Works completed and payment to be done by end of Dec, 2019 | By end of Dec, 2019 | 0.87 | 3.93 | 88.13 |
| New works to be initiated and payment by end of January | End of Jan, 2020 | 6.24 | 28.17 | 116.30 |

# Activities Grounded so far

FPO Progress (30th Nov, 2019)

- As per Raghavendra Record – Rs. 4.89 Lakhs

- As per Anuradha Record – Rs, 14.84 Lakhs

- As per FPO records – Rs. 8.37 Lakhs

Farm Ponds

- Water Troughs

- BFE

- Night shelters

- Living soils

- CHC – Local Implements

- Feed to pregnant ewes

- BRC

- RFS

# Details of the works completed – Payment done (inception to 30th November, 2019

| Sl. No | Activities | Amount Paid |
| --- | --- | --- |
| 1 | CLIC Maintenance, Bank Charges, Clic Accountant Salary, CO Salary, Clic Anchor Salary, Office Rent, FPO Office Furniture | 589786 |
|  | Livings Soils (Silt Application, Compost Pits, Plantation) | 425312 |
| 2 | Farm Ponds | 40000 |
| 3 | BFE | 95000 |
| 4 | BRC | 59300 |
| 5 | Feed to Pregnant ewes | 37558.5 |
| 6 | RFS Events | 51290 |
| 7 | Water Tanker | 125000 |
| 8 | Water Troughs | 56000 |
|  | Total | 1479246.5 |

# Plan for utilizing available balance fund

| Sl. No | Activities | Work Completed by End of Nov, 2019 and Payment to be done | Work Completed and payment by end of Dec, 2019 | New works to be initiated and payment by end of January |
| --- | --- | --- | --- | --- |
| 1 | Office Maintenance and Salaries, Bank Charges |  | 39000 | 0 |
| 2 | CHC local |  | 0 | 0 |
| 3 | CMSS Program (Bags) |  | 0 | 0 |
| 4 | Water Troughs |  | 13000 | 0 |
| 5 | RFS |  | 0 | 0 |
| 6 | Jowar Fodder seed |  | 0 | 0 |
| 7 | Living Soils (Seed) |  | 0 | 467188 |
| 8 | Notice Boards |  | 0 | 0 |
| 9 | Farm Ponds |  | 20000 | 156000 |
| 10 | BRC |  | 0 | 0 |
| 11 | Horse Gram Seed |  | 0 | 0 |
| 12 | CRP Honorarium (Well Inventory) |  | 0 | 0 |
| 13 | BFE |  | 15000 | 0 |
| 14 | Night Shelters | 386013 | 0 | 737 |
| 15 | Critical Irrigation | 0 | 0 | 0 |
| 16 | Feed to Pregnant Eves | 0 | 0 | 0 |
| Total |  | 386013 | 87000 | 623925 |
| Cumulative Total |  |  |  |  |

# FA Staff (From Feb, 18 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | CC | 3 | 23 | 20 | 3 |
| 2 | NRM – 1 (Key) | 1 | 23 | 23 | 0 |
| 3 | NRM – 2 | 1 | 23 | 23 | 0 |
| 4 | NRM – 3 | 2 | 23 | 5 | 18 |
| 5 | Institutional Building | 3 | 23 | 20 | 3 |
| 6 | Gender | 1 | 23 | 20 | 3 |
| 7 | Agriculture Coordinator | 4 | 23 | 16 | 7 |
| 8 | Livestock | 3 | 23 | 22 | 1 |
| 9 | Accounts | 4 | 23 | 20 | 3 |
| 10 | Database Assistant | 1 | 23 | 23 | 0 |

# FPO Staff (From Nov, 18 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | Clic Anchor | 2 | 14 | 13 | 1 |
| 2 | Accountant | 2 | 14 | 13 | 1 |
| 3 | CO – 1 (Aug – Dec, 19) | 2 | 14 | 12 | 2 |
| 4 | CO – 2 (Oct – Dec, 19) | 1 | 14 | 14 | 0 |
| 5 | CO – 3 (Oct – Dec, 19) | 1 | 14 | 13 | 1 |

# Reasons at different levels for slow progress (Scoring out of 100)

| Level | Reasons | Score as a reason for slow progress |
| --- | --- | --- |
| SPMU | - Frequent changes of Guidelines and Designs - Delayed fund release - Enough time is not giving to understand new concept (Less explanation) – Ex. Living Soils | 30 |
| DPMU | - More visits to field – execution is delaying - Direct interaction with beneficiaries without informing FA staff | 10 |
| LFA | - Inadequate Capacity Building of FA staff - More visits to field – execution is delaying - Improper way of dealing with farmers - Frequent changes in staff | 20 |
| FA | - Inadequate staff - Lack of exposure and experience - Due to multiple works, focus in changing | 15 |
| FPO | - Less attendance of BoDs in meetings - BoDs are not sharing decisions taken and Information shared in the meeting to community immediately - BoDs are more interested in benefitting self and not representing the community - No proper orientation to COs on program | 25 |

# Required support to expedite the progress

- Tank Silt Application cost Rs.2500-00 is not at all sufficient in terms of fund and no. of trips

- There is one area in our village, where SC farmers are more with no borewell area. In that area a big farm pond with 100*100 size need to be allowed. So many farmers and shepherd community would benefit out of the activity

- Cost estimation for farm pond is not sufficient, especially for stone revetment with lining. Where stones are not available, farmers contribution is going up to Rs.10000.00, therefore, farmers not showing interest in taking up farmponds

- In living soils, Rs. 500-00 for pitting, planting and filling of pit is very less, this need to be increased

- Timely release of budget release

- Shepherd community is not having access to veterinary services due to distance. They are asking FA livestock person for support. If primary medicines made available at FPO level, the freezer and other equipment can be utilized and services to shepherd community will get access to services within village

# Annex – 2: FA Staff positioned, resigned and gap

| Position | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| CC | T Venugopal |  |  |  |  |  | E Venkata Ramana |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C Bramhaiah |  |
| Key NRM | M Eswaraiah |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM | M Ravi |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM | D Ramesh |  |  |  |  |  |  |  |  |  |  |  |  |  | Madhavi |  |  |  |  |  |  |  |  |
| Agriculture |  | K Madhubabu |  |  |  |  | Abdul Khader |  |  |  |  |  |  |  |  |  |  | M Jagadish |  |  |  | K KIshore |  |
| Gender |  | EVenkata Ramana |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IB | T Venugopal |  |  |  |  |  | N Venkat Reddy |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C Bramhaiah |  |
| Livestock |  | Swarnalatha |  | P Nagendra |  |  |  |  |  |  |  |  |  |  | B Naga MUneppa |  |  |  |  |  |  |  |  |
| Accounts |  | C Vara PRasad |  | A Basha |  |  |  |  |  |  |  |  |  |  |  |  |  | M Ramanamma |  |  |  |  | N Gangadhara |
| Database Assistant | G Kiran Kumar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |

# Annex – 3: FPO Staff positioned, resigned and gap

| Position | 2018 |  | 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| CLIC Anchor | Krishna Reddy |  |  |  |  |  |  |  |  |  |  |  |  | Prasad |
| Accountant | Sushmitha |  |  |  |  |  |  |  |  |  |  |  | Ashok |  |
| CO - 1 | Lekha Sai |  |  |  |  |  |  |  |  |  |  |  |  | Hari prasad |
| CO - 2 | Aziz Khan |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CO – 3 | Jayaraj |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |