# KNL – CSA – CSA – C Belegal– Thungabadra FPO

# Fund Release and Expenditure Status

| Details | Timeline | Amount (Lakhs) | % in the released amount | Cumulative % of expenditure |
| --- | --- | --- | --- | --- |
| Fund Received by FPO | February, 2019 | 30.71 |  |  |
| Fund Utilized | November, 2019 | 13.39 | 43.60 | 43.60 |
| Work Completed in Dec 1- 29th payment done | 29th Dec, 2019 | 1.80 | 5.86 | 49.46 |
| Works completed and payment to be done by end of Dec, 2019 | By end of Dec, 2019 | 0.54 | 1.76 | 51.22 |
| New works to be initiated and payment by end of January | End of Jan, 2020 | 0.80 | 2.61 | 53.83 |
| New works to be initiated and payment by end of February | End of Feb, 2020 | 0.71 | 2.31 | 56.14 |
| New Works to be initiated and payment by end of March | End of March | 16.90 | 55.03 | 111.17 |

# Activities Grounded so far

- Farm Pond

- BRC

- CHC Local

- Seed (Brown top millet, Little Millet, Jowar)

- CMSS Program (Grader, Stitching Machine, Moisture sensor, Weighing machine)

- Living Soil

- BFE

- Night Shelters

- Spring Balance

- Water Tanker

- Feed to Pregnant Ewes

- Resource Person fee for PoP Survey

- OB Well Survey - CRP Honorarium

- Water Troughs

# Details of the works completed – Payment done (inception to 30th November, 2019

| Sl. No | Activities | Amount Paid |
| --- | --- | --- |
| 1 | CLIC Maintenance, Bank Charges, Clic Accountant Salary, CO Salary, Clic Anchor Salary, Office Rent, FPO Office Furniture | 563874 |
| 2 | Livings Soils (Silt Application, Compost Pits, Plantation) | 45900 |
| 3 | Farm Ponds | 118047 |
| 4 | BFE | 90000 |
| 5 | BRC | 39275 |
| 6 | Living Soils | 178000 |
| 7 | Feed to Pregnant ewes | 55699 |
| 8 | Water Tanker | 125000 |
| 9 | Water Troughs | 69000 |
| 10 | PoP Survey – CRP Honorarium | 6000 |
| 11 | Seed (Brown top millet, Little Millet, Jowar) | 3641 |
| 12 | Observation borewell survey – CRP Honorarium | 5950 |
| 13 | CMSS | 31111 |
| 14 | CHC – Local | 7778 |
|  | Total | 1339275 |

# Plan for utilizing available balance fund

| Sl. No | Activities | Work Completed during 1-29th Dec, 2019 and Payment to be done | Works completed and payment to be done by end of Dec, 2019 | New works to be initiated and payment by end of January | New works to be initiated and payment by end of February | New works to be initiated and payment by end of March |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Office Maintenance, Salaries, Bank Charges | 16300 | 51000 | 48500 | 48500 | 69500 |
| 2 | Livings Soils | 0 | 0 | 0 | 0 | 600000 |
| 3 | Farm Ponds | 0 | 0 | 0 | 0 | 937953 |
| 4 | BFE | 20500 | 0 | 0 | 0 | 0 |
| 5 | BRC | 13400 | 0 | 0 | 0 | 0 |
| 6 | Feed to Pregnant ewes | 0 | 0 | 0 | 0 | 40000 |
| 7 | RFS Events | 0 | 0 | 10000 | 10000 | 10000 |
| 8 | Water Tanker | 0 | 0 | 0 | 0 | 0 |
| 9 | Water Troughs | 0 | 0 | 0 | 0 | 0 |
| 10 | Observation Bore wells survey– CRP Honorarium | 0 | 1470 | 18000 | 9000 | 9000 |
| 11 | BYP Service Providers - Data Collection, Travel allowance | 0 | 0 | 3600 | 3600 | 3600 |
| 12 | Existing WHS – CRPs honorarium | 0 | 2400 | 0 | 0 | 0 |
| 13 | Procurement of BYP Chicks | 0 | 0 | 0 | 0 | 20000 |
| 14 | Night Shelters | 125000 | 0 | 0 | 0 | 0 |
| 15 | Audit Fee | 5000 | 0 | 0 | 0 | 0 |
| Total |  | 180200 | 54870 | 80100 | 71100 | 1690053 |

# FA Staff (From Feb, 18 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | CC | 2 | 23 | 15 | 8 |
| 2 | NRM – 1 (Key) | 2 | 23 | 15 | 8 |
| 3 | NRM – 2 | 2 | 23 | 19 | 4 |
| 4 | NRM – 3 | 1 | 23 | 23 | 0 |
| 5 | Institutional Building | 1 | 23 | 23 | 0 |
| 6 | Gender | 2 | 23 | 19 | 4 |
| 7 | Agriculture Coordinator | 4 | 23 | 20 | 3 |
| 8 | Livestock | 4 | 23 | 23 | 0 |
| 9 | Accounts | 1 | 23 | 8 | 15 |
| 10 | Database Assistant | 3 | 23 | 18 | 5 |

# FPO Staff (From Nov, 18 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | Clic Anchor | 1 | 14 | 14 | 0 |
| 2 | Accountant | 1 | 14 | 14 | 0 |
| 3 | CO – 1 | 3 | 13 | 12 | 1 |
| 4 | CO – 2 | 1 | 13 | 13 | 0 |
| 5 | CO – 3 | 1 | 13 | 13 | 0 |

# Reasons at different levels for slow progress (Scoring out of 100)

Scoring as a reason for slow progress (100)

| Level | Scores Given by |  |  | Average |
| --- | --- | --- | --- | --- |
|  | FPO/ BODs | FA | LFA |  |
| FPO/ BOD | 17 | 35 | 20 | 24 |
| FA | 30 | 15 | 20 | 22 |
| LFA | 25 | 10 | 10 | 15 |
| DPMU | 18 | 10 | 5 | 11 |
| SPMU | 10 | 30 | 45 | 28 |

Reasons mentioned by LFA

- SPMU

  - Delayed fund release

  - Frequent changes of orders, procedures

  - No salaries for the staff for almost 9 months

  - Delayed guidelines/ policies

  - Restriction of human resources

  - In consistence of project activities

- DPMU

  - Lack of Technical Knowledge for the staff

  - Inadequate support to LFAs

  - Biased in supporting LFAs

- LFA

  - Vacant staff positions at LFA (Agri, Data Base)

  - Could not be strict with FA as the salaries not given

- FA

  - Frequent change of staff

  - Staff do not have technical knowledge

- FPO

  - As the BoDs are new, they are taking time to understand their responsibilities and deliver them

  - Unable to execute works due to election code

  - Political interventions

Reasons mentioned by FA

- SPMU

  - Delayed fund release

  - Salaries not issuing properly

- DPMU

  - Changing the guidelines suddenly

  - Late permission of payments

  - No communication with FA

  - Less participation in work execution

- LFA

  - No staff for agriculture

  - No clear guidance

  - Asking data suddenly and disturbing our schedule

- FA

  - Insufficient staff

  - Less coordination among staff

- FPO

  - Less participation of BODs

  - Lack of awareness among BODs

  - BODs are not owning the program

  - FPO Staff rotation

  - COs do not have field experience

  - Delayed of acceptance activities by beneficiaries farmers

Reasons mentioned by FPO

- SPMU

  - CHC module in web Portal to have columns as local CHC register

  - Untimely budget release

  - Unable to giving clarification on works execution along with budget

- DPMU

  - Changes of Planning

- LFA

  - As this is the existing FPO before APDMP project, there are two bodies of BoDs with 9 members each. There are 5 women in both the bodies. One is looking after APDMP and another is looking after other projects.

  - LFA is unable to convince community to get necessary support

- FA

  - Not assigning works in time

- FPO

  - Farmers are not interested in giving personal documents and taking lot of time to give necessary documents

  - Work division among COs is not there

  - BoDs are not responding timely

  - Farmers are not positive about the program and not supporting us

# Required support to expedite the progress

- IB position at LFA level to be contributed as the system is now in performing stage

- SPMU should not undermine the capacities of subject matter specialists

- SPMU should not change decisions suddenly

- Timely fund release

- Quick changes of activities/design/ estimation cost should not be there

- Frequent changes of plan, approval of funds should not be there, as changes cannot be done once communicate to community

- Clear understanding of instructions to FPO staff

- Uniform salary pattern to FPO staff across categories is not welcoming

- Salary to be increased to CLic anchor and accountant

- Performance of FPO staff to be done for salary increase – as per the agreement

- FA has to create awareness among BoD members

- SPMU to take a decision to have a meeting with concerned MLAs not to involved in APDMP

- Guidelines required how to coordinate with Sachivalaya staff and FA staff

- Role clarity between LFA/ FA/ Sachilavalaya taff

- Convergence activities – DPMU to put effort in a way that it is sanctioned

- BoDs travel expenditure need to be reimbursed

- Stop giving impossible timelines – need to give enough time for getting information

- Finance related information should be through Tally only… but with no other software means

- LFA financial person should play active role in guideline, nurturing and maintaining the data

- Financial data editing option to be available with FPO Accountant/ FA/ LFA

- Seeing option of financial data should be there with FPO/ FA/ LFA

- Review with LFAs at SPMU level should be based on Tally data only.

- MoUs to be renewed with LFA

Process Followed

From Beginning to Sanction

|  | Steps till getting sanction | Farm Ponds (6) | BYP Night Shelters (20) | BYP Night Shelters (80) | Living Soils (98 Ha) | Steps till final payment (Night Shelter – 1) | Farm Ponds (6) | BYP Night Shelters (20) | BYP Night Shelters (80) | Living Soils (98 Ha) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | BoDs meeting – discussion | 15 Days (January, 2019) | 7 Days | 45 Days | 30 Days | Marking | 10 Days | 15 Days | 30 Days | 20 Days |
| 2 | Meeting with farmers |  |  |  |  | JCB Hiring |  |  |  |  |
| 3 | Beneficiaries list – documents collection |  |  |  |  | Execution |  |  |  |  |
| 4 | Feasibility study |  |  |  |  | Earth Work |  |  |  |  |
| 5 | Resolution in BoDs meeting |  |  |  |  | Monitoring by FA |  |  |  |  |
| 6 | Estimation Preparation |  |  |  |  | M Book |  |  |  |  |
| 7 | Preparation of Proposals and submission |  |  |  |  | LFA – Check Measurement |  |  |  |  |
| 8 | Technical Sanction | February, 2019 | Not approved so far | Immediately | 7/ 10 Days | BoD Meeting |  |  |  |  |
| 9 | Admin Sanction |  |  |  |  | BoD monitoring |  |  |  |  |
| 10 |  |  |  |  |  | DPMU Check Measurement |  |  |  |  |

# Annex – 2: FA Staff positioned, resigned and gap

| Position | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| CC | Yadava reddy |  |  |  |  | Hussian |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key NRM | Yadava Reddy |  |  |  |  | Hussain |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM |  | Hussain |  |  |  | Darga Mastan Vali |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM | Giddaiah |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agriculture | Janardhan |  |  |  |  | Sivaram |  | R Ashok |  |  |  |  |  |  |  |  | Veera PRakash |  |  |  |  |  |  |
| Gender | Kanthamma |  |  |  |  |  |  |  |  |  |  |  | K Seethamma |  |  |  |  |  |  |  |  |  |  |
| IB | D Abdullah |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Livestock | Palankaiah |  |  |  |  |  |  | Lakhsmaiah |  |  | D Vijaya Kumar |  |  |  |  |  |  |  |  |  | Chandrika |  |  |
| Accounts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Bharathi |  |  |  |  |  |  |  |
| Database Assistant |  |  |  |  | Balaraj |  | MS Harikirshnba |  |  |  |  |  | Peddaiah M |  |  |  |  |  |  |  |  |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |

# Annex – 3: FPO Staff positioned, resigned and gap

| Position | 2018 |  | 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| Clic Anchor | M Akhani Basha |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Accountant | K Sekhar |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CO (Dec, 18) |  | Madan Gopal |  |  |  |  |  |  |  | G Veeresh |  |  | Chakrapani |  |
| CO (Dec, 18) |  | Govardhan |  |  |  |  |  |  |  |  |  |  |  |  |
| CO (Dec, 18) |  | Indra Teja |  |  |  |  |  |  |  |  |  |  |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |