# KNL - AAA-NYA - ERRAGUDI - Sri Lakshmi Sai MACS

# Fund Release and Expenditure Status

| Details | Timeline | Amount (Lakhs) | % in the released amount | Cumulative % of expenditure |
| --- | --- | --- | --- | --- |
| Fund Received by FPO | February, 2019 | 26.05 | 100 |  |
| Fund Utilized | November, 2019 | 9.49 | 36.43 | 36.43 |
| Work Completed in Dec 1- 15th payment done | I5th Dec, 2019 | 1.90 | 7.29 | 43.72 |
| Works in progress and payment to be done by end of Dec, 2019 | By end of Dec, 2020 | 7.34 | 28.18 | 71.90 |
| New works to be initiated and payment by end of January | End of Jan, 2020 | 14.85 | 57.01 | 128.91 |
| New works to be initiated and payment by end of February | End of Feb, 2020 | 0.07 | 0.07 | 129.17 |

# Activities Grounded so far

- Silt Application

- Compost Pit

- Plantation

- Night Shelters

- BY_BFE

- Feed Distribution Pregnant Sheep

- Farm Ponds

- FFS

- RFS

- BRC

- Water Troughs

- Water Tanker

# Plan for utilizing available balance fund

| Sl. No | Activities | Work Completed in Dec 1- 15th payment done | Works in progress and payment to be done by end of Dec, 2019 | New works to be initiated and payment by end of January | New works to be initiated and payment by end of February |
| --- | --- | --- | --- | --- | --- |
| 1 | Office Maintenance and Salaries | 37002 | 0 | 88000 | 0 |
| 2 | Feed to pregnant eves | 35770 | 0 | 459000 | 0 |
| 3 | Backyard for Entrepreneur | 30000 | 50500 | 0 | 0 |
| 4 | Water Tanker | 87000 | 33000 | 0 | 0 |
| 5 | Farm Ponds | 0 | 60000 | 765000 | 0 |
| 6 | BYP Night Shelters | 0 | 386750 | 165750 | 0 |
| 7 | Water Troughs | 0 | 46000 | 0 | 0 |
| 8 | CHC Implements | 0 | 150000 | 0 | 0 |
| 9 | RFS | 0 | 8000 | 7000 | 7000 |
| Total |  | 189772 | 734250 | 1484750 | 7000 |
| Cumulative Total |  | 189772 | 924022 | 2408772 | 2415772 |

# FA Staff (From Dec, 17 to Nov, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | CC | 1 | 25 | 25 | 0 |
| 2 | NRM – 1 (Key) | 2 | 25 | 23 | 2 |
| 3 | NRM – 2 | 3 | 25 | 25 | 0 |
| 4 | NRM – 3 | 2 | 25 | 25 | 0 |
| 5 | Institutional Building | 2 | 25 | 23 | 2 |
| 6 | Gender | 2 | 25 | 25 | 0 |
| 7 | Agriculture Coordinator | 2 | 25 | 23 | 2 |
| 8 | Livestock | 2 | 25 | 25 | 0 |
| 9 | Accounts | 2 | 25 | 25 | 0 |
| 10 | Database Assistant | 2 | 25 | 25 | 0 |

# FPO Staff (From Nov, 18 to Dec, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | Clic Anchor | 1 | 14 | 14 | 0 |
| 2 | Accountant | 1 | 14 | 14 | 0 |
| 3 | CO – 1 | 3 | 14 | 9 | 5 |
| 4 | CO – 2 | 3 | 14 | 13 | 1 |
| 5 | CO – 3 | 4 | 14 | 12 | 2 |

# Reasons at different levels for slow progress (Scoring out of 100)

- SPMU

Scoring as a reason for slow progress (100)

SPMU – 30

DPMU – 10

LFA -20

FA – 10

FPO - 30

Guidelines are frequently changing (Living Soils, BYP Night Shelters)

  - Fund flow is delayed, this resulted in staff resignation

  - AWPB is not approved till date

- DPMU

  - DPMU is not visiting frequently to this cluster

- LFA

  - LFA is not sending the proposals submitted to FA to DPMU. It is getting delayed

Approval from LFA

Subject expert (NRM/ Agri/ Livestock) is recommending payment of FA, then LFA team leader approving it.

Then payment is being processed by FPO. It is observed especially for NRM works

Payment Approval for completed works is getting delayed at LFA level

- FA

  - FA staff is not visiting the FPO very frequently (One NRM person is placed locally)

  - FA office is located 130 Kms away from this cluster (other two clusters of this FA are nearby)

  - For any training, meeting and orientation program at FA level, the attendance of FPO BoDs and FPO staff is always less, thus communication is not effective, due to which progress is slow

FPO Progress (By 30th Nov, 19)

- As per Raghavendra Record – Rs. 6.38 Lakhs

- As per Anuradha Record – Rs.9.68 Lakhs

- As per FPO Record – 9.49

As a principle, this FPO is making payment for completed works only, part payment is not there and therefore, progress in this FPO is slow.

- FPO

  - Labour scarcity is a big problem in the area

  - Material is not available locally, due to remote location procurement is a very costly affair

  - COs are frequently resigning

  - Due to several reasons beneficiaries identified are coming forward during execution time

  - Due to sheet rock beneath soil within 1 to 1.5 metre, execution of Farm ponds execution is getting delayed

  - No Kharif Crop in the area, thus millet promotion could not be done

  - Most of the BoDs are very busy with their occupational works, therefore, meeting other than scheduled day is difficult and taking decisions is delayed till scheduled day meeting

  - In this cluster men aged 35-50 are doing jobs in factories and going as labourers to factories. Thus labour availability is scarce and too costly.

# Annex – 1: Details of the works completed – Payment done (inception to 30th November, 2019

| Sl. No | Activities | Amount Paid |
| --- | --- | --- |
| 1 | CLIC Maintenance, Bank Charges, Clic Accountant Salary, CO Salary, Clic Anchor Salary, Office Rent, FPO Office Furniture | 375739 |
| 2 | Water Troughs for Livestock (2) | 44200 |
| 3 | BRC | 77000 |
| 4 | Poultry_BFE | 30000 |
| 5 | Fodder Seed (Stylo Hemata) | 7000 |
| 6 | RFS | 4140 |
| 7 | Farm Ponds (3) | 25732 |
| 8 | Living Soils (5 Paches) – Silt Application, Compost Pits and Plantation | 431096 |
|  | Total | 994907 |

# Annex – 2: Plan for available balance fund

| Sl. No | Activities | Work Completed in Dec 1- 15th payment done |  |  | Works in progress and payment to be done by end of Dec, 2019 |  |  | New works to be initiated and payment by end of January |  |  | By the end of February |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | No. of Units | Unit Cost (Lakhs) | Total Amount (Lakhs) | No. of Units | Unit Cost (Lakhs) | Total Amount (Lakhs) | No. of Units | Unit Cost (Lakhs) | Total Amount (Lakhs) | No. of Units | Unit Cost (Lakhs) | Total Amount (Lakhs) |
| 1 | Office Maintenance |  |  | 37002 |  |  | 0 |  |  | 88000 |  |  |  |
| 2 | Feed to pregnant eves | 140* 20 Kg | 255.5 | 35770 |  |  | 0 | 1800 * 20 KG | 255.5 | 459000 |  |  |  |
| 3 | BFE |  |  | 30000 |  |  | 50500 |  |  | 0 |  |  |  |
| 4 | Water Tanker |  |  | 87000 |  |  | 33000 |  |  | 0 |  |  |  |
| 5 | Farm Ponds |  |  | 0 | 3 | 20000 | 60000 | 5 | 153000 | 765000 |  |  |  |
| 6 | BYP Night Shelter |  |  | 0 | 70 | 5525 | 386750 | 30 | 5525 | 165750 |  |  |  |
| 7 | Water Troughs |  |  | 0 | 2 | 23000 | 46000 |  |  | 0 |  |  |  |
| 8 | CHC Local Implements |  |  | 0 |  |  | 150000 |  |  | 0 |  |  |  |
| 9 | RFS |  |  | 0 | 8 | 1000 | 8000 | 7 | 1000 | 7000 | 7 | 1000 | 7000 |
| Total |  |  |  | 189772 |  |  | 734250 |  |  | 1484750 |  |  | 7000 |

# Annex – 3: FA Staff positioned, resigned and gap

| Position | 2017 | 2018 |  |  |  |  |  |  |  |  |  |  |  | 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D |
| CC | Narasimhulu Uppara |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key NRM | B Chandra Sekhar Reddy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | S Babu |  |  |  |  |  |  |  |  |
| NRM | S Babu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | T Murlai |  |  |  |  |  |  | P Siva |  |
| NRM | S Pullareddy |  |  |  |  |  |  |  |  |  |  |  |  | N Lakhsmi Narayana |  |  |  |  |  |  |  |  |  |  |  |
| IB | Narasimhulu Uppara |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agriculture | N Radha Krishna Mutrhy |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D Hussanaiah |  |  |  |  |  |  |  |  |  |
| Gender | K J Prabhavathi |  | J bhanodaya |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Livestock | SK Himam Saheb |  |  |  |  |  |  |  |  |  | G Rangamuni |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Accounts | S Sreedhara Rao |  |  |  |  |  |  |  |  |  |  |  |  | S Raj Kumar |  |  |  |  |  |  |  |  |  |  |  |
| Database Assistant | U Venkareswarlu |  |  |  |  |  |  |  |  |  |  |  |  | S Karranna |  |  |  |  |  |  |  |  |  |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |

# Annex – 3: FPO Staff positioned, resigned and gap

| Position |  |  |  | 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| CLIC Anchor |  | M Sekhar |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Accountant |  | K Sreenivasulu |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CO - 1 |  |  |  | S Vasu Deva Reddy |  |  | U Sankara Prasad |  |  |  |  | M Ramesh |  |  |  |
| CO - 2 |  |  |  | P Siva Ganga Raju |  |  | D Subhahan |  | Y Balaiah |  |  |  |  |  |  |
| CO - 3 |  |  |  | A Narendra |  |  | Prasad |  | D Hari Babu |  |  | T Darsana Madhu |  |  |  |

| Colour Index |  |  |  |
| --- | --- | --- | --- |
| Not Applicable | Resigned from Job | Vacant Months | Staff in service |