# EFFORT-SNIRD - Donapadu Cluster Venkateswara FPO

# Fund Release and Expenditure Status

| Details | Timeline | Amount (Lakhs) | % in the released amount | Cumulative % of expenditure |
| --- | --- | --- | --- | --- |
| Fund Received by FPO | February, 2019 | 23.95 | 100 |  |
| Fund Utilized | November, 2019 | 10.56 | 44.27 | 44.27 |
| Payment to be made for the work already completed | I8th Jan, 2019 | 1.28 | 5.34 | 49.61 |
| Work in progress | By end of Jan, 2020 | 2.33 | 9.73 | 59.34 |
| Approved works, execution to be completed | End of Feb, 2020 | 11.88 | 49.60 | 108.94 |

# Activities Grounded so far

- Farm Ponds

- Backyard Poultry Unit

- Bio-resource Centre

- Rearers Farmer Group

- Data Display Boards

- Custom hiring centre – implements

- Water Tankers

- Crop Water Budget - Training

# Plan for utilizing available balance fund

| Sl. No | Activities | Immediately payment to be done for works already completed | By end of January | By the end of February |
| --- | --- | --- | --- | --- |
| 1 | Farm Ponds | 0.22 | 2.1 | 5.38 |
| 2 | Cattle Trough | 0.46 | 0.23 | 0 |
| 3 | Backyard Poultry | 0.6 |  | 0 |
| 4 | Night Shelters |  |  | 6.50 |
| Total |  | 1.28 | 2.33 | 11.88 |

# FA Staff (From Feb, 18 to Nov, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | CC | 2 | 22 | 22 | 0 |
| 2 | NRM – 1 | 2 | 22 | 16 | 6 |
| 3 | NRM – 2 | 1 | 22 | 22 | 0 |
| 4 | NRM – 3 | 4 | 22 | 12 | 10 |
| 5 | Institutional Building | 2 | 22 | 22 | 0 |
| 6 | Gender | 1 | 22 | 19 | 3 |
| 7 | Agriculture Coordinator | 2 | 22 | 12 | 10 |
| 8 | Livestock | 3 | 22 | 16 | 6 |
| 9 | Accounts | 2 | 22 | 22 | 0 |
| 10 | Database Assistant | 3 | 22 | 22 | 0 |

# FPO Staff (From Oct, 18 to Nov, 19)

| Sl. No | Position | No. of Persons worked | No. of Staff Months | No. of Staff months staff positioned | No. of months with no staff |
| --- | --- | --- | --- | --- | --- |
| 1 | Clic Anchor | 2 | 14 | 14 | 0 |
| 2 | Accountant | 2 | 14 | 14 | 0 |
| 3 | CO – 1 | 1 | 14 | 14 | 0 |
| 4 | CO – 2 | 1 | 14 | 14 | 0 |
| 5 | CO – 3 | 2 | 14 | 14 | 0 |

# AWPB Preparation and Approval

- AWPB

  - FA has prepared and submitted AWPB in August, 2019 to LFA

  - LFA after verification it has submitted the AWPB to DPMU after a week

  - Due to change of activities (Deep ploughing was included in AWPB before, later it was disallowed, Change in budget pattern for living soil) FA reworked and submitted to DPMU through LFA

  - In October, again SPMU raised queries regarding the AWPB in November, FA could able to send final AWPB by end of November, 2019

- Living Soils

  - Apart from above, living soils proposal was prepared to an extent of 31.75 acres, however, SPMU raised query to limit the extent to 30 acres only, re-adjusting the extent took much time and final proposal was submitted on 10th day of December, 2019.

- Farm Ponds

  - No. of farmers per cluster was 5 in the beginning and accordingly 5 farm ponds were sanctioned in the month of October, 2019. Though there was demand, with lot of effort only 5 beneficiaries were identified and proposal submitted.

  - Farm ponds were sanctioned with a measurement of 10*10*3. However, there was no flexibility given in the measurements based on field situation. Strictly ensured, thus, execution was delayed.

- General Observation of FA Staff on planning process

  - First Leaning site planning 100 acres – identification of works, beneficiaries and proposal preparation with all annexures took almost 2-3 month time. Later it was changed to living soils model

  - Living soils concept coined in February, 2019, after understanding the concept with an exposure visit to Aranya area, taking new concept to farmers, completing the planning took almost 3-4 months.

  - Due to this change over, crucial summer period was lost.

  - For preparation of estimate proposal, for each activity we need to prepare 3 original copies where each copy consist of 10 different documents starting from minutes, estimate, aadhar card, land patta, GIS coordinates, photo of beneficiaries and covering letter.

  - When we need to prepare estimates more works like farm ponds (22) and night shelters in the similar lines, preparing three original copies for each work is taking lot of time.

  - We are capturing photos of beneficiaries with our mobiles and taking black and white printing, sometimes due to lack of clarity of beneficiaries photo, estimates were rejected.

  - Sometimes land is in the name of the farmer, his son name is bring written as beneficiary. But DPMU is asking for VRO certification and signatures of sibblings on No objection certificate. This process is taking lot of time.

# Execution, Monitoring, Recording and Payment process

After sanctioning the execution process involved the following steps

- Giving Marking for the work

- Re confirming the Geo Coordinates

- During execution

  - CO monitors on day to day basis

  - FPO BoD member of that habitation would monitor frequently

  - FA engineer of respective GP would monitor regularly

  - LFA NRM expert visits mandatorily before very full/ part payment

- After writing Measurement book FPO resolution would be passed. This was followed by submission of payment request to LFA, after recommendation of LFA NRM expert, LFA Team Leader would be approve the payment, based on which FPO process payment in the form of Cheque.

This FPO fund utilization (inception to till Nov, 2019)

- As per Raghavendra record – 3.82 Lakhs (15.94%)

- As per Anuradha record – 6.87 Lakhs (28.68%)

- As per FPO records – 10.56 Lakhs (44.09%)

Reasons for slow progress

- Due to election execution was not possible in the beginning of this year

- After election code, standing crop was another reason for slow progress

- Change of BoDs and OBs in FPOs took so much time due to political reasons

  - Change of signatories has taken much time, payment could not be done for works executed before

- FA Key NRM facilitator also has representation in FPO project account. As Key NRM position is vacant for few months, payment could not be done

- Delayed payment for works done also reasons for slow progress

- After April month, COs salary was not paid for 4-5 months as per the LFA instructions as no work in the field. This also reason for slow progress

- Staff rotation due to delay in admin cost release was big reason for slow progress

- Due to new opportunities in the market, identifying suitable candidates with qualification and experience is difficult, especially agriculture and veterinary staff

- As of now Agriculture, Livestock and Gender positions are still vacant in the FA

# Annex – 1: Details of the works completed – Payment done

| Sl. No | Activities | Amount Paid |
| --- | --- | --- |
| 1 | CLIC Maintenance, Bank Charges, Clic Accountant Salary, CO Salary, Clic Anchor Salary, Office Rent, FPO Office Furniture | 608635 |
| 2 | Farm Ponds | 111176 |
| 3 | BYP _ Entrepreneur | 50000 |
| 4 | BRC | 70000 |
| 5 | RFS | 6800 |
| 6 | Data Display Boards | 4500 |
| 7 | CHC Implements | 75600 |
| 8 | Water Tanker | 117999 |
| 9 | Crop water Budget – Training | 11570 |
|  | Total | 1056280 |

# Annex – 2: Plan for available balance fund

| Sl. No | Activities | Immediately payment to be done for works already completed |  |  | By end of January |  |  | By the end of February |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | No. of Units | Unit Cost (Lakhs) | Total Amount (Lakhs) | No. of Units | Unit Cost (Lakhs) | Total Amount (Lakhs) | No. of Units | Unit Cost (Lakhs) | Total Amount (Lakhs) |
| 1 | Farm Ponds | 1 | 0.22 | 0.22 | 7 | 0.30 | 2.1 | 7 | 0.10 | 0.7 |
| 2 | Farm Ponds |  |  |  |  |  |  | 12 | 0.39 | 4.68 |
| 3 | Cattle Trough | 2 | 0.23 | 0.46 | 1 | 0.23 | 0.23 |  |  |  |
| 4 | Backyard Poultry | 1 | 0.6 | 0.6 |  |  |  |  |  |  |
| 4 | Night Shelters |  |  |  |  |  |  | 100 | 0.065 | 6.50 |
| Total |  |  |  | 1.28 |  |  | 2.33 |  |  | 11.88 |

# Annex – 3: FA Staff positioned, resigned and gap

| Position | 2018 |  |  |  |  |  |  |  |  |  |  | 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| CC | A Abdul Khader |  |  |  |  | K Rama Mohana Rao |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM | K Rama Mohana Rao |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM | M Venkata Narasimha Rao |  |  |  |  |  |  |  |  |  |  |  |  | GAP |  |  |  |  |  | M Bharath Kumar |  |  |  |
| NRM | SK Mohammad Lohiya |  |  |  |  |  |  |  |  | Gap |  |  |  |  |  |  |  |  |  | V Rajasekhar |  |  |  |
| NRM |  |  |  | Manohar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NRM |  |  |  |  | J Yohan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IB | P Sreenivasulu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K Sareen |  |  |  |
| Agriculture | S Abdul Khder |  |  |  |  | GAP |  |  |  |  |  | B Mamatha |  |  |  |  |  |  | Gap |  |  |  |  |
| Gender | Kurapati Nirmala |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Gap |  |  |  |
| Livestock | Manda Vasu |  |  |  | Gap | V Vikram |  |  |  |  |  | Gap | Kommu Jashuva |  |  |  |  |  | Gap |  |  |  |  |
| Accounts | B Narasimha Rao |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A Siva Sankar Prasad |  |  |  |  |  |  |
| Database Assistant | N Ayyappa |  |  |  |  |  |  |  |  |  |  |  |  |  |  | G Raghu |  | Y Venkat Reddy |  |  |  |  |  |

| Colour Index |  |  |
| --- | --- | --- |
| Resigned from Job | Vacant Months | Staff in service |

# Annex – 3: FPO Staff positioned, resigned and gap

| Position | 2018 |  |  | 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| CLIC Anchor | CH. Sreenivasa Rao |  |  |  |  |  | Thota Venkateswarlu |  |  |  |  |  |  |  |  |
| Accountant | V Ravi Kumar |  |  |  |  |  | M Sravanti |  |  |  |  |  |  |  |  |
| CO - 1 | Dibbaiah |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CO - 2 | P Srinu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CO - 3 | N Anjaneyulu |  |  |  |  |  |  |  |  | P Balaiah |  |  |  |  |  |

| Colour Index |  |
| --- | --- |
| Resigned from Job | Staff in service |