Annual Outcome Survey of APDMP, 2019-20

Proposal Submitted to: SPMU, APDMP

By Lead Technical Agency, WASSAN Foundation.

Coordinators from LTA:

MV Ramachandrudu and Narasimha Rao S

From SPMU:  Raghavendra Rao P, M&E

Key Summary Points:

- The exercise is mandated by APDMP Project Implementation Manual and IFAD’s standard procedures. It is taken up every year to assess the project direction towards achieving outcomes. It is proposed to be done by internal persons.

- 200 households in 20 GPs will be surveyed; FGDs with FPOs in 20 Clusters.

- SPMU to deploy 12 resource persons from among the internal staff of the project S/DPMU and L/FA for a period of about 12 days. And meets the budget for their travel, stay, food and if any additional remuneration is given – Budget estimates are provided in the note.

- LTA team will anchor the process – develop the Research questions, method, questionnaire, mobile app, data compilation and analysis. M&E person at SPMU and at LTA will anchor the process under the guidance of a senior M&E expert at LTA.

- The AOS will take a total of 30 days from the date of SPMU deploying the team.

Background:

Annual Outcome Survey (AOS) is a mandatory step for APDMP. This survey provides an opportunity to project teams to understand the direction of the project and level of achievements that the project has made in terms of its agreed outcomes. This survey is supposed to be conducted by internal teams of the project. IFAD has developed a detailed technical manual for conducting this AOS. Following this guidelines, WASSAN developed this proposal for conducting the Annual Outcome Survey of APDMP, for the consideration of SPMU.

Objectives of the Proposal:

- Measure changes happening at the household level in terms of livelihoods and food security during the project life;

- Assess targeting efficiency;

- Provide evidence of project success or failure;

- Provide timely performance information necessary to undertake corrective actions.

Duration of the Assignment:

- 45 Days from the date of approval. It also depends on the deployment of project staff who are expected to conduct this survey (as this survey is supposed to be an internal exercise of the project teams). If the internal staff deployment is delayed, the AOS would also be delayed to that extent.

Expected Output from the assignment:

- A report on the level of achievements of the project in terms of agreed outcomes till now.

- A report on enabling and disabling conditions for realizing the outcomes of the project

Broad Framework for Annual Outcome Survey:

- Following the broad contours of the technical manual on this subject by IFAD, WASSAN developed the methodology/ tools/ indicators as per the project design/ manual.

- The proposed framework for assessing the outcomes of APDMP looks at the following sequence/ chain of events for each cluster of activities that was taken up in APDMP. Various indicators are identified for each level and key questions are developed to understand/ assess the level of achievement of project.  (Picture No 1).

- It is proposed that successful completion of activities will produce an output. The utilization of this output requires enabling conditions and efforts by farmers. When these two conditions are satisfied, the output would be utilized and outcomes would be generated. These outcomes could be short term outcomes and long term outcomes. This sequence/ connected chain of eventualities is taken as basis for identifying the outcome indicators (with the support of key questions/ indicators) and make an assessment/ statements on the outcomes of the project.

Picture No 1: Picture No 1: Broad Framework for Conducting Annual Outcome Survey of APDMP

It is proposed that outcomes (short term and long term) would be achieved only when the activities are completed (as per project guidelines) and enabling conditions are created to use the outputs appropriately.

- The indicators are developed for quantifying the level of achievement and key questions at each level help to generate the required data on project outcomes.

- The check list of key questions/ indicators is presented in Annexure No 1. The key questions of this checklist would be used as basis for developing data on indicators of outcomes and making statements/ assessment of outcomes. This process of data synthesis/ analysis would be organized by WASSAN.

- From this data, the report would make key statements on the achievements of the project in terms of its outcomes. As an illustration, the following statements could explain the outcomes of a particular activity.

  - X % of sample respondents could establish required enabling conditions for appropriate utilization of outputs and made necessary efforts to utilize the outputs. (Eg: In case of farm pond, 75% of farm ponds received rainfall; farm ponds got filled and farmers made efforts to utilize water for irrigating crops)

  - Out of this X%, Y% of respondents could achieve short term outcomes. (Eg: out of 75% farmers who full filled the enabling conditions, 60% could protect the crops and yield of the crops)

  - Out of this X%, Z% of respondents could achieve long term outcomes.   (Eg: Out of 75% of farmer families, who fulfilled the enabling conditions, 50% of farmers earned higher income; 45% of farmer families consumed better foods from their field; 68% of farmers have established drought mitigation systems in his/her fields)

# Study Sample

- A sample of 200 households selected randomly in project areas which includes project beneficiaries and non-beneficiaries as a comparison group.

- Four GPs in each district to a total of 20 Gram Panchayats (GPs) from five districts would be selected on random sampling method covering all 9 LFAs.

- From these 20 GPs, 10 households in each GP covering beneficiary (8) and non-beneficiary (2) categories would be selected to a total sample of 200 households on random sampling method.

- The sample will be selected in consultation with SPMU. Households will be selected based on the MIS/ field level data for project beneficiaries and randomly for control population.

- Based on the MIS of the project, main activities/ clusters of activities are selected for developing a ‘map of outcome indicators/ key questions’. (Annexure no 1). This annexure will be improved further based on the inputs from SPMU.

# Strategy for conducting the AOS

- Team Deployment:

  - A team of 12 members (9 from LFAs and 3 from FAs) who have been trained and involved in such a participatory studies would be selected. Out of 12 members, a two member team of six groups would be formed.

  - One team would visit a district to conduct AOS in selected GPs in the district. Efforts would be made that team members of one district/ FA would be sent to other district so that, biasness would be avoided in collecting the information from the households.

  - Each team would spent 2 to 3  days in a Gram Panchayat and do the following …

- Study 10 selected households by administering the pre tested questionnaire

- One Focus Group discussion with the community

- One Key Informant Interview (FPO Chairperson/ FPO Active BOD member/ FPO Clic Anchor) – through a questionnaire

- Orientation Program for Teams:

  - WASSAN will conduct an orientation program for the field investigators. After this orientation program, five teams will be formed to conduct the field work. Each team will spend their time for 6 days in a given location (LFA).

- 1 Day for orientation about AOS and Checklist

- 1 Day in field for familiarizing of questionnaire (Pre –testing)

- Six days in a district to cover four selected GPs (2 to 3 days in each GP to cover 10 HHs, 1 FGD and 1 Key Informants interview)

# Roles of Different Agencies:

- Role of FA

  - Informing the selected 10 Households about the study and date of the visit, so that they will be available

  - Informing the BoDs about the survey and identifying the  one or two key informants among BODs who are actively involved in the project implementation and who can articulate their experience in the project

  - FA team to be available in the field on the scheduled day to support enumerating team in finding beneficiaries.

  - Organize the travel/ logistics for the field investigator team during the field work.

- Role of LFA and DPMU

  - Deploying a member from their team for a period of one week as per the instructions of SPMU

- Role of SPMU

  - Sending a correspondence to all concerned DPMUs and LFAs about the AOS

  - Deployment of the team members for the study (12 Team members and 1 person for coordination)

  - Payment to the deployed teams (their travel, stay and food costs and remuneration, if any).

  - Organizing a day orientation to enumerating team at SPMU

  - Connecting the ODK questionnaire to the APDMP server for data storage and retrieval

  - Approving the questionnaire and schedule of AOS

  - Giving guidelines/ instructions for fund release to meet the cost of  travel, food and accommodation for enumerating team

- Role of LTA

  - Selection of Sample (20 Gram Panchayats)

  - Selection of Households in selected GPs in consultation with SPMU

  - Designing the Questionnaire

  - Finalization of the Questionnaire in consultation with SPMU

  - Orientation of enumeration team on AOS and Questionnaire

  - Data cleaning, classifying, consolidation, analysis and report writing

  - Sharing the report with SPMU.

- Role of Enumerating team

  - Collecting information by conducting interviews with selected household head, key informants and through Focus Group Discussion

  - Filling up of all questions in the questionnaire in ODK

  - Giving a brief report on findings of focus group discussion and observations made by them

Budget:

- Budget required for this assignment is presented in the following table.

| NO | Item | Unit | Unit Cost Rs/ Unit | Quantity | Amount Rs |
| --- | --- | --- | --- | --- | --- |
| 1 | Training Program for field testing/ orienting field investigators on AOS (15 persons for 6 days including class room sessions; field work in four GPs; including food, accommodation; travel of 15 participants for 6 days) | Participant Day | 1500 | 90 | 135000 |
| 2 | Travel, food, Accommodation of Field Investigators to selected GPs (2 person Team X 10 days/ District X 5 Districts X 2000 Rs/ Person/ Day) | District | 40000 | 5 | 200000 |
| 3 | SPMU to decide on if additional remuneration/ incentive is required for the deployed teams |  |  |  |  |
| 3 | Total |  |  |  | 335000 |

- Local travel from FA to selected GPs has to be arranged by LFA. This cost is not included in the budget. Similarly, Representatives of FA/ LFA/ DPMU have to participate in the field work during AOS.

Deployment from LFA:

From LTA, one additional person month of a senior colleague is required for conceptualizing the study, training and data analysis in addition to the Process Monitoring person.

Time Line: after formal approval date of the SPMU

- Finalizing the study methodology: 4 days

- Training of the  internal team constituted for the purpose including field testing: 6 days

- Conduct of study:

- Data analysis and final report

Annexure No 1: Draft – to be finalized.

Outcome Paths for Each Cluster of Activities in APDMP

Water Harvesting Structures - Farm Pond – Outcome Pathways

| Activities of the Project | Key Questions | Enabling Conditions/ Actions by Farmers | Key Questions | Outputs | Key Questions | Short term Outcomes | Key Questions | Long term Outcomes | Key Questions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Execution of Farm Ponds | When was it completed in full shape? (MMYY) | Rain fall/ Farm pond is filled with run off | Whether farm pond filled with rain water? If No skip entire checklist? If Yes? | Number of fillings/ water stored in farm ponds | How many times it was filled with water till date? Whether and how a pump for lifting water is arranged for? | Crop is stabilized/ protected from drying during dry spell, in XX number of acres | What changes observed with the existence of farm pond? - Crop stabilized - Crop Intensity increased - Crop Diversity increased - Area is extended | Increased yields | Yield (Qntls/ acre)? - Before Farm Pond - After Farm Pond? |
|  |  | Water in farm pond is used for irrigating crops | Whether crop is taken up under farm pond? If No, skip entire checklist? If Yes What crop is/ are grown under Farm Pond? - Before Farm Pond? - After Farm Pond? | Additional area brought into cultivation | What is the extent of land cultivated? - Before Farm Pond? - After Farm Pond? |  |  | Increased incomes |  |
|  |  | Famers has access to equipment to lift/ carry water from farm pond to fields | Do you own water lifting equipment from farm pond? If No? Did you access it from CHC? If No? How did you lift water from pond? |  |  |  |  | Increased diversity in crops |  |

| Living Soils (Tank Silt Application; Biomass Trees and Compost Pits) – Outcome Pathways |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activities by Project | Key Questions | Enabling Conditions/ Actions by Farmers | Key Questions | Outputs | Key Questions | Short Term Outcomes | Key Questions | Long Term Outcomes | Key Questions |
| Tank Silt Application | What is the extent of land benefitted with silt application? When was it completed/ applied? | Rainfall |  | Improved physical/ chemical conditions of soil | What is the purpose for opting silt application? Did you achieve that after silt application? | Improved seed germination; plant growth, plant survival is observed | What crop is sown in that land? Extent of are cultivated? After silt application, did you observe any following change/ s - Seed Germination - Plant growth - Plant density - Plant Survival | Crop is stabilized/ intensified/ diversified on long term basis |  |
| Timely plantation of biomass trees | When was plantation done? And How many? What are the species planted? | Protection of Plants | What protection measures taken to protect saplings planted? | Improved humus/ biological actions in soil |  | Decreased expenditure on chemical fertilizers |  |  |  |
|  |  |  |  | Availability of biomass/ tree litter in the fields |  |  |  |  |  |
| Digging Compost Pits | When was it completed? | Collection of Tree Litter/ other material and Filling/ Refilling the compost pit | Whether the pit was filled with crop residues, tree litter? | Availability of manure in the field |  | Decreased number of watering/ irrigations | Did you observe the following changes? Decrease in no. of watering? Decreased in frequency of watering? |  |  |
|  |  | Application of manure to the soils | Whether manure is ready for application? |  |  | Crop yields increased | Yield (Qntls/ acre)? - Before Farm Pond - After Farm Pond? |  |  |
|  |  | Crops are cultivated on the rain-fed lands, where manure is applied | Manure applied or not? |  |  | Incomes from crops increased |  |  |  |

| BYP Entrepreneur – Outcome Pathways |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activities from Project | Key Questions | Enabling Conditions/ Actions from Farmers | Key Questions | Outputs | Key Questions | Short Term Outcomes | Key Questions | Long Term Outcomes | Key Questions |
| BYP entrepreneur is identified, trained and supported to get established as entrepreneur in the project villages | Do you have previous experience in poultry rearing? Yes or No | Sufficient space with shade/ water/ feed/ protection is available for the enterprise | Extent of area (Acres) allocated for poultry? When was the plantation done in that poultry shed area? Do you have permanent water source? Yes or No | XX number of chicks are available for YY families for rearing chicks in their backyards | How many chicks supplied so far to BYP-HH beneficiaries? How many BYP-HH supplied chicks? | YY Number of families regularly rear back yard poultry, without breaking the cycles | How many BYP-HH beneficiaries regular purchasing chick? | Consumption of meat/ nutritious food increases in rural families |  |
| Vaccination/ health care services are available from paravet | Is paravet providing health care services regularly? | Entrepreneur is connected with supply chain (of native breeds of poultry chicks) | Who supplies chicks to you? Is there any agreement with the supplier for supplying chicks? | XX number of chicks get health care services (Vaccination/ feed/ others) | All birds are being vaccinated/ dewormed by local service provider? Yes or No | Entrepreneur is able to make profit by selling chick to the families in the villages | How many birds are selling in week time? How many eggs are selling in week time? | YY number of families regularly rear back yard poultry and make profit by selling them |  |
|  |  |  |  | Decreased morality rate? |  | Increase in average bird weight is observed? Yes or No |  |  |  |
| Common interest groups are established |  |  |  |  |  |  |  | Institutional arrangements/ networking with line department and markets/ support services are entrenched in the backyard poultry business |  |

| Backyard Poultry – Rearer Level Outcome Pathways |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activities by Project | Key Questions | Enabling Conditions/ Actions by Farmers | Key Questions | Outputs | Key Questions | Short Term Outcomes | Key Questions | Long Term Outcomes | Key Questions |
| Night shelters to protect chicks | When the night shelter construction was completed? What is the capacity of the shelter? |  |  | Protection for birds from predators? |  |  |  |  |  |
| Supply/ purchase of chicks from Backyard Poultry Entrepreneur | How many birds purchased each time? How many times birds are purchased so far | Spend time to rear/ protect the chicks | Who look after these birds every day? How much time spent on this activity every day? | XX number of families are engaged continuously in backyard poultry | How many birds do you purchase from entrepreneur? At what frequency? | High quality backyard poultry is produced (high unit weight; low mortality; low investment; high profit; easy to do business) | How many birds sold every month? How many eggs sold every week? | Incomes at family level improved by selling back yard poultry | What is the average selling cost of live bird? What is the selling cost of each egg? |
| Vaccination services from paravet | Is paravet providing health care services regularly? | Take care of the chicks by vaccinating/ feeding with right kind of feed | At what frequency the vaccination/ deworming is done? | Mortality rate of chicks is reduced (Bench Mark?) | Did you observe the decrease in mortality rate? | XX number of cycles of production are completed by XX number of families (Frequency Distribution of Families and Number of Cycles) |  | Health of rural families increased by consuming eggs/ meat |  |

| Small Ruminants – Outcome Pathways |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activities from project | Key Questions | Enabling Conditions/ Farmers Actions | Key Questions | Outputs | Key Questions | Short Term Outcomes | Key Questions | Long Term Outcomes | Key Questions |
| Night shelters for small ruminants | When the night shelter was constructed? What is the capacity of the shelter? | Rearing the goat/ sheep as per the guidance from RFS | Are you a member of RFS group? | Improved weight of animals | What are the lessons learned from RFS? | Rearers start improving their practices | How many practices adopted? What are the changes observed after following RFS suggested practices? - Less prone to diseases - Less expenditure on health - No distress sale - Increase in average animal weight - Decreased mortality - Increase in flock size? | Increased incomes from livestock |  |
|  |  | Rearers participate in learning events | Do you participate in RFS regularly? How many RFS sessions you have attended till now? |  |  |  |  |  |  |
| Supply of Feed (Pregnant Eves) | How many animals benefited? |  |  | Increased number of livestock/ flock size |  | Reduced distress sale of livestock |  | Families continue to rear livestock locally, without migrating far way places (for water/ fodder) |  |
| Supply of Fodder by establishing nursery/ fodder plots |  |  |  | Reduced incidents of disease/ mortality |  |  |  | Institutional arrangements for knowledge sharing; services and support systems are established to withstand the drought |  |
| Vaccination services and Deworming Services | Is paravet providing health care services regularly? |  |  |  |  |  |  |  |  |
| Rearers Field Schools are conducted |  |  |  |  |  |  |  |  |  |

| Seed Systems – Outcomes Pathways |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activities from Project | Key Questions | Enabling Conditions/ Farmers Actions | Key Questions | Outputs | Key Questions | Short Term Outcomes | Key Questions | Long Term Outcomes | Key Questions |
| Seed Production (Breeder and Foundation) | Did you grow B/ F seed before? What is the foundation seed sown area (acre)? What is the breeder seed sown area (acre)? | Quality controls systems are enforced | Do you have permanent water source? Who is providing technical guidance for crop cultivation? Did you adopt practices suggested during RFS? | XX number of seeds are produced for YY number of crops | How much yield (Qntls/ Acre) received? | XX number of crops have local production/ distribution/ sale of seeds (Self-sufficiency in seed production is achieved in XX number of crops) | How much seed quantity is distributed to farmers for sowing in next season? How many farmers were given seed in next season? | Local systems for seed production; distribution; sales are established with a view to withstand the drought and improve the diversity in crops |  |
| Seed Production (Certified Seed) | What is the crop sown area (acre)? | Quality controls systems are enforced | Do you have permanent water source? Who is providing technical guidance for crop cultivation? | XX number of farmers diversify the crops (Frequency Distribution of Farmers and Number of Crops) | How much yield (Qntls/ Acre) received? | Number of farmers from project villages who can produce good quality seeds | How much seed quantity is distributed to farmers for sowing in next season? How many farmers were given seed in next season? | Food security/ fodder security improved and protected in drought years with diversity in crops |  |
| Distribution of Navadhanya Seed Kits | What is the crop sown area (acre)? How many varieties were sown? |  | Do you have permanent water source? |  | What advantages observed in navadhanya cropping system when compare with single/ mono cropping system? - Diversity of crops - Maximum lands covers with greenery - Increased moisture holding capacity - Less chances of total crop failure? | Production of food grains from fields in drought years (XX number of farmers have produced YY kgs of grains from ZZ acres of land in drought years) |  |  |  |

| Protective Irrigation – Outcome Pathways |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity by Project | Key Questions | Enabling Conditions/ Actions by Farmers | Key Questions | Outputs | Key Questions | Short Term Outcomes | Key Questions | Long Term Outcomes | Key Questions |
| Protective Irrigation is provided | What is the crop benefitted under protective irrigation? What is the extent of area benefitted? What is the mode of water transportation? | Adequate number of water bodies are created to harvest/ store water | How many irrigations given? | Crop is protected for XX number of farmers; YY number of acres | At what stage protective irrigation is given? | Yields of Crops stabilized/ protected | What is the yield (Qntls/ Area) received? | Systems for providing protective irrigation are established to withstand the droughts for large number of farmers | What is your contribution for getting protective irrigation? |
|  |  | Adequate water is available in water bodies during dry spells, at affordable prices |  |  |  | Net income from crop is marginally reduced. But income from crop is protected. (Total loss of crop is prevented) |  |  |  |
|  |  | Run off into water harvesting structures |  |  |  |  |  |  |  |

| Farmer’s Field School/ Rearers Field Schools – Outcome Pathways |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity by Project | Key Questions | Enabling Conditions/ Actions by Farmers | Key Questions | Outputs | Key Questions | Short Term Outcomes | Key Questions | Long Term Outcomes | Key Questions |
| Farmers Field Schools are conducted | Are you a member of R/ FFS? How many sessions were conducted so far? How many R/ FFS sessions you have attended? | Theoretical sessions are conducted Farmers conducted experiments and shared observations with each other | Did you discuss these issues during R/FFS? Have you conducted any experiments on your own? OR followed any experiments by other farmers? | Farmers learn newer theories/ practices on crops/ livestock (change in knowledge). | What are the major issues in agriculture/ livestock rearing in this area? What are the new practices suggested to address these issues? | Farmers change X number of practices in crop cultivation | How many practices you have adopted? What support systems are present to follow the newer practices suggested during R/FFS? What changes do you observe after changing the practice? | More farmers adopt the improved new practices | How many farmers changed their farming practices that have with stood the drought? Could they protect yields of crops, through these new practices? Could they get better incomes from these practices? |
| Rearers Field Schools are conducted |  | Practical sessions are conducted |  | Exchange of practices/ knowledge takes place among farmers |  | Farmers change X number of practices in livestock rearing |  |  |  |
|  |  | Farmers regularly participate in the sessions |  |  |  | Crop yields improved |  |  |  |
|  |  | Farmers take up experiments/ demonstrations and engage in “learning by doing” sessions in their fields |  |  |  | Survival rate of livestock/ yields (weight of livestock) improves |  |  |  |
|  |  | Rain fall |  |  |  | Incomes from farming/ livestock increases in case of FFS/ RFS farmers |  |  |  |
|  |  | Farmers are connected to CHC/ BRC/ CMSS/ FPO |  |  |  |  |  |  |  |