# Understanding Performance of FPOs in APDMP - Challenges and Directions for Future

# A Report from Process Monitoring Team

# Jan 2020

# Background:

# WASSAN is conducting Process Monitoring of APDMP. The themes, periodicity and methodology of assessment are jointly decided by WASSAN and SPMU from time to time. As per the learning needs of SPMU, a study was conducted to assess the performance of FPOs established under APDMP. The contents of the report are organized into three parts.

- Details of the Study

- Challenges faced by FPOs in Achieving Progress

- Directions for Future Action

Part 1 - Details of the Study:

# Purpose:

# To understand the major challenges that hinder the performance of FPOs

# To suggest directions for future action for improving the performance of FPOs

# Sample Size:

# 9 FPOs (one FPO per LFA) where expenditure is low as per the information at SPMU.

# Study Period and Study Team:

# Dec 2019 and Jan 2020 and LFA members

# Methods and Tools:

# Analysis of Secondary data (at SPMU level); Analysis of Primary Data on Project at FPO

# Field visits and Focused Group Discussions with Directors of FPOs; Representatives of FA and LFA; DPMU members in limited number of cases.

# Analysis of Financial Expenditure and Human Resource Deployment

# Stakeholder wise Perception Analysis on Attributes/ reasons behind low performance (Scoring Method)

# Outputs:

# FPO wise reports

# Consolidated Report on Challenges and Future Directions

# Reasons behind Performance - Score Sheets

Part 2: Challenges faced by FPOs in Achieving Progress

The following are the main categories of challenges faced by FPOs in achieving progress.

- Inefficient Project Management Systems

  - There is considerable delay in finalizing and sharing guidelines (program/operational) and strategies activities; designs and planning procedures with FAs. There are also frequent changes in these guidelines (Living Soils, BYP Night Shelters), after initial approvals. Because of these reasons, FA team is spending more time in understanding the new/ changed guidelines; repetitive data collection, planning exercises and vague discussions. This is also causing delays/ changes/ errors in identification of beneficiaries, plans and locations. Because of this, FPO/ FA is not only losing face in the villages, but also proposals are getting rejected (as there are errors) by DPMU.

  - Delayed and untimely approvals by DPMU.

- Inflexible Program Designs and Estimates

  - In the name of ensuring uniformity in activities across FPOs, innovations and site specific activities are not included in action plans. Activities most needed by farmers are not in the work plan (Deep Ploughing, Land reclamation)

  - Approved cost norms for certain activities (like silt application, night shelters, farm ponds and water troughs) are very less.

  - Guidelines and estimates are being passed by DPMU to LFA and LFA to FA. This causes considerable delay. There is no flexibility in operational aspects.

- Inadequate support at Field:

  - Field visits by LFA are largely limited to important meetings (Eg: AGM) and to office of FA. Visits by LFA to fields/ work sites are inadequate.  FA thinks that LFAs have to give more time during field level planning and execution level events (not just meetings)

  - There is no value addition to field visits by DPMU, as these are mainly meant for monitoring. As DPMU and LFA teams visit separately, FA has to spend double the time to accompany them to field. This is taking away considerable precious time of FA from the main activities and causing delays in planning and execution of works.

  - FPOs also think that visits by FA staff to FPOs are less than adequate. FA teams are spending more time at FPO office and not going to the fields/ works sites.

- Delays in Approvals and Follow up:

- DPMU is not providing support in getting sanctions for convergence activities (NREGA, Agriculture and Animal Husbandry)

- No follow up by FA team for getting approvals. FA is not initiating works immediately after getting approvals

- LFA is not sending the proposals submitted by FA to DPMU in time, thus sanctions are getting delayed

- Delayed payment approval by LFA for completed works

- Gaps in Staff Deployment

  - Staff rotation and turn over at different levels (FPO/ FA/ LFA) is observed in majority of cases.

  - Certain staff positions (Livestock, Agriculture) are vacant at DPMU/ LFA/ FA level for considerable lengths of time.

  - As salaries are not paid in time, experienced staff at FA is resigning. Staff with no/ less experience is joining. Therefore there are several delays in the program execution.

  - Coordination among FA staff is low. They are unable to provide xnecessary clarifications/ support/ guidance in time to FPO.

  - L/ FA staff is not recognizing the work/ efforts of FPO staff who does good work

- Inadequate Capacity Building inputs

  - Inadequate Capacity Building of staff at different level (BoDs, FPO Staff/ FA) on program, technical and financial matters is leading to poor quality outputs and long delays in planning, approvals and execution.

  - Staff at all levels is not getting adequate and proper orientation before initiating any activity. Since the guidelines are changing frequently, any amount of orientation programs also find inadequate.

- Slow Growth of FPO as an institution

  - As the members of BoD are new, they are taking time to understand their responsibilities and deliver them.

  - Most of the BoDs are very busy with their occupations. Therefore meeting other than scheduled day is difficult. Any decision has to wait till the scheduled day of meeting

  - Most of the cases, there is no quorum during meetings of BoDs in monthly meetings.

  - BoDs are not sharing relevant information the with community members immediately

  - BoD members are more interested in benefits to themselves and not necessarily representing the interests of community

  - BoDs are not motivating farmers enough to take up sanctioned activities

  - BoD members are not having enough orientation/ awareness on business promotion, due to which decisions are getting delayed

- Field level reasons

  - Materials (stone, sand and other material) are not locally available. It is difficult to transport these materials from towns to remote locations in the villages. This is leading to delays and exceeding the estimate costs.

  - Advance payment system for works is not allowed. Due to these reasons, initially identified farmers and real beneficiaries are not coming forward to undertake works in time.

  - Sometimes, there is also labour scarcity in the villages which is delaying the execution of works.

  - Beneficiaries are comparing the cost norms and procedures of APDMP with MGNREGS and they are not willing to work APDMP works. (Contribution; measurement of works, quality of works, etc).

  - In some cases three clusters are not in compact area, FA team is spending more time in travelling (in one case FA team member are travelling 60-70 kms every day)

Part 3 -Directions for Future Action

The following are the suggestions/ recommendations for improving the performance of FPOs in APDMP.

  - Clarity and Communication: There is a communication gap between various levels of the project teams. This is leading to considerable confusion and delay at action. The following recommendations are proposed to minimise this.

- SPMU should make advance preparations on developing guidelines; operational strategies, cost norms and other principles of the program. SPMU should develop proper protocols for communicating the decisions at SPMU level in a systematic manner through video conferencing and other modern methods to avoid time lags and misunderstanding. Layers in communications on such matters could also be avoided by using web based communication systems.

- SPMU should avoid frequent changes in Guidelines/ procedures.

- SPMU should clearly communicate the essence of the project and indicate that they allow innovation and flexibility in the project execution, without compromising on the project objectives. SPMU has to develop separate protocols for executing standard items and innovative items.

  - Dependable Data: Currently, data on physical and financial progress and other information is not available in a consistent manner (ie. Expenditure data is not same at FPO level; FA level, LFA level and DPMU/ SPMU levels for the same date). This is creating a basis that is misleading the decision makers. The following are the suggestions/ recommendations to change this.

- SPMU should develop simple software that converts the data bases from Tally to web based templates. Only FPO staff should be allowed to edit this data base and SPMU should not edit this data.

- FPOs could update upload financial expenditure related data from Tally once in week though specially developed software. This software could convert the expenditure data into required templates and help in presenting progress on finances with accuracy on the web sites.

- Everyone could access/ use this data from these templates.

- Avoid duplicity of data collection by developing a rational and web based data collection. Let everyone use the same data so that this system gets strengthened.

  - Approvals of Plans: Currently both LFA and DPMU are working at various stages of approvals. This is leading to duplication of roles and delays. The following procedure is recommended.

- For all works, LFA can approve if the FA proposes standard and approved designs. There is no need for DPMU to play any role in approval in such cases.

- When any change is required in the designs/ estimates, such activities could be approved by SMPU/ DPMU.

- Any deviation in the approved works could be identified through ‘work audits’ and necessary action could be taken up. This will reduce time lags in approval of all works by both LFA and DMPU.

  - Role of DPMU: There is certain duplication of LFA and DPMU roles. Since DPMU is part of ATMA/ Government Agency, DPMU has certain advantages to perform certain functions, which are not possible for LFA. It is important for DPMU to perform such functions in a systematic manner. Currently, these functions are neglected. The following are the recommendations on the roles of DMPU.

- Mobilizing funds to project villages from other departments through convergence.

- Evolving support systems/ networking for marketing of products from FPOs

  - Staff Deployment: In the light of new decisions/ policy changes in the deployment of HR at LFA and FA, there is a need to delineate the HR deployment plans clearly. For this, SPMU has to create the following enabling conditions.

- Develop role clarity between Grama Sachivalaya and FA/ LFA on the agenda of FPOs, in the light of new staff deployment policy at FA/ LFA level.

- Ensure the staff of FA/ LFA/ FPOs get timely salaries regularly. This is the most important action that can improve the morale of the staff engaged in APDMP.

- Build capacities of FA staff/ FPO staff on the functioning of FPO

  - Capacity Building Program for FPOs: FPOs in APDMP are mainly established as service providers to farmers/ members. This institution is expected to provide mainly three types of services – information/ knowledge; marketing (aggregation; inputs; outputs) and equipment. These institutions need functional staff to perform these roles. The following are the recommendations.

- Build the capacities of FPO staff to perform these functions/ services.

- Develop partnership with a resource organization which can systematically build the capacities of FPO (staff; directors and members) in the context of APDMP

- Develop functional relationships between Grama Sachivalay and FPOs in a meaningful manner.

Initially SPMU team was also expected to be part of the study. However, SPMU members could not participate in the field work of the study.